## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-16
Name of the builder group |  |  |  | Raghav Reality Developers
Name of the builder company |  |  |  | Raghav Reality Developers
Name of the Project |  |  |  | Raghav Parijat
Provided Contact Details (Name & Contact No.) |  |  |  | 9768928716
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Poonam
Name / No of the Existing Building |  |  |  | Building No.72, Nehru Nagar Om CHSL Ltd
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800050808
Project location details |  | Raghav Parijat, CTS No.12(PT) & Existing Building No. 72, Nehru Nagar Om CHSL, near Building No. 73, Madhukunj Society U/c, MG Road, , Nehru Nagar, Kurla 3, Kurla East, Kurla, Mumbai - 400024.
CTS No |  | 12(PT) & Existing Building No. 72, Nehru Nagar Om CHSL
Locality |  | NA
Road |  | MG Road |  | Locality/Village |  | Nehru Nagar, Kurla 3
City |  | Kurla East |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400024
Nearby Landmark |  | Building No. 73, Madhukunj Society U/c |  | Distance from city centre: |  | 600M from Kurla Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Other Plot |  |  | Amrut Co-Operative Housing
West | NA | 12.20 m. Wide Road |  |  | Building No. 68/ MG Road
North | NA | Other Plot |  |  | Bldg No. 73, Madhukunj Society U/c |  |  |  | Kurla Kajrolkar CHSL
South | NA | Other Plot |  |  | Open Plot/ MG Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.0611349,72.8832934
Location Link |  | https://goo.gl/maps/GkdA5SkZPZ8EzYpN8?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 867.53
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 5.8401
Total FSI availaible for the project |  |  |  | 8.8401
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7669.05
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | Mhada-22/1164/2023 |  |  | Dated | 2023-10-09
Approved Floor plan No. |  | Mhada-22/1164/2023 |  |  | Dated | 2023-10-09
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-22/1164/2024/FCC/1/New |  |  | Dated | 2024-12-26
|  | This Further C.C. Extended up to top of 17th floor as per approved amended plans dtd. 09.10.2023. |  |  | Valid Upto Date | 2026-02-28
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7669.05
Approved no of units |  |  | Flats - 146
Approved no of Floors |  |  | Building No. 72 = LB + UB + Gr + 1st to 19th Floor
Proposed no of Floors |  |  | Building No. 72 = LB + UB + Gr + 1st to 19th Floor
Expected Completion |  |  | As per RERA - 30/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 72 = LB + UB + Gr + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 8 Floor Completed | , RCC upto 9 Slab, Brickwork upto 8 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 31.16% |  | 60.61% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 9 | 45% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 8 | 42.11% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 14.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | Part II Building No. 72 = LB + UB + Gr + 1st to 19th Floor | [5 empty] | Excavation Completed, 1st Basement Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation | , 1st Basement Completed
Stage of construction: |  | Excavation Completed, 1st Basement Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 9.5
Plinth |  | 14.25 | 75% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 14.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Avg. Progress % Part I & II |  | 19.33% |  | Avg. Disbursement % Part I & II |  | 49.68% |  | Plinth in process | 0
[8 empty] | Plinth completed | 0
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16000 |  |  |  | 15000 to 1600 | shailesh | 2024-12-02 | verbal & market
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 12800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.72 |  | 146 |  | 77013.729 |  | 115520.5935
Total
Grand Total |  | 0 |  | 0 |  | 0
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor for Parking, Entrance Lobby & Society Office
1 |  |  |  | 0 | 0 | Ground Floor for Parking, Entrance Lobby & Society Office
2 |  |  |  | 0 | 0 | Ground Floor for Parking, Entrance Lobby & Society Office
3 |  |  |  | 0 | 0 | Ground Floor for Parking, Entrance Lobby & Society Office
4 |  |  |  | 0 | 0 | Ground Floor for Parking, Entrance Lobby & Society Office
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area + Balcony | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.72
Lower Basement For Pump Room
Upper Basement For Parking Pit
Ground Floor For Society Office, Entrance Lobby & Parking
1st Floor For Residential & Fitness Centre | [10 empty] | 10.764
1 |  | 1BHK | 425.8238 | 0 | 638.7358 | 1st Floor For Residential & Fitness Centre
2 |  | Fitness Centre
3
4 |  | 1.5BHK | 529.3735 | 0 | 794.0603 |  |  | 77.8452
5 |  | 2BHK | 647.1317 | 0 | 970.6975
6 |  | 2BHK | 547.78 | 0 | 821.6699
7 |  | 2BHK | 547.78 | 0 | 821.6699
8 |  | 1BHK | 425.8238 | 0 | 638.7358
2nd to 6th, 8th to 13th & 15th to 19th Floor | [8 empty] | 15000
1 |  | 1BHK | 425.8238 | 0 | 638.7358 | 2nd to 6th, 8th to 13th & 15th to 19th Floor |  |  | 9581036.4
2 |  | 2BHK | 547.78 | 0 | 821.6699 |  |  |  | 12325049.1
3 |  | 2BHK | 547.78 | 0 | 821.6699 |  |  |  | 12325049.1
4 |  | 1.5BHK | 529.3735 | 0 | 794.0603 |  |  |  | 11910904.2
5 |  | 2BHK | 647.1317 | 0 | 970.6975 |  |  |  | 14560462.8
6 |  | 2BHK | 547.78 | 0 | 821.6699 |  |  |  | 12325049.1
7 |  | 2BHK | 547.78 | 0 | 821.6699 |  |  |  | 12325049.1
8 |  | 1BHK | 425.8238 | 0 | 638.7358 |  |  |  | 9581036.4
7th Floor (Part Refuge Area)
1 |  | 1BHK | 425.8238 | 0 | 638.7358 | 7th Floor (Part Refuge Area)
2 |  | Refuge Area
3
4 |  | 1.5BHK | 529.3735 | 0 | 794.0603 |  |  | 17379.0332
5 |  | 2BHK | 647.1317 | 0 | 970.6975 |  |  | 15246.7681
6 |  | 2BHK | 547.78 | 0 | 821.6699 |  |  | 15334.6245
7 |  | 2BHK | 547.78 | 0 | 821.6699
8 |  | 1BHK | 425.8238 | 0 | 638.7358
14th Floor (Part Refuge Area) | [8 empty] | 14666.6667 | 15333.3333
1 |  | 1.5BHK | 560.0509 | 0 | 840.0764 | 14th Floor (Part Refuge Area)
2 |  | Refuge Area
3
4 |  | 1.5BHK | 529.3735 | 0 | 794.0603
5 |  | 2BHK | 647.1317 | 0 | 970.6975
6 |  | 2BHK | 547.78 | 0 | 821.6699
7 |  | 2BHK | 547.78 | 0 | 821.6699
8 |  | 1BHK | 425.8238 | 0 | 638.7358 |  |  | 15339.6766
Remarks:
* | Construction work is in process at the time of Visit (Labour found).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | As per the site visit, The south side of building (Part I) has been completed with the 1st RCC slab, and on the north side of building (Part II) excavation work is in progress.
* | We have updated revised approved Plan on 03/06/2024.
* | Recommended Rates / Other charges of the Property have been revised on 02/12/2024.
* | We have updated latest CC (On 30/12/2024).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Raghav Parijat
Layout :
Building No.72
Google Map :
Formulas:
Nehru Nagar, Kurla 3 = [Nehru Nagar, Kurla 3, row above]
Building No. 72
Building No. 73
Building No. 69
Building No. 72
Part I
Building No. 72
Part II

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted