## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Sr.No. | Particulars |  |  | Details
1 | Name of the project |  |  | Vrundavan Park
2 | Address as per the site visit |  |  | Vrundavan Park , Near Vrundavan Society, Internal Road, Devrung, Devrung, Kalyan West, Tal. Bhiwandi, Dist.Thane 421302
|  |  |  | Latitude, Longitude : |  | 19.283082,73.151985
| Location Link |  |  | https://maps.app.goo.gl/tRLgNzFVmgz8Chh26
| RERA Name & No. |  |  | Vrundavan Park (P51700049309) |  | Jai - Building No.1 (Wing A & B)
Jui - Building No. 2 (Wing A, B & C)
| Name / No of the Existing Building |  |  | NA
3 | Closest landmark |  |  | Vrundavan society
4 | Address as per the Sale brochure |  |  | Vrundavan Park, S. No.94 Hissa No.19, 23, 25, Gaon -Devrung, Tal. Bhiwandi, Dist.Thane
5 | Address as per the plans & permissions |  |  | Proposed Residential & Commercial Survey No.94/19, 94/23, 94/25 at Village - Devrung, Taluka - Bhiwandi, Dist -Thane |  |  |  | Same
6 | Address as per the legal documentation |  |  | Proposed Residential & Commercial Survey No.94/19, 94/23, 94/25 at Village - Devrung, Taluka - Bhiwandi, Dist -Thane
7 | Date of APF initiation from YBL |  |  | 2025-09-15
8 | Date of documents delivery / Receipt |  |  | 15/09/2025 & 17/09/2025
9 | List of documents provided |  |  | Approved Plan C.C RERA Certificate Builder Profile Cost Sheet
10 | Queries communicated to YBL regarding discrepancies in documentation, details etc |  |  | None
11 | Date of query resolution from YBL |  |  | None
12 | Any further documentation that needs to be complied prior to start of disbursement in the project? Provide complete details. |  |  | None
13 | Name of developer personnel for site visit coordination with contact details (Mobile, landline, email) |  |  | Mr. Nikhil 9594940145
14 | Date of contacting concerned developer personnel for site visit |  |  | 2025-09-16
15 | Date, day & timing of Site visit |  |  | 16/09/2025, Tuesday @ 02:15 PM
16 | Name of the person conducting the site visit & contact details |  |  | Mr. Mangesh Laxman Bapardekar
17 | Name of person met at site (Full Name, Designation, Mobile Number, Landline Number, email id) |  |  | NA
18 | Details of Financial Institutions who's APF Approval Letters / Boards were displayed on site |  |  | None
19 | Details of sold v/s unsold units |  |  | Sold = 64, Unsold = 87 |  |  |  | 87
20 | Has the developer availed any kind of construction / project finance? If yes, details are required. |  |  | None
21 | Developer name |  |  | M/s. Shree Vastunirman Developers
22 | Developer group parent company |  |  | M/s. Shree Vastunirman Developers
23 | Developer office address along with contact details |  |  | Shop No 2 Sundaram Chs Opp Bhanusagar Cinema Valipeer Road Kalyan West 421301
24 | Architect details ( Name, office address, mobile number, registration number ) |  |  | Ar. Mrunal R Dhanawade (Archwaydesigns) Office No.2, 1st Floor, Nilkanth Darshan Co. Op. Society Ltd., Plot No. 125/A4, Opp. Vijay Sales, Old Panvel 410206
25 | Authority jurisdiction for the project location |  |  | Town Planning Thane |  |  |  | Same
26 | Zoning Approval for the project location as per the MDP |  |  | Town Planning Thane
27 | Does the proposed development match with the Zoning Approval? Detailed feedback |  |  | Yes its comes under Residential zone
28 | Project type ( Residential / Mixed / Flats / Villas / Row Houses etc ) |  |  | Residential + Commercial
29 | Plot Area (Sq.M) |  |  | 3000
30 | Does the Plot Area match as per the legal documentation? |  |  | Yes
31 | Does the Plot Area match as per the Non Agriculture documentation? |  |  | Yes as per plan. But NA order not provided to verify.
32 | Does the ongoing construction match with the Approved Site Layout? If no, details expected. |  |  | Yes
33 | Net Plot Area (Sq.M) |  |  | 2865.062
| Builtup Area (Sq.M) |  |  | 6441.962 |  |  |  | 2.2485
34 | Permissible FSI / FAR |  |  | 1.1
35 | Premium FSI / FAR |  |  | 0.25828
36 | Ancillary FSI / FAR |  |  | 0.84323
37 | Permissible TDR |  |  | 0.047098
38 | Total FSI |  |  | 2.2486
39 | Project launch date |  |  | 2023-02-07
| Project Construction Start date |  |  | Feb 2023 |  |  |  | as per documnents
40 | Average weighted stage of construction for the project with construction stages of individual wings
Construction Details: |  | Building No.1 (Wing A) = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 6 Floor, Painting upto 5 Floor, Finishing upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 6 Floor, Painting upto 5 Floor, Finishing upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 83.57% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction Details: |  | Building No.1 (Wing B) = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 81.43% |  | 91.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 57.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction Details: |  | Building No.2 (Wing B & C) = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 20% |  | 30% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction Details: |  | Building No.2 (Wing A) = G + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
41 | Expected Completion Date |  |  | As projected by the RERA |  |  | 2027-12-31
|  |  |  | As projected by the Developer |  |  | Dec 2027
42 | Permissions applicable v/s available (Detailed analysis) |  |  | NA
43 | Physical & social infrastructure availability details ( Bus stop, railway station, public park, main road, airport, hospital, public transport, school, market etc ) |  |  | SCHOOL : St.Mary's English School - 0.80Km Z.P School Bapgaon - 1.6Km SHOPPING : R Mart - 2.1Km Durga super market -2.0Km HOSPITALS : Vrindavan Super Speciality Hospital -3.5Km Vedant Kalyan Hospital - 4.4Km PETROL PUMP : Bharat Petroleum -1.3Km Hindustan Petroleum - 1.2Km
44 | Proposed Amenities |  |  | Entrance Gate Parking Lift Meter Room Society Office Compound Wall Open Gym Childern Paly Area |  |  |  | https://housing.com/in/buy/projects/page/293429-vrundavan-park-jai-by-shree-vastunirman-developers-in-kalyan-west
45 | Boundary details ( Are they matching as per the legal & technical documentation ) |  |  | Yes
46 | Phase, building & wingwise structure details ( Approvals v/s proposed v/s constructed ( If 100 % complete ) ( Deviations to be pointed out ) |  |  | Approved Floor
Building No.1 (Wing A & B) = G + 1st to 7th Floor Building No.2 (Wing A, B & C) = G + 1st to 7th Floor
Proposed Floor
Building No.1 (Wing A & B) = G + 1st to 7th Floor
Building No.2 (Wing A, B & C) = G + 1st to 7th Floor
Approval Detail : Plan approval
Layout Plan No. |  | BS/RKKN/BP/Mauje.Devrung/Tal. Bhiwandi/SSTN/2516 |  |  | Dated | 2022-10-13 |  |  |  |  | 201 to 201 | 201 | 201
Approved Floor Plan No |  | BS/RKKN/BP/Mauje.Devrung/Tal. Bhiwandi/SSTN/2516 |  |  | Dated | 2022-10-13 |  |  |  |  | 202 to 202 | 202 | 202
Commencement Certificate No. Valid Up to: |  | MHSL/K-1/T-8/BP/Devrung-Bhiwandi/SR-40/2022 |  |  | Dated | 03/01/2023
|  | Building No.1 = G + 1st to 7th Floor Building No.2 = G + 1st to 7th Floor | [8 empty] | 203 to 203 | 203 | 203
Fire Noc No Valid Up to: |  |  |  |  | Dated | [5 empty] | 204 to 204 | 204 | 204
[11 empty] | 205 to 205 | 205 | 205
Environmental Clearance Certificate (EC) No Valid Up for: |  |  |  |  | Dated | [5 empty] | 206 to 206 | 206 | 206
[11 empty] | 207 to 207 | 207 | 207
Airport Noc No Valid Up for: |  |  |  |  | Dated | [5 empty] | #REF! | #REF! | #REF!
[5 empty] | Valid Upto Date | [5 empty] | #REF! | #REF! | #REF!
O. Certificate No.: |  | NA Approved upto : |  | Date of approval: | Dated | NA | NA |  |  |  | #REF! | #REF! | #NUM!
Commercial Area Details : (Shop) | [10 empty] | #REF! | #REF! | #NUM!
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  |  | #REF! | #REF! | #NUM!
Building No.2 (Jui) |  | 4 |  | 560.1047 |  | 840.1571 |  |  |  |  | #REF! | #REF! | #NUM!
Total |  | 4 |  | 560.1047 |  | 840.1571 |  |  |  |  | #REF! | #REF! | #NUM!
Residential Area Details : (Flat) | [10 empty] | #REF! | #REF! | #NUM!
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  |  | #REF! | #REF! | #NUM!
Building No.1 (Jai) | Wing A | 35 |  | 14205.1701 |  | 20597.4966 |  |  |  |  | #REF! | #REF! | #NUM!
| Wing B | 35 |  | 14205.1701 |  | 20597.4966 |  |  |  |  | #REF! | #REF! | #NUM!
Building No.2 (Jui) | Wing A | 28 |  | 8511.8752 |  | 12342.219 |  |  |  |  | #REF! | #REF! | #NUM!
| Wing B | 28 |  | 9259.5157 |  | 13426.2978
| Wing C | 21 |  | 6944.6368 |  | 10069.7233 |  |  |  |  | #REF! | #REF! | #REF!
Total |  | 147 |  | 53126.3678 |  | 77033.2334 |  |  |  |  | #REF! | #REF! | #REF!
Grand Total |  | 151 |  | 53686.4726 |  | 77873.3905 |  |  |  |  | #REF! | #REF! | #REF!
Building Details Floor Wise | [7 empty] | 151 |  |  | #REF! | #REF! | #REF!
Details of Commercial in Building | [10 empty] | #REF! | #REF! | #REF!
Flat No. (Approved Plan) | Description | Carpet Area | Otla Area | Loft Area | Gross Carpet Area | Attached Terrace Area | Saleable Area Loading : |  |  |  | #REF! | #REF! | #REF!
[7 empty] | 50% |  |  |  | #REF! | #REF! | #REF!
Building No.2 (Jui) | [10 empty] | #REF! | #REF! | #REF!
Wing A | [10 empty] | #REF! | #REF! | #REF!
Ground Floor For Commercial & Parking | [10 empty] | #REF! | #REF! | #REF!
1 | Shop | 66.7099 | 0 | 0 | 66.7099 | 0 | 100.0648
2 | Shop | 161.2447 | 0 | 0 | 161.2447 | 0 | 241.8671
3 | Shop | 209.4674 | 0 | 0 | 209.4674 | 0 | 314.2012
4 | Shop | 122.6827 | 0 | 0 | 122.6827 | 0 | 184.024
Details of Residential in Building
Flat No. (Approved Plan) | Description | Carpet Area | Enclosed Balcony Area | Balcony Area | Gross Carpet Area | Attached Terrace Area | Saleable Area Loading :
45%
Building No.1 (Jai)
Wing A
Ground Floor For Driver Room & Parking
1st to 7th Floor For Residential
1 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106 | 24.225 | 2.7
2 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
3 | 1BHK | 278.9491 | 31.5654 | 20.9898 | 331.5043 | 0 | 480.6812
4 | 2BHK | 413.3645 | 67.9208 | 36.9205 | 518.2059 | 0 | 751.3985
5 | 2BHK | 413.3645 | 67.9208 | 36.9205 | 518.2059 | 0 | 751.3985
Wing B
Ground Floor For Parking
1st to 7th Floor For Residential | [7 empty] | 4800
1 | 2BHK | 413.3645 | 67.9208 | 36.9205 | 518.2059 | 0 | 751.3985 | 3606712.8552
2 | 2BHK | 413.3645 | 67.9208 | 36.9205 | 518.2059 | 0 | 751.3985 | 3606712.8552
3 | 1BHK | 278.9491 | 31.5654 | 20.9898 | 331.5043 | 0 | 480.6812 | 2307269.8584
4 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106 | 2301651.0504 | 4692.2838
5 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106 | 2301651.0504 | 4796.5568
Building No.2 (Jui)
Wing A | [9 empty] | as per site meet person 1BHK = 23 lAKH
1st to 7th Floor For Residential | [7 empty] | 24.555 |  | 2116000
1 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106 | 18.85 |  | 4957.7211
2 | 1RK | 202.9014 | 0 | 20.9898 | 223.8912 | 0 | 324.6422 | 1558282.752
3 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
4 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
Wing B
Ground Floor For Parking
1st to 7th Floor For Residential
1 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
2 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106 | 4588.0109
3 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
4 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
Wing C
Ground Floor For Society Office & Parking
1st to 7th Floor For Residential
1 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
2 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
3 | 1BHK | 278.9491 | 30.7581 | 20.9898 | 330.697 | 0 | 479.5106
48 | Phase, building & wingwise naming & numbering details |  |  | Building No.1 (Wing A & B) = G + 1st to 7th Floor Building No.2 (Wing A, B & C) = G + 1st to 7th Floor
49 | Phase, building, wing, unit wise pricing details (Base pricing, floor rise, location / view specific, etc) |  |  | Flats = 147 Shop = 4
50 | Are there any deviations between the ongoing construction & the available plans & permissions. If yes, details are expected. |  |  | No
51 | Pricing comparisons ( Builder pricing v/s Resale v/s Nearby Projects with Rationale & justification ) |  |  | As per Site Details :
|  |  |  | Realizable Rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 4800
52 | Transaction documentation details ( Black / White percentages etc ) |  |  | No
53 | All details payable |  |  | As per Market Enquiry :
|  |  |  | Realizable Rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 4800
|  |  |  | Recommended rate of Parking |  |  | 150000
54 | Different types of payment schemes offered such as CLPP, TLPP, C & TLPP, Interest Subvention Plans etc |  |  | NA
55 | Schedule of Payment as per the developer |  |  | NA
|  |  |  | At Booking |  |  | 10%
|  |  |  | Commecement |  |  | 20%
|  |  |  | Plinth |  |  | 15%
|  |  |  | 1st Slab |  |  | 5%
|  |  |  | 2nd Slab |  |  | 5%
|  |  |  | 3rd Slab |  |  | 5%
|  |  |  | 4th Slab |  |  | 5%
|  |  |  | 5th Slab |  |  | 5%
|  |  |  | Completion of Brick work |  |  | 5%
|  |  |  | Completion of Plaster work |  |  | 5%
|  |  |  | Completion of Water Proofing |  |  | 5%
|  |  |  | Completion of Flooring, Doors & Windows |  |  | 5%
|  |  |  | Painting, Electrical & Sanitary Fittings |  |  | 5%
|  |  |  | On Possession |  |  | 5%
|  |  |  | Total |  |  | 100%
56 | Are there any discrepancies in the legal / technical documentation that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
57 | Any evidences of social disturbances at the project site that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
58 | Any notices or boards of litigation at project site / developer office that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
59 | Any further documentation that needs to be tracked by the Financial Institution & obtained from the customer / developer post project completion? Provide complete details. |  |  | None
60 | Declarations :-
(a) | Have you done APF technical for this project for any other Financial Institution? |  |  | None
(b) | Have you done evaluation of this project for the Project / Construction Finance perspective for any Financial Insitution? |  |  | No
Remarks:
1 | Bldg No.1 (Wing A & B) & Bldg No.2 (Wing B & C) = Construction work is in process at the time of Visit (labour found). Bldg No.2 (Wing A) = Work not yet started. | [6 empty] | as per conformed with builder Wing A not started.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Encl Balcony + Balcony Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
PHOTOGRAPHS OF PROPERTY : |  |  | Vrundavan Park
Layout
Google Map :
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
Name of Engineer Visited the property |  | Mr. Mangesh Laxman Bapardekar |  | Authorized Signatory Name & Seal of the Agency
Note on E22: Visit Date
Note on E23: Visit Date
Note on E24: Visitor Name
Note on E25: Met person & No
Note on E27: mention it if provided by builder or else NA
Note on E110: 2 School 2 Shopping Centre or mall 2 Hospital
Note on E197: Proposed Structure
Vrundavan Park
Building No.2
(Wing A)
Building No.2
(Wing B)
Building No.2
(Wing C)
Building No.1
(Wing B)
Building No.1
(Wing A)
N
Bldg No.1 (Wing A)
Bldg No.1 (Wing B)
Bldg No.1 (Wing B)
Bldg No.2 (Wing B)
Bldg No.2 (Wing C)

## Valuation
Lifestyle Amenities : Internal Paved roads. Decorative compound Walls with security features Power backup for lifts & common areas Modern Amenities ; FLOORING Vitrified flooring in all rooms Anti-skid tiles in attached terrace area KITCHEN Granite kitchen platform Stainless steel and sink mixture TOILETS Designer bathroom with branded sanitary ware Concealed plumbing with premium C. P. fittings Geyser connection to all bathrooms WINDOWS Powdered Aluminium Sliding windows
SECURITY Modern security system with CCTV at security cabin Intercom facility in each flat ELECTRIFICATION Branded concealed copper wiring with isolater / MCB TV, telephone & internet points in all rooms WALLS AND PAINTS Gypsum finished internal walls with plastic paints