## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-18
Name of the builder group |  |  |  | M/s.Om Sadguru Realtors
Name of the builder company |  |  |  | M/s.Om Sadguru Realtors
Name of the Project |  |  |  | Sadguru Darshan
Contect Details ( Name & Contect No.) |  |  |  | 9833535663
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajesh : 9822535663 & Ms. Neha (Sales) 7387487109
Name / No of the Building |  |  |  | Building No.1 Building No.2 Building No.3
Docouments Provided |  |  |  | Approved Plans, CC, Sale plan & Builder saleable Sheet
RERA No. |  |  |  | P51700017137
Project location details |  | Sadguru Darshan, Survey No.27 & H.No. 2B+3A, Chauk - Karjat - Murbad Road, Murbad, Thane.
Survey No |  | 27 & H.No. 2B+3A
Road |  | Chauk - Karjat - Murbad Road |  | Locality/Village |  | Murbad
City |  | Murbad |  | District |  | Thane
Taluka |  | Murbad |  | Pin Code |  | 421401
Near by Landmark |  | Gurudarshan Society |  | Distance from city centre: |  | 600 M from Murbad Bus Depot
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Bunglow
West | NA | NA |  |  | Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.255482,73.395059
Location Link |  | https://goo.gl/maps/4tvLdPqZbKkfNE4z6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3906
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.2
Total FSI availaible for the project |  |  |  | 1.2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4687.2
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Layout Approval No |  | J.Kr.527/2021 |  |  | Dated | 2021-07-06
Approved Floor plan No. |  | J.Kr.527/2021 |  |  | Dated | 2021-07-06
Commencement Certificate No. |  | J.Kr.527/2021 |  |  | Dated | 2021-07-06
Valid Up to: Type/Building No.1, 2 = Gr + 1st to 7th Floor Type/Building No.3 = Gr + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4687.2
Approved no of units |  |  | Flats - 152
Approved no of Floors |  |  | Type/Building No.1, 2 = Gr + 1st to 7th Floor Type/Building No.3 = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Type/Building No.1, 2 = Gr + 1st to 7th Floor Type/Building No.3 = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 30/05/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Part I Building No. 1 = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 3.5
Plinth |  | 5.25 | 75% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Part II Building No. 1 = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Footing work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Footing work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 2.5% |  | 26.25% |  | Excavation in process | 3.5
Plinth |  | 1.75 | 25% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Avg Progress % |  | 5% |  | Avg Disbursement % |  | 32.5%
Construction details: |  | Building No. 2 = G + 1st to 7th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 3 = G + 1st to 4th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 4 | 100% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3600
Development Charges |  |  |  |  | 2,00,000/-
Society Charges |  |  |  |  | 50,000/-
Club House Charges |  |  |  |  | 1,00,000/-
Legal Charges |  |  |  |  | 10,000/-
Car Parking |  |  |  |  | 3,00,000/-
Distressed valuation of the Property |  |  |  |  | 2880
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 49 | 26220.7273 |  | 40544 |  |  | 152
Building No.2 |  | 63 | 31333.4658 |  | 51576
Building No.3 |  | 40 | 15666.8352 |  | 24917
Total |  | 152 | 73221.0282 |  | 117037
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Type/Building No.1
Ground Floor For Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 430.6138 | 0 | 683 | 1st to 7th Floor For Residential |  |  | 1.5861
2 |  | 2BHK | 676.8672 | 0 | 1074 |  |  |  | 1.5867
3 |  | 1BHK | 506.5269 | 0 | 776 |  |  |  | 1.532
4 |  | 1BHK | 506.5269 | 0 | 776 |  |  |  | 1.532
5 |  | 2BHK | 655.4738 | 0 | 1023 |  |  |  | 1.5607
6 |  | 1BHK | 472.3512 | 0 | 718 |  |  |  | 1.5201
7 |  | 1BHK | 497.4583 | 0 | 742 |  |  |  | 1.4916
Type/Building No.2
Ground Floor For Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 446.2754 | 0 | 742 | 1st to 7th Floor For Residential |  |  | 1.6627
2 |  | 2BHK | 659.1874 | 0 | 1067 |  |  |  | 1.6187
3 |  | 2BHK | 549.1793 | 0 | 873 |  |  |  | 1.5896
4 |  | 2BHK | 543.6896 | 0 | 885 |  |  |  | 1.6278
5 |  | 1BHK | 389.4415 | 0 | 678 |  |  |  | 1.741
6 |  | 1BHK | 406.7716 | 0 | 712 |  |  |  | 1.7504
7 |  | 1BHK | 404.5111 | 0 | 649 |  |  |  | 1.6044
8 |  | 2BHK | 630.878 | 0 | 1020 |  |  |  | 1.6168
9 |  | 1BHK | 446.2754 | 0 | 742 |  |  |  | 1.6627
Type/Building No.3
Ground Floor For Residential
G-1 |  | 1BHK | 346.251 | 0 | 499 | Ground Floor |  |  | 1.4412
G-2 |  | 1BHK | 334.3029 | 0 | 501 |  |  |  | 1.4986
G-3 |  | 1BHK | 378.4084 | 0 | 551 |  |  |  | 1.4561
G-4 |  | 1BHK | 387.8269 | 0 | 565 |  |  |  | 1.4568
G-5 |  | 1BHK | 387.8269 | 0 | 553 |  |  |  | 1.4259
G-6 |  | 1BHK | 357.1764 | 0 | 525 |  |  |  | 1.4699
G-7 |  | 1BHK | 341.1919 | 0 | 504 |  |  |  | 1.4772
G-8 |  | 1BHK | 341.1919 | 0 | 495 |  |  |  | 1.4508
1st & 3rd Floor
1 |  | 1BHK | 403.3648 | 68.8788 | 649 | 1st & 3rd Floor |  |  | 1.609
2 |  | 1BHK | 353.5167 | 79.9227 | 641 |  |  |  | 1.8132
3 |  | 2BHK | 448.3744 | 76.4352 | 781 |  |  |  | 1.7418
4 |  | 1BHK | 387.138 | 85.7353 | 660 |  |  |  | 1.7048
5 |  | 1BHK | 387.138 | 85.7353 | 641 |  |  |  | 1.6557
6 |  | 1BHK | 354.5123 | 85.7353 | 585 |  |  |  | 1.6502
7 |  | 1BHK | 403.4885 | 79.9227 | 662 |  |  |  | 1.6407
8 |  | 1BHK | 403.4885 | 79.9227 | 648 |  |  |  | 1.606
2nd & 4th Floor
1 |  | 1BHK | 403.3648 | 73.9164 | 651 | 2nd & 4th Floor |  |  | 1.6139
2 |  | 1BHK | 380.1576 | 0 | 577 |  |  |  | 1.5178
3 |  | 2BHK | 488.3358 | 0 | 726 |  |  |  | 1.4867
4 |  | 1BHK | 417.331 | 44.2669 | 648 |  |  |  | 1.5527
5 |  | 1BHK | 417.331 | 44.2669 | 648 |  |  |  | 1.5527
6 |  | 1BHK | 327.0103 | 0 | 497 |  |  |  | 1.5198
7 |  | 1BHK | 410.8888 | 96.4885 | 701 |  |  |  | 1.7061
8 |  | 1BHK | 410.8888 | 35.575 | 647 |  |  |  | 1.5746
Remarks:
1. Building no. 2 & 3 - All work Completed. Provide OC. Building No. 1 - Construction work is in process at the time of visit. 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + A.P Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We update revised approved plans (on 11/12/2021). 8. Since building no.1 have received CC on 06/07/2021, but as of construction work is not completed yet. 7. On Site, we meet Mr. Tejas - 9529052310.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Mangesh |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sadguru Darshan
Google Map :
Formulas:
Murbad = [Murbad, row above]
Bldg No.2
Part I
Bldg No.2
Part II
Bldg No.3
Part I
Bldg No.2
Bldg No.2
Bldg No.2
Bldg No.2
Bldg No.3
Bldg No.2
Building No. 1
Building No. 1 Part 1
Building No. 1 Part 2
Building No. 2
Building No. 3

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Sadguru Darshan | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
13/08/2020.
2020-12-21 | Asmi | Akash TM send this cost sheet
Only Other charges added