## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-17
Branch Name/ID |  | Mahindra Rural Housing Finance - Virar |  |  | Date & Time of Site Visit | 23/09/2025 at 06:07 PM
Name of the person met at site & Contact No |  | Miss. Ritika 9322509492 |  |  | Date of Report Release | 24/09/2025
Project Details
Name of the project |  | Evara
Address |  | Evara, Old Survey No.5, 5B, 5D, 5F, 5G & New Survey No. 5/1, 5/2, 5/3, 5/4, 5/6, 5/7, 5/8, 5/5/A, 5/5/B, 5/5/C, 5/5/D, 5/5/E, near Evershine Amavi Mall, Narangi Bypass Road, Dongre, Virar West, Vasai, Palghar - 401303. | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Old Survey No |  | 5, 5B, 5D, 5F, 5G & New Survey No. 5/1, 5/2, 5/3, 5/4, 5/6, 5/7, 5/8, 5/5/A, 5/5/B, 5/5/C, 5/5/D, 5/5/E | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Dongre | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Narangi Bypass Road | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Virar West | [7 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Vasai | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Palghar | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 401303 | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P99000080818 | [10 empty] | Mahad | Daund
Landmark |  | Evershine Amavi Mall | [10 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.466722,72.807694 | [7 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/jY1J44T8q6Lua6tZ6 | [10 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s. Neminath Poonam Realty LLP | [10 empty] | Mahasala | Bhor
Office address (agreement) |  | 66B, 3rd Floor, Horniman Circle Chamber, S. A Brelvi Road, Fort, Mumbai 400 001 | [10 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [10 empty] | Murud | Velhe
Builder Bank Details |  | ICICI Bank Limited IFSC Code - ICIC0000268
Contact No. |  | Mr.. Anil Mehta 9322509992
Location of the project Municipal Limit : |  | Vasai-Virar City Municipal Corporation. (VVCMC)
Project Type (Apartments/Plot/ Combined) |  | Apartment + Shop
No of Wings / Buildings |  | Avenue-P (Sector 2) | Wing A to G |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flat - 772 Shop - 39 |  |  | Exposure Limit (Proposed) | 115 |  | 115.8
Approved No. of Floor |  | Avenue P - Sector 2 (Wing A to C )= Gr + 1st to 21st Floor Avenue P - Sector 2 (Wing D to G) = Gr + 1st to 22nd Floor
Proposed No. of Floor |  | Avenue P - Sector 2 (Wing A to C )= Gr + 1st to 21st Floor Avenue P - Sector 2 (Wing D to G) = Gr + 1st to 22nd Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | 30 M Wide Proposed Road | Other Plot / Sector 3 | Other Plot | 12 M Internal Road
|  | Physical on site |  | Narangi Bypass Road | Open Plot | Open Plot | Dongarpada Road
Verification of survey No. (Title document) |  | New Survey Nos. 5/1, 5/2, 5/3, 5/4, 5/5A, 5/5B, 5/5C, 5/5D, 5/5E, 5/6, 5/7 and 5/8 (Earlier bearing Survey Nos. 5, 5B, 5D, 5F and 5G)
Plot area mentioned in the sale deed (As per 7/12) |  | 878781.01 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 585107.88
Approach road |  | Yes, Approx 25ft
Connectivity |  | 1. 0.50km from Gurukul Excellence International School 2. 1.5km from Samarth International School 3. 0.75km from Government ZP Hospital 4. 1.0km from Wellcare Multispeciality Hospital 5. 0.8km from Grand Galleria 6. 0.55km from Reliance SMART Bazaar 7. 0.28km from Radhakrishna Mandir 8. 0.85km from Saibaba Mandir 9. 2.9km from Virar West Bus stop 10. 1.7km from Virar Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 585107.88
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.0878
|  | Total FSI availaible for the project |  |  |  | 2.1878
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 1280081.53
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 1280081.53
Building plan approvals - Approval No : |  | VVCMC/TP/AMEND/VP/453/04/2025-26 |  |  |  | Date | 21/05/2025
Building height / No. of Floors |  | Avenue P - Sector 2 (Wing A, B & C) = Gr + 1st to 21st Floors (Height = 70.00 Mtrs) Avenue P - Sector 2 (Wing D, E, F & G) = Gr + 1st to 22nd Floors (Height = 69.90Mtrs)
Construction/Building Permission Valid Upto |  | VVCMC/TP/RDP/VP-0453/04/2025-26 Avenue P - Sector 2 (Wing A, B & C) = Gr + 1st to 21st Floors Avenue P - Sector 2 (Wing D, E, F & G) = Gr + 1st to 22nd Floors |  |  |  | Date | 2025-05-21
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No. Valid Up to: |  | VVCMC/FIRE/HQ/3013/2025 |  |  |  | Date
Avenue P - Sector 2 (Wing A to C) = G + 1st to 21st Floors (Height = 69.95 Mtrs) Avenue P - Sector 2 (Wing D to G) = G + 1st to 22nd Floors (Height 69.60 Mtrs)
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 14/07/2025 |  | Baseline finish date |  | 2030-12-31
Construction details:
Avenue P - Sector 2 (Wing A) = Gr + 1st to 21st Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Footing work is process
|  |  |  | 0 | 1 | 0 | 21
Stage of construction: |  | Excavation work Completed. Footing work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.25
Excavation |  | 0% |  | 21 | 100% | 2.5% |  | Excavation in process | 10.5
Plinth |  | 10% |  | 5.25 | 25% |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.25
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 10.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 15.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Avenue P - Sector 2 (Wing B) = Gr + 1st to 21st Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed.
|  |  |  | 0 | 1 | 0 | 21
Stage of construction: |  | Excavation work Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.25
Excavation |  | 0% |  | 21 | 100% | 0% |  | Excavation in process | 10.5
Plinth |  | 10% |  | 0 | 0% |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.25
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 10.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 15.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Avenue P - Sector 2 (Wing C) = Gr + 1st to 21st Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 0 | 1 | 0 | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.25
Excavation |  | 0% |  | 21 | 100% | 10% |  | Excavation in process | 10.5
Plinth |  | 10% |  | 21 | 100% |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.25
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 10.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 15.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Avenue P - Sector 2 (Wing D) = Gr + 1st to 22nd Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 0 | 1 | 0 | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 10% |  | Excavation in process | 11
Plinth |  | 10% |  | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Avenue P - Sector 2 (Wing E) = Gr + 1st to 22nd Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work is process
|  |  |  | 0 | 1 | 0 | 22
Stage of construction: |  | Excavation work Completed. Plinth work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 7.5% |  | Excavation in process | 11
Plinth |  | 10% |  | 16.5 | 75% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Avenue P - Sector 2 (Wing F) = Gr + 1st to 22nd Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed.
|  |  |  | 0 | 1 | 0 | 22
Stage of construction: |  | Excavation work Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 0% |  | Excavation in process | 11
Plinth |  | 10% |  | 0 | 0% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Avenue P - Sector 2 (Wing G) = Gr + 1st to 22nd Floors |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 0 | 1 | 0 | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 10% |  | Excavation in process | 11
Plinth |  | 10% |  | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Avenue-P (Sector 2)
Commercial Area Details : (Shop)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 9 |  | 11460.3232 |  | 17190.4847
Wing B |  | 10 |  | 10099.4306 |  | 15149.146
Wing C |  | 10 |  | 19032.5819 |  | 28548.8728
Wing G |  | 10 |  | 2231.8723 |  | 3347.8085
Total |  | 39 |  | 42824.208 |  | 64236.312
Residential Area Details : (Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 76 |  | 79506.3485 |  | 115435.5696
Wing B |  | 38 |  | 55107.3744 |  | 80172.1019
Wing C |  | 76 |  | 79466.1449 |  | 115917.5241
Wing D |  | 126 |  | 90764.3084 |  | 131608.2472
Wing E |  | 165 |  | 102908.1456 |  | 149216.8111
Wing F |  | 165 |  | 102767.6754 |  | 149013.1293
Wing G |  | 126 |  | 90529.8685 |  | 131442.6862
Total |  | 772 |  | 601049.8658 |  | 872806.0694
Grand Total |  | 811 |  | 643874.0738 |  | 937042.3814
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Avenue-P (Sector 2)
Wing A
Ground Floor For Commercial, Parking & Meter Room
1 |  | Shop | 1778.6434 | 0 | 1778.6434 | 0 | 2667.965
2 |  | Shop | 515.0574 | 0 | 515.0574 | 0 | 772.5861
3 |  | Shop | 302.4684 | 0 | 302.4684 | 0 | 453.7026
4 |  | Shop | 584.1623 | 0 | 584.1623 | 0 | 876.2434
5 |  | Shop | 477.5987 | 0 | 477.5987 | 0 | 716.398
1st Floor
1 |  | Shop | 2837.0675 | 0 | 2837.0675 | 0 | 4255.6012
2 |  | Shop | 1064.129 | 0 | 1064.129 | 0 | 1596.1936
2nd Floor
1 |  | Shop | 2837.0675 | 0 | 2837.0675 | 0 | 4255.6012
2 |  | Shop | 1064.129 | 0 | 1064.129 | 0 | 1596.1936
Wing B
Ground Floor For Commercial, Parking & Meter Room
6 |  | Shop | 517.4255 | 0 | 517.4255 | 0 | 776.1382
7 |  | Shop | 543.7973 | 0 | 543.7973 | 0 | 815.6959
8 |  | Shop | 496.8662 | 0 | 496.8662 | 0 | 745.2994
9 |  | Shop | 556.4988 | 0 | 556.4988 | 0 | 834.7482
10 |  | Shop | 610.2112 | 0 | 610.2112 | 0 | 915.3167
11 |  | Shop | 617.423 | 0 | 617.423 | 0 | 926.1346
1st Floor
3 |  | Shop | 1574.7732 | 0 | 1574.7732 | 0 | 2362.1598
4 |  | Shop | 1803.8311 | 0 | 1803.8311 | 0 | 2705.7467
2nd Floor
3 |  | Shop | 1574.7732 | 0 | 1574.7732 | 0 | 2362.1598
4 |  | Shop | 1803.8311 | 0 | 1803.8311 | 0 | 2705.7467
Wing C
Ground Floor For Commercial, Parking & Meter Room
12 |  | Shop | 614.8397 | 0 | 614.8397 | 0 | 922.2595
13 |  | Shop | 802.8868 | 0 | 802.8868 | 0 | 1204.3301
14 |  | Shop | 481.1508 | 0 | 481.1508 | 0 | 721.7262
15 |  | Shop | 847.9879 | 0 | 847.9879 | 0 | 1271.9819
16 |  | Shop | 682.1147 | 0 | 682.1147 | 0 | 1023.172
17 |  | Shop | 2726.1983 | 0 | 2726.1983 | 0 | 4089.2974
1st Floor
5 |  | Shop | 1425.046 | 0 | 1425.046 | 0 | 2137.5689
6 |  | Shop | 5013.6559 | 0 | 5013.6559 | 0 | 7520.4839
2nd Floor
5 |  | Shop | 1425.046 | 0 | 1425.046 | 0 | 2137.5689
6 |  | Shop | 5013.6559 | 0 | 5013.6559 | 0 | 7520.4839
Wing G
Ground Floor For Commercial, Parking & Meter Room
18 |  | Shop | 258.8742 | 0 | 258.8742 | 0 | 388.3113
19 |  | Shop | 240.7907 | 0 | 240.7907 | 0 | 361.186
20 |  | Shop | 215.1724 | 0 | 215.1724 | 0 | 322.7585
21 |  | Shop | 215.1724 | 0 | 215.1724 | 0 | 322.7585
22 |  | Shop | 215.1724 | 0 | 215.1724 | 0 | 322.7585
23 |  | Shop | 160.276 | 0 | 160.276 | 0 | 240.4139
24 |  | Shop | 215.1724 | 0 | 215.1724 | 0 | 322.7585
25 |  | Shop | 215.1724 | 0 | 215.1724 | 0 | 322.7585
26 |  | Shop | 233.9017 | 0 | 233.9017 | 0 | 350.8526
27 |  | Shop | 262.168 | 0 | 262.168 | 0 | 393.252
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet + Encl Balcony Area | Balcony + AP Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Avenue-P (Sector 2)
Wing A
3rd Floor For Residential
1 |  | 3BHK | 953.1522 | 104.0341 | 1057.1863 | 222.1151 | 1606.9585
2 |  | 3BHK | 935.4992 | 104.0341 | 1039.5333 | 154.6518 | 1584.6492
3 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
4 |  | 3BHK | 856.922 | 181.6963 | 1038.6184 | 0 | 1505.9966
4th to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential
1 |  | 3BHK | 915.0476 | 153.4408 | 1068.4885 | 0 | 1549.3083
2 |  | 3BHK | 918.4921 | 153.4408 | 1071.9329 | 0 | 1554.3028
3 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
4 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 3BHK | 915.0476 | 153.4408 | 1068.4885 | 0 | 1549.3083
2 |  | 3BHK | 918.4921 | 153.4408 | 1071.9329 | 0 | 1554.3028
3 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
4 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
- |  | Refuge Area
Wing B
3rd Floor For Residential
1 |  | 4BHK | 1254.006 | 175.1303 | 1429.1363 | 416.1362 | 2176.2817
2 |  | 4BHK | 1254.006 | 175.1303 | 1429.1363 | 649.4998 | 2234.6225
4th to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential
1 |  | 4BHK | 1243.7802 | 222.5995 | 1466.3797 | 0 | 2126.2506
2 |  | 4BHK | 1243.7802 | 222.5995 | 1466.3797 | 0 | 2126.2506
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 4BHK | 1171.8767 | 204.4084 | 1376.285 | 0 | 1995.6133
- |  | Refuge Area
2 |  | 4BHK | 1171.8767 | 204.4084 | 1376.285 | 0 | 1995.6133
Wing C
3rd Floor For Residential
1 |  | 3BHK | 935.4992 | 104.0341 | 1039.5333 | 585.5616 | 1653.7137
2 |  | 3BHK | 958.4266 | 74.4869 | 1032.9134 | 1371.9794 | 1840.7193
3 |  | 3BHK | 868.6548 | 149.7272 | 1018.382 | 808.9146 | 1678.8826
4 |  | 3BHK | 845.4046 | 181.6963 | 1027.1009 | 0 | 1489.2963
4th to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential
1 |  | 3BHK | 918.4921 | 153.4408 | 1071.9329 | 0 | 1554.3028
2 |  | 3BHK | 915.0476 | 153.4408 | 1068.4885 | 0 | 1549.3083
3 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
4 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 3BHK | 915.0476 | 153.4408 | 1068.4885 | 0 | 1549.3083
2 |  | 3BHK | 918.4921 | 153.4408 | 1071.9329 | 0 | 1554.3028
- |  | Refuge Area
3 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
4 |  | 3BHK | 841.099 | 181.6963 | 1022.7953 | 0 | 1483.0532
Wing D
Ground Floor For Parking, Entrance Lobby & Meter Room
1st Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
2nd Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
3rd to 6th, 8th to 11th, 13th to 16th & 18th to 22nd Floor
1 |  | 2BHK | 578.1344 | 109.8466 | 687.9811 | 0 | 997.5725
2 |  | 2BHK | 631.9544 | 109.8466 | 741.8011 | 0 | 1075.6115
3 |  | 2BHK | 575.9816 | 109.8466 | 685.8283 | 0 | 994.451
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 2BHK | 578.1344 | 109.8466 | 687.9811 | 0 | 997.5725
2 |  | 2BHK | 631.9544 | 109.8466 | 741.8011 | 0 | 1075.6115
3 |  | 2BHK | 575.9816 | 109.8466 | 685.8283 | 0 | 994.451
- |  | Refuge Area
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
Wing E
Ground Floor For Parking, Entrance Lobby & Meter Room
1st Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
-
5 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
2nd Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
-
5 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
3rd to 6th, 8th to 11th, 13th to 16th & 18th to 22nd Floor
1 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
2 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
3 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
4 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
5 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
2 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
3 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
4 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
5 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | Refuge Area
Wing F
Ground Floor For Parking, Entrance Lobby & Meter Room
1st Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
-
5 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 1BHK | 456.7165 | 77.5008 | 534.2173 | 0 | 774.6151
2nd Floor For Residential & Part Parking Area
- |  | Parking Area
-
-
-
5 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
3rd to 6th, 8th to 11th, 13th to 16th & 18th to 22nd Floor
1 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
2 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
3 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
4 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
5 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
2 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
3 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
4 |  | 1BHK | 418.5043 | 77.5008 | 496.0051 | 0 | 719.2074
5 |  | Refuge Area
6 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
7 |  | 2BHK | 551.8703 | 105.5948 | 657.4651 | 0 | 953.3244
8 |  | 2BHK | 569.0927 | 105.5948 | 674.6875 | 0 | 978.2969
Wing G
1st Floor For Residential & Part Parking Area
1 |  | 2BHK | 592.2353 | 65.5528 | 657.788 | 111.9456 | 1009.7655
2 |  | 2BHK | 640.9962 | 86.3811 | 727.3773 | 62.4312 | 1117.1283
3 |  | 2BHK | 590.0825 | 65.5528 | 655.6352 | 111.9456 | 1006.6439
4 |  | Parking Area
5
6
2nd Floor For Residential & Part Parking Area
1 |  | 2BHK | 578.1344 | 114.4751 | 692.6096 | 0 | 1004.2839
2 |  | 2BHK | 631.9544 | 114.4751 | 746.4296 | 0 | 1082.3229
3 |  | 2BHK | 575.9816 | 114.4751 | 690.4568 | 0 | 1001.1623
4 |  | Parking Area
5
6
3rd to 6th, 8th to 11th, 13th to 16th & 18th to 22nd Floor
1 |  | 2BHK | 578.1344 | 109.8466 | 687.9811 | 0 | 997.5725
2 |  | 2BHK | 631.9544 | 109.8466 | 741.8011 | 0 | 1075.6115
3 |  | 2BHK | 575.9816 | 109.8466 | 685.8283 | 0 | 994.451
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
7th, 12th & 17th Floor For Part Refuge Area
1 |  | 2BHK | 578.1344 | 109.8466 | 687.9811 | 0 | 997.5725
2 |  | 2BHK | 631.9544 | 109.8466 | 741.8011 | 0 | 1075.6115
3 |  | 2BHK | 575.9816 | 109.8466 | 685.8283 | 0 | 994.451
- |  | Refuge Area
4 |  | 2BHK | 602.6764 | 109.8466 | 712.523 | 0 | 1033.1583
5 |  | 2BHK | 666.7222 | 109.8466 | 776.5688 | 0 | 1126.0247
6 |  | 2BHK | 603.4298 | 109.8466 | 713.2765 | 0 | 1034.2509
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000
Recommended of Parking ( If Available) |  |  |  |  | 2,50,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = RERA Carpet + Encl Balcony + Balcony + AP Area
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 45%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Miss. Ritika 9322509492
11 | We have referred Approved plans & CC from RERA site.
12 | Please check for Environment Clearance Certificate.
Photographs Of Property : |  | Evara
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Navnath Bhatkar |  | Authorized Signatory Name & Seal of the agency
A
B
C
D
E
F
G
Evara
Wing A
Wing B
Wing C
Wing D
Wing E
Wing F
Wing G
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C61: RERA Start date
Note on H163: if multiple buildings are in project and are connected internally
Note on C165: AAC Block or Brick
Note on H167: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3