## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-19
Name of the builder group |  |  |  | M/s. Ira Homes
Name of the builder company |  |  |  | M/s. Ira Homes
Name of the Project |  |  |  | Ira Insignia
Contact Details ( Name & Contact No.) |  |  |  | Hiren Vador (9653106574)
No of the Building / Name |  |  |  | Building No.1 (Nandi) Building No.2 (Neelkanth) Building No.3 (Rudra)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P51700031409
Project location details |  | Ira Insignia, Survey No.239, Hissa No.4, Survey No. 52, Hissa No. 1/A & 1/D (P), near Durga Mata Mandir, Navneet Nagar Road, Bhopar (Desale Pada), Dombivali (East), Kalyan, Thane.
Survey No |  | 239, Hissa No.4, Survey No. 52, Hissa No. 1/A & 1/D (P) | [5 empty] | Survey No |  | 239, Hissa No.4
Road |  | Navneet Nagar Road |  | Locality/Village |  | Bhopar (Desale Pada) |  | Road |  | Navneet Nagar Road |  | Locality/Village |  | Bhoper (Desai Pada)
City |  | Dombivali (East) |  | District |  | Thane |  | City |  | Dombivali (East) |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421204 |  | Taluka |  | Kalyan |  | Pin Code |  | 421204
Nearby Landmark |  | Durga Mata Mandir |  | Distance from city centre: |  | 3.5Km from Dombivali Railway Station |  | Nearby Landmark |  | Durga Mata Mandir |  | Distance from city centre: |  | 3.5Km from Dombivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 12M Wide Rd |  |  | Krishna Highland, Blossom
West | NA | 24M Wide Rd |  |  | Internal Road
North | NA | 18M Wide Rd |  |  | Chandresh Vastu E-Wing Lodha Heritage
South | NA | Other Plot |  |  | Gokul Dham-D
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude : |  | 19.191954,73.085053
Location Link : |  | https://maps.app.goo.gl/KqML2gfCvhFVfkYh8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9496.79 |  |  |  | 8022.72
Permissible FSI |  |  |  | 1.1 |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.65999 |  |  |  | -2.4929e-07
Total FSI availaible for the project |  |  |  | 1.76 |  |  |  | 1.1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 16714.289 |  |  |  | 8824.99
Total number of Buildings |  |  |  | 03 Buildings |  |  |  | 03 Building
Approval Detail : Plan approval
Layout Approval No |  | KDMCC/RAR/2025/APL/00002 |  |  | Dated | 2025-02-17 |  | KDMC/TPD/BP/27Village/2021-22/14 |  |  | Dated | 2021-07-30
Approved Floor plan No. |  | KDMCC/RAR/2025/APL/00002 |  |  | Dated | 2025-02-17 |  | KDMC/TPD/BP/27Village/2021-22/14 |  |  | Dated | 2021-07-30
Commencement Certificate No. Valid Up to: |  | KDMCC/RAR/2025/APL/00002 |  |  | Dated | 2025-02-17 |  | KDMC/TPD/BP/27Village/2021-22/14 |  |  | Dated | 2021-07-30
|  | Building No 1 = G + 3P + 1st to 2nd Floor Building No 2 = G + 3P + 1st to 21st Floor Building No 3 = G + 3P + 1st to 21st Floor | [5 empty] | Valid Up to: Building No 1 & 3 = St/Gr + 2P + Amenity Floor + 1st to 3rd Floor Building No 2 = St/Gr + 2P + Amenity Floor + 1st to 4th floor + 5th floor(MHADA)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details | [7 empty] | 253
Approved area of building (Sq.Mt) |  |  | 16714.289
Approved no of units |  |  | Flats = 230, Inclusive Housing Flats = 23 |  |  |  |  | Mhada Flats = 25, Sale Flats = 40
Approved no of Floors |  |  | Building No 1 (Nandi) = G + 3P + 1st to 2nd Floor Building No 2 (Neelkanth) = G + 3P + 1st to 21st floor Building No 3 (Rudra) = G + 3P + 1st to 21st floor
Proposed no of Floors |  |  | Building No 1 (Nandi) = G + 3P + 1st to 26th Floor |  |  |  |  | https://www.irainsignia.com/images/gallery/g2.jpg
Building No 2 (Neelkanth) = G + 3P + 1st to 28th floor
Building No 3 (Rudra) = G + 3P + 1st to 28th floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No 1 (Nandi) = G + 3P + 1st to 26th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 26
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 13
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 26
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 6.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 13
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 19.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 26
Construction details: |  | Building No 2 (Neelkanth) = G + 3P + 1st to 28th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 11.29% |  | 45.97% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 1 | 3.226% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | Building No 3 (Rudra) = G + 3P + 1st to 28th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 24.67% |  | 55.54% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 9 | 28.12% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 5 | 17.86% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 3.75 | 13.39% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 10.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6800 |  |  | 5100 to 6800 change by us as per market inquery
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 4,00,000/-
Distressed valuation of the Property |  |  |  |  | 5440
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Bldg No 1 (Nandi) |  | 9 |  | 5671.121 |  | 8506.6816 |  | Ok
Bldg No 2 (Neelkanth) | (Inclusive Housing) | 23 |  | 9337.2318 |  | 14005.8477 |  | Ok
| Sale | 99 |  | 60205.0433 |  | 90307.565 |  | Ok
Bldg No 3 (Rudra) |  | 122 |  | 74214.0664 |  | 111321.0996 |  | Ok
Total |  | 253 |  | 149427.4626 |  | 224141.1939
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Inclusive Housing / Sale Flat | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor |  | 230
50%
Building No 1 (Nandi)
Ground Floor for Society Office, Driver Room, Meter Room & Parking
1st to 3rd Podium Floor for Parking
1st Floor For Residential | [12 empty] | 1,..,1 | 1 | 1
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 1st Floor For Residential |  | 56.802 | 5414.3893
2 |  | 2BHK | 751.085 | 0 | 1126.6275 | [7 empty] | 101 to 101 | 101 | 101
3 |  | 1BHK | 533.3562 | 0 | 800.0343 |  |  | 6874.7052 | 5124.7803 |  |  |  | 102 to 102 | 102 | 102
4 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 103 to 103 | 103 | 103
5 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 104 to 104 | 104 | 104
6 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 105 to 105 | 105 | 105
2nd Floor For Residential (Part Terrace Area) | [12 empty] | 106,..,106 | 106 | 106
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 2nd Floor For Residential (Part Terrace Area) |  | 56.802 | 5414.3893
2 |  | 2BHK | 751.085 | 0 | 1126.6275 | [7 empty] | 201 to 201 | 201 | 201
3 |  | 1BHK | 533.3562 | 0 | 800.0343 |  |  |  | 5124.7803 |  |  |  | 202 to 202 | 202 | 202
4 |  | Terrace Area | [10 empty] | 203 to 203 | 203 | 203
5 | [12 empty] | 204 to 204 | 204 | 204
6 | [12 empty] | 205 to 205 | 205 | 205
Building No 2 (Neelkanth)
1st to 3rd Podium Floor for Parking
1st to 3rd Floor For Residential (For Inclusive Housing Scheme) | [7 empty] | 3 | 12212.6437 | 8141.7625
1 |  | 1BHK | 406.8792 | 0 | 610.3188 | 1st to 3rd Floor For Residential (For Inclusive Housing Scheme) |  | 31.8 | 10700.3891 | 7133.5927
2 |  | 1BHK | 406.8792 | 0 | 610.3188
3 |  | 1BHK | 405.4799 | 0 | 608.2198 |  |  | 9700.4402
4 |  | 1BHK | 405.4799 | 0 | 608.2198
5 |  | 1BHK | 405.4799 | 0 | 608.2198
6 |  | 1BHK | 405.4799 | 0 | 608.2198
4th Floor For Residential (For Inclusive Housing Scheme) (Part Refuge Area) | [7 empty] | 1
1 |  | 1BHK | 406.8792 | 0 | 610.3188 | 4th Floor For Residential (For Inclusive Housing Scheme) (Part Refuge Area) |  | 31.8
2 |  | 1BHK | 406.8792 | 0 | 610.3188
3 |  | 1BHK | 405.4799 | 0 | 608.2198
4 |  | Refuge Area
5 |  | 1BHK | 405.4799 | 0 | 608.2198
6 |  | 1BHK | 405.4799 | 0 | 608.2198
5th to 7th, 9th to 12th, 14th to 17th & 19th to 21st Floor | [7 empty] | 14
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 5th to 7th, 9th to 12th, 14th to 17th & 19th to 21st Floor |  | 7367.1199
2 |  | 2BHK | 751.085 | 0 | 1126.6275
3 |  | 1BHK | 533.3562 | 0 | 800.0343
4 |  | 1BHK | 533.3562 | 0 | 800.0343
5 |  | 1BHK | 533.3562 | 0 | 800.0343
6 |  | 1BHK | 533.3562 | 0 | 800.0343
8th, 13th & 18th Floor For Residential (Part Refuge Area) | [7 empty] | 3
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 8th, 13th & 18th Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 751.085 | 0 | 1126.6275
3 |  | 1BHK | 533.3562 | 0 | 800.0343
4 |  | Refuge Area
5 |  | 1BHK | 533.3562 | 0 | 800.0343
6 |  | 1BHK | 533.3562 | 0 | 800.0343 |  |  | 6874.7052
Building No 3 (Rudra)
Ground Floor for Parking
1st & 3rd Podium Floor for Parking
1st to 3rd, 5th to 7th, 9th to 12th, 14th to 17th & 19th to 21st Floor | [7 empty] | 17 |  |  |  |  | 1,..,1 | 1 | 1
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 1st to 3rd, 5th to 7th, 9th to 12th, 14th to 17th & 19th to 21st Floor |  | 56.802
2 |  | 2BHK | 751.085 | 0 | 1126.6275 | [7 empty] | 1301 to 2101 | 1301 | 2101
3 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 1302 to 2102 | 1302 | 2102
4 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 1303 to 2103 | 1303 | 2103
5 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 1304 to 2104 | 1304 | 2104
6 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 1305 to 2105 | 1305 | 2105
4th, 8th, 13th & 18th Floor For Residential (Part Refuge Area) | [7 empty] | 4 |  |  |  |  | 1305,..,2105 | 1305 | 2105
1 |  | 2BHK | 751.085 | 0 | 1126.6275 | 4th, 8th, 13th & 18th Floor For Residential (Part Refuge Area) |  | 56.802
2 |  | 2BHK | 751.085 | 0 | 1126.6275 | [7 empty] | 401 to 1801 | 401 | 1801
3 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 402 to 1802 | 402 | 1802
4 |  | Refuge Area | [10 empty] | 403 to 1803 | 403 | 1803
5 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 404 to 1804 | 404 | 1804
6 |  | 1BHK | 533.3562 | 0 | 800.0343 | [7 empty] | 405 to 1805 | 405 | 1805
Remarks: | [12 empty] | #REF! | #REF! | #REF!
1 | Building no.1 = Work not yet started. Building no. 2 = Construction work is same as last visit (dtd.07/06/2025) Few labours found on site. Building no.3 = Construction work is same as last visit dtd. 07/06/2025 (No labour found). | [6 empty] | Construction work is in process at the time of Visit. (Slow Speed)
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | We have updated revised approved plans of Building No. 1, 2 & 3 on 07/06/2025.
8 | This project comes under the Inclusive Housing Scheme.
8 | In Building No. 2, the 1st to 4th floors are for the Inclusive Housing Scheme.
9 | Recommended rates/other charges of the property have been revised on 07/06/2025 as per market inquiry.
10 | On Site, we meet Mr.Hiren (Sale person). (9653106574)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram Lambore |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ira Insignia
PHOTOGRAPHS OF PROPERTY : |  |  | Ira Insignia
Layout :
Google Map :
Formulas:
Bhopar (Desale Pada) = [Bhopar (Desale Pada), row above]
Locality/Village = [Locality/Village, row above]
Rudra
Rudra
Rudra
Building No. 3
Building No. 2
Building No. 1
Ira Insignia
Rudra
Bldg No.2
Bldg No.2
Bldg No.2
Bldg No.2
Bldg No.3
Bldg No.3
Bldg No.3
Bldg No.3 (9th slab)
Bldg No.3 (9th slab)
Bldg No.3 (9th slab)