## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.comm
Valuation Report
Date: |  |  |  |  | 20/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-19
Name of the builder group |  |  |  |  | M/s.Swastik Enterprises
Name of the builder company |  |  |  |  | M/s.Swastik Enterprises
Name of the Project |  |  |  |  | Paramount Enclave
Name of the Project as per RERA |  |  |  |  | Paramount Enclave Building No.2
Contact Details ( Name & Contact No.) |  |  |  |  | 9324358655
Name / no of the Building |  |  |  |  | Building No.2
Docouments Provided |  |  |  |  | Approved Plans, NA order
RERA No. |  |  |  |  | P99000017353
Project location details |  | Paramount Enclave Building 02, Survey No. 1023/1 & 1023/2, Plot No. 25, Mahim, Palghar.
Plot No | 25 |  |  | Survey No. |  | 1023/1, 1023/2 | Locality | Palghar West
Road | Mahim Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401404
Near by Landmark |  | J.P. International School |  |  | Distance from city centre: |  | About 4.1 Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open |  | Road |  | Green Park
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.67566,72.74292
Location Link |  | https://goo.gl/maps/3sGfeQwJ69x2yYo47
Approval details:
Approved usage of the Property: Residential & Commercial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 12620
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0.34945
Total FSI availaible for the project |  |  |  |  | 1.2494
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 15768
Total number of Buildings |  |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | MHSL/K-1/MJ1/BSP/SR/CR/349/18 |  |  |  | Dated | 13/04/2018.
Building plan approval No |  | MHSL/K-1/MJ1/BSP/SR/CR/349/18 |  |  |  | Dated | 13/04/2018. | Expiry date:NA
Date of Commencement Certificate |  | NA |  |  |  | Dated | NA
NA Order |  | MHSL/K-1/MJ1/BSP/SR/CR/349/18 |  |  |  | Dated | 13/04/2018.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | NA |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 15768 |  | Approved no of units |  |  | Shops = 04 Flats = 50
Approved no of Floors |  | G + 1st to 7th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: : Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Building No. 2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 79.29% |  | 91.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 42.86% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 28.57% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Builder Saleble area) | [5 empty] | 3800 | [6 empty] | 3600 to 3800 | 2023-08-30 | nikhil
Recommended rate of the Shop Per Sq. Ft. ( on Builder Saleble area) | [5 empty] | 8000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Society, Development& Other charges | [5 empty] | 195000/-
Recommended rate of Parking | [5 empty] | 100000/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3040
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building no.2
Ground Floor for Shops & Parking
1 |  | Shop | 194.8284 |  | 0 | 390 | N | Ground Floor for Shops & Parking |  | 18.1 |  | 10.764
2 |  | Shop | 274.0514 |  | 0 | 550 | N |  |  | 25.46 |  | 10.764
3 |  | Shop | 274.0514 |  | 0 | 550 | N |  |  | 25.46 |  | 10.764
4 |  | Shop | 194.8284 |  | 0 | 390 | N |  |  | 18.1 |  | 10.764
1st Floor
101 |  | 1BHK | 343.4254 |  | 0 | 580 | N | 1st Floor |  | 28.38 | 3.525 | 10.764
102 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
103 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
104 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
105 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
106 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
107 |  | 1BHK | 388.2575 |  | 0 | 720 | N |  |  | 31.27 | 4.8 | 10.764
108 |  | 1BHK | 388.2575 |  | 0 | 720 | N |  |  | 31.27 | 4.8 | 10.764
109 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
2nd, 4th Floor & 6th Floor
1 |  | 1BHK | 343.4254 |  | 0 | 580 | N | 2nd, 4th Floor & 6th Floor |  | 28.38 | 3.525 | 10.764
2 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
3 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
4 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  | 2283000 | 28.38 | 3.525 | 10.764
5 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
6 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
7 |  | 1BHK | 388.2575 |  | 0 | 650 | N |  |  | 31.27 | 4.8 | 10.764
8 |  | 1BHK | 388.2575 |  | 0 | 650 | N |  |  | 31.27 | 4.8 | 10.764
9 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
3rd & 5th Floor
301, 501 |  | 1BHK | 343.4254 |  | 0 | 580 | N | 3rd & 5th Floor |  | 28.38 | 3.525 | 10.764
302, 502 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
303, 503 |  | 1RK | 272.5445 |  | 0 | 430 | N |  |  | 20.52 | 4.8 | 10.764
304, 504 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
305, 505 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
306, 506 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
307, 507 |  | 1BHK | 364.8458 |  | 10.7675 | 690 | N |  |  | 31.27 | 2.625 | 10.764
308, 508 |  | 1BHK | 364.8458 |  | 10.325 | 690 | N |  |  | 31.27 | 2.625 | 10.764
309, 509 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
7th Floor
701 |  | 1BHK | 343.4254 |  | 0 | 700 | N | 7th Floor |  | 28.38 | 3.525 | 10.764
702 |  | Terrace | [9 empty] | 10.764
703 |  | Terrace | [9 empty] | 10.764
704 |  | 1BHK | 343.4254 |  | 0 | 700 | N |  |  | 28.38 | 3.525 | 10.764
705 |  | 1BHK | 343.4254 |  | 0 | 580 | N |  |  | 28.38 | 3.525 | 10.764
706 |  | 1BHK | 350.0991 |  | 0 | 580 | N |  |  | 29 | 3.525 | 10.764
707 |  | 1BHK | 364.8458 |  | 115.9014 | 690 | N |  |  | 31.27 | 2.625 | 10.764
708 |  | 1BHK | 364.8458 |  | 111.1383 | 850 | N |  |  | 31.27 | 2.625 | 10.764
709 |  | Terrace | [9 empty] | 10.764
Remarks: 1. Construction work is in process (Very very Slow Speed). 2. We considered Saleable area as per Builder area chart. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 6. Car parking is subjected to authentic documentation. 7. NA order download from RERA and updated. 8. As per RERA, completion period of project Paramount Enclave Building No.2 is expired on 30/03/2023 but still project is under construction. 6. On site, we meet Mr. Love Singh (Site Engineer) - 7798777034.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY: |  |  |  | Paramount Enclave Building No.2
Google Map :

## Construction %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 75 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 6 | 37.5 | Progress |  |  | 10 | 30 | 5.625 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 22.5 | 5.625 | 0 | 0 | 0 | 0
| 8 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 8 | 0 | 0
Flooring | Total Floor | completed Floor
| 8 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 8 | 0 |  | RCC | 30 | 22.5
Finishing | Total Floor | completed Floor |  | Bricks | 5.625 | 5.625
| 8 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 45.625 | 58.125

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.3 | 9.075 | CB |  |  | 0 |  |  | 0
|  | 2.15 | 1 | 2.15 | FB |  |  | 0 |  |  | 0
|  | 2.75 | 1.2 | 3.3 |  | 0.75 | 1.95 | 1.4625 |  |  | 0
| kitch | 1.85 | 1.8 | 3.33 | CB | 0.75 | 2.75 | 2.0625 |  |  | 0
|  |  |  | 0 | FB |  |  | 1.4 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 1.5 | 4.125 | CB |  |  | 0 |  |  | 0
|  | 1.4 | 0.2 | 0.28 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1.5 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet2 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 | 0.9 | 1.95 | 1.755 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.9 | 1.95 | 1.755 |  |  |  | 0 |  |  | 0
| passage2 | 1.95 | 0.35 | 0.6825 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 315.735 | 29.3325 |  |  | 53.0127 | 4.925 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.3 | 2.75 | 9.075 | CB |  |  | 0 |  |  | 0
|  |  |  | 0.96 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2 | 1.65 | 3.3 | CB |  |  | 0 |  |  | 0
|  | 2 | 1.55 | 3.1 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 1.5 | 3.2 | 4.8 | CB |  |  | 0 |  |  | 0
|  | 1.25 | 3.5 | 4.375 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.05 | 1.5 | 1.575 | DB |  |  | 0 |  |  | 0
| toilet2 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.2 | 0.9 | 1.08 |  |  |  | 0 |  |  | 0
| passage2 | 0.95 | 2.3 | 2.185 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 339.3889 | 31.53 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATIOn
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Paramount Enclave | 1BHK | 264 | 382.8 | 4030.8255 | 1543000
housing. | Paramount Enclave | 1BHK | 323 | 468.35 | 4031.1733 | 1888000
housing. | Paramount Enclave | 1BHK | 331 | 479.95 | 3958.7457 | 1900000
Average |  |  |  |  | 4006.9148
Valuation Adopted |  |  |  |  | 4000