## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-19 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Lipika Enterprises | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Lipika Enterprises | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Agarwal Skyrise | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 8956198281
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mrs. Pooja : 8956198281
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Sale Plan | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P99000053167 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Agarwal Skyrise, Survey No.131, H. No. 1, near Agarwal Lifestyle, YK Nagar NX Road, , Bolinj, Virar West, Vasai, Palghar - 401303. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 131, H. No. 1 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | YK Nagar NX Road |  | Locality/Village |  | Bolinj | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Virar West |  | District |  | Palghar | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Vasai |  | Pin Code |  | 401303 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Agarwal Lifestyle |  | Distance from city centre: |  | 1.90KM from Virar Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Agarwal Lifestyle
North | NA | 30.00 M. Wide D.P. Road |  |  | YK Nagar NX Road
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.466064,72.802313
Location Link |  | https://maps.app.goo.gl/obfPS9J9qoixNPdF9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4753.88
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 4.8816
Total FSI availaible for the project |  |  |  | 5.9816
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 28435.64
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation. (VVCMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | VVCMC/TP/AMEND/VP/6092/23/ 2023-24 |  |  | Dated | 2023-06-22 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP/6092/23/ 2023-24 |  |  | Dated | 2023-06-22 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | VVCMC/TP/RDP/VP-6092/23/ 2023-24 |  |  | Dated | 2023-06-22 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Wing A = Gr/Stilt + 1st to 22nd Floor Wing B = Gr/Stilt + 1st to 21st(Pt) Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 28435.64
Approved no of units |  |  | Sale Flats - 335, Mhada Flats - 21, Shops - 30
Approved no of Floors |  |  | A Wing = Gr + 1st to 22nd Floor B Wing = Gr + 1st to 21st(Pt) Floor
Proposed no of Floors |  |  | A Wing = Gr + 1st to 22nd Floor
B Wing = Gr + 1st to 21st Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Landscape Garden, Childrens play area, Multi purpose court, Senior citizen area, Gymnasium, Indoor games, Gazebo, Community Zone, Yoga plaza, Sun Deck, Jogging track, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Gr + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor, Flooring upto 12 Floor, Painting upto 10 Floor Completed | , Internal Plaster upto 20 Floor, External Plaster upto 20 Floor, Flooring upto 12 Floor, Painting upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor, Flooring upto 12 Floor, Painting upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 81.14% |  | 91.82% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 20 | 90.91% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 90.91% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 54.55% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 45.45% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | B Wing = Gr + 1st to 21st Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 18 Floor, Painting upto 15 Floor Completed | , Flooring upto 18 Floor, Painting upto 15 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 18 Floor, Painting upto 15 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 87.14% |  | 94.29% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 21 | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 21 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 71.43% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6000 |  |  | RATE 6000 AKASH MOTE VERBAL 23/06/2025 | [8 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8500 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 200000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 18 |  | 3236.089 |  | 5015.9379
Wing B |  | 12 |  | 3473.3275 |  | 5383.6577
Total |  | 30 |  | 6709.4165 |  | 10399.5955
Residential Area Details : Sale Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 195 |  | 144540.3913 |  | 217078.9245
Wing B |  | 140 |  | 83054.9164 |  | 124961.1776
Total |  | 335 |  | 227595.3077 |  | 342040.1022 |  | 356 | 386
Residential Area Details : Mhada Flats
Wing B |  | 21 |  | 10294.259 |  | 15441.3886
Grand Total |  | 386 |  | 244598.9832 |  | 367881.0863
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Wing A | [7 empty] | 10.764
Ground Floor For Commercial, Meter Room, Society Office, Drivers Room, Entrance Lobby & Parking
1 |  | Shop | 159.5225 | 0 | 159.5225 | 0 | 247.2598
2 |  | Shop | 319.045 | 0 | 319.045 | 0 | 494.5197
3 |  | Shop | 141.5466 | 0 | 141.5466 | 0 | 219.3972
4 |  | Shop | 172.5469 | 0 | 172.5469 | 0 | 267.4477
5 |  | Shop | 183.5262 | 0 | 183.5262 | 0 | 284.4656
6 |  | Shop | 97.5218 | 0 | 97.5218 | 0 | 151.1589
7 |  | Shop | 97.5218 | 0 | 97.5218 | 0 | 151.1589
8 |  | Shop | 181.804 | 0 | 181.804 | 0 | 281.7961
9 |  | Shop | 174.3768 | 0 | 174.3768 | 0 | 270.284
10 |  | Shop | 172.5469 | 0 | 172.5469 | 0 | 267.4477
11 |  | Shop | 173.8386 | 0 | 173.8386 | 0 | 269.4498
12 |  | Shop | 143.1612 | 0 | 143.1612 | 0 | 221.8999
13 |  | Shop | 218.1863 | 0 | 218.1863 | 0 | 338.1887
14 |  | Shop | 236.808 | 0 | 236.808 | 0 | 367.0524
15 |  | Shop | 158.2308 | 0 | 158.2308 | 0 | 245.2577
16 |  | Shop | 248.1102 | 0 | 248.1102 | 0 | 384.5708
17 |  | Shop | 178.8977 | 0 | 178.8977 | 0 | 277.2914
18 |  | Shop | 178.8977 | 0 | 178.8977 | 0 | 277.2914
Wing B
Ground Floor For Commercial, Meter Room, Entrance Lobby & Parking
19 |  | Shop | 251.5547 | 0 | 251.5547 | 0 | 389.9098
20 |  | Shop | 223.5683 | 0 | 223.5683 | 0 | 346.5308
21 |  | Shop | 260.2735 | 0 | 260.2735 | 0 | 403.424
22 |  | Shop | 328.0867 | 0 | 328.0867 | 0 | 508.5344
23 |  | Shop | 217.2175 | 0 | 217.2175 | 0 | 336.6872
24 |  | Shop | 460.4839 | 0 | 460.4839 | 0 | 713.7501
25 |  | Shop | 296.2253 | 0 | 296.2253 | 0 | 459.1492
26 |  | Shop | 217.2175 | 0 | 217.2175 | 0 | 336.6872
27 |  | Shop | 337.4514 | 0 | 337.4514 | 0 | 523.0497
28 |  | Shop | 265.225 | 0 | 265.225 | 0 | 411.0987
29 |  | Shop | 280.4022 | 0 | 280.4022 | 0 | 434.6234
30 |  | Shop | 335.6215 | 0 | 335.6215 | 0 | 520.2134
Flat No. (Approved Plan) | Sale / Mhada | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Wing A | [7 empty] | 10.764
1st Floor For Residential | [7 empty] | 1
101 | Sale | 2BHK | 583.5164 | 116.4665 | 699.9829 | 0 | 1049.9744 |  | 50.975 | 10.59
102 | Sale | 2BHK | 605.7979 | 112.6991 | 718.497 | 0 | 1077.7455
103 | Sale | 3BHK | 823.7689 | 119.8033 | 943.5722 | 0 | 1415.3584
104 | Sale | 2BHK | 561.5579 | 35.5212 | 597.0791 | 108.5011 | 949.8692
105 | Sale | 2BHK | 580.9331 | 35.5212 | 616.4543 | 107.9629 | 978.6629
106 | Sale | 3BHK | 796.6436 | 82.3446 | 878.9882 | 0 | 1318.4824
107 | Sale | 2BHK | 617.2078 | 35.5212 | 652.729 | 222.7072 | 1053.3292
108 | Sale | 2BHK | 617.2078 | 99.567 | 716.7748 | 0 | 1075.1621
109 | Sale | 2BHK | 576.9504 | 0 | 576.9504 | 343.4792 | 951.2954
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 18
201 ,.., 2201 | Sale | 2BHK | 583.5164 | 116.4665 | 699.9829 | 0 | 1049.9744
202 ,.., 2202 | Sale | 2BHK | 605.7979 | 112.6991 | 718.497 | 0 | 1077.7455
203 ,.., 2203 | Sale | 3BHK | 823.7689 | 119.8033 | 943.5722 | 0 | 1415.3584
204 ,.., 2204 | Sale | 2BHK | 561.5579 | 113.9908 | 675.5486 | 0 | 1013.323
205 ,.., 2205 | Sale | 2BHK | 580.9331 | 113.9908 | 694.9238 | 0 | 1042.3858
206 ,.., 2206 | Sale | 3BHK | 796.6436 | 82.3446 | 878.9882 | 0 | 1318.4824
207 ,.., 2207 | Sale | 2BHK | 617.2078 | 111.9456 | 729.1534 | 0 | 1093.73
208 ,.., 2208 | Sale | 2BHK | 617.2078 | 99.567 | 716.7748 | 0 | 1075.1621
209 ,.., 2209 | Sale | 2BHK | 576.9504 | 78.4696 | 655.42 | 0 | 983.1299
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
801 ,.., 1801 | Sale | 2BHK | 583.5164 | 116.4665 | 699.9829 | 0 | 1049.9744
802 ,.., 1802 | Sale | 2BHK | 605.7979 | 112.6991 | 718.497 | 0 | 1077.7455
803 ,.., 1803 | - | Refuge Area
804 ,.., 1804 | Sale | 2BHK | 561.5579 | 113.9908 | 675.5486 | 0 | 1013.323
805 ,.., 1805 | Sale | 2BHK | 580.9331 | 113.9908 | 694.9238 | 0 | 1042.3858
806 ,.., 1806 | Sale | 3BHK | 796.6436 | 82.3446 | 878.9882 | 0 | 1318.4824
807 ,.., 1807 | Sale | 2BHK | 617.2078 | 111.9456 | 729.1534 | 0 | 1093.73
808 ,.., 1808 | Sale | 2BHK | 617.2078 | 99.567 | 716.7748 | 0 | 1075.1621
809 ,.., 1809 | Sale | 2BHK | 576.9504 | 78.4696 | 655.42 | 0 | 983.1299
Wing B | [7 empty] | 10.764
1st Floor For Residential | [7 empty] | 1
101 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
102 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
103 | Mhada | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815 |  | TERRACE AREA OF 17.66 DUCT PORTION
104 | Sale | 1BHK | 415.8133 | 0 | 415.8133 | 221.7384 | 697.6328
105 | Sale | 1BHK | 411.4001 | 0 | 411.4001 | 409.4626 | 719.4658
106 | Sale | 1BHK | 411.4001 | 0 | 411.4001 | 506.7691 | 743.7924
107 | Sale | 3BHK | 763.2752 | 0 | 763.2752 | 303.3295 | 1220.7452
108 | Mhada | 1BHK | 415.2751 | 79.1154 | 494.3905 | 0 | 741.5858 |  | TERRACE AREA OF 11.09 DUCT PORTION
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
2nd to 7th, 9th & 10th Floor | [7 empty] | 8
201 ,.., 1001 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646 |  | 5462.5023
202 ,.., 1002 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
203 ,.., 1003 | Mhada | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
204 ,.., 1004 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
205 ,.., 1005 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
206 ,.., 1006 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
207 ,.., 1007 | Sale | 3BHK | 761.2301 | 100.6434 | 861.8735 | 0 | 1292.8102
208 ,.., 1008 | Mhada | 1BHK | 411.2924 | 79.1154 | 490.4078 | 0 | 735.6118
8th Floor ( Part Refuge Area) | [7 empty] | 1
801 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
802 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
803 | Mhada | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
804 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
805 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
806 | - | Refuge Area
807 | Sale | 3BHK | 761.2301 | 100.6434 | 861.8735 | 0 | 1292.8102
808 | Mhada | 1BHK | 411.2924 | 79.1154 | 490.4078 | 0 | 735.6118
11th Floor | [7 empty] | 1
1101 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1102 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1103 | Mhada | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1104 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1105 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617 |  | 5495.5496
1106 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
1107 | Sale | 3BHK | 761.2301 | 100.6434 | 861.8735 | 0 | 1292.8102
1108 | Sale | 1BHK | 411.2924 | 79.1154 | 490.4078 | 0 | 735.6118
12th, 14th to 17th, 19th & 20th Floor | [7 empty] | 7
1201 ,.., 2001 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1202 ,.., 2002 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1203 ,.., 2003 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1204 ,.., 2004 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1205 ,.., 2005 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
1206 ,.., 2006 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
1207 ,.., 2007 | Sale | 3BHK | 761.2301 | 100.6434 | 861.8735 | 0 | 1292.8102
1208 ,.., 2008 | Sale | 1BHK | 411.2924 | 79.1154 | 490.4078 | 0 | 735.6118
13th & 18th Floor | [7 empty] | 2
1301 & 1801 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1302 & 1802 | Sale | 2BHK | 558.221 | 113.022 | 671.243 | 0 | 1006.8646
1303 & 1803 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1304 & 1804 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
1305 & 1805 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
1306 & 1806 | - | Refuge Area
1307 & 1807 | Sale | 3BHK | 761.2301 | 100.6434 | 861.8735 | 0 | 1292.8102
1308 & 1808 | Sale | 1BHK | 411.2924 | 79.1154 | 490.4078 | 0 | 735.6118
21st Floor (Part Terrace Area) | [7 empty] | 1
2101 | - | Terrace Area
2102 | -
2103 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
2104 | Sale | 1BHK | 411.8306 | 77.8237 | 489.6544 | 0 | 734.4815
2105 | Sale | 1BHK | 407.4174 | 77.8237 | 485.2411 | 0 | 727.8617
2106 | - | Terrace Area
2107 | Sale | 2BHK | 684.0522 | 81.2682 | 765.3204 | 0 | 1147.9806
2108 | - | Terrace Area
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 23/06/2025
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Agarwal Skyrise
Layout :
Google Map :
Formulas:
Bolinj = [Bolinj, row above]
Wing A
Wing B
B
Wing A
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate