## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Sr.No. | Particulars |  |  | Details
1 | Name of the project |  |  | Shree Viraj Residency Wing-D Phase 3
2 | Address as per the site visit |  |  | Shree Viraj Residency Wing-D Phase 3, Near Nisarg Samruddhi Heights, Internal Road, At Village - Shirgaon, Badlapur East, Tal. Ambernath, Dist.Thane - 421503.
|  |  |  | Latitude, Longitude : |  | 19.152785,73.235980
| Location Link |  |  | https://maps.app.goo.gl/kowug88zke35nkyM9
| RERA Name & No. |  |  | Shree Viraj Residency Wing-D Phase 3 |  | P51700080527
| Name / No of the Existing Building |  |  | NA
3 | Closest landmark |  |  | Nisarg Samruddhi Heights
4 | Address as per the Sale brochure |  |  | Shree Viraj Residency Wing-D Phase 3, Near Nisarg Samruddhi, Shirgaon Village, MIDC, Badlapur East
5 | Address as per the plans & permissions |  |  | Proposed Residential Building On Land Bearing S No. 63, H No.5A, P. No. 1 to 7, S. No. 63, H. No.6, 7 & 8, S No. 62, H No.8, Village- Shirgaon, Tal. Ambernath, Dist. Thane |  |  |  | Same
6 | Address as per the legal documentation |  |  | Proposed Residential Building On Land Bearing S No. 63, H No.5A, P. No. 1 to 7, S. No. 63, H. No.6, 7 & 8, S No. 62, H No.8, Village- Shirgaon, Tal. Ambernath, Dist. Thane
7 | Date of APF initiation from YBL |  |  | 2025-09-19
8 | Date of documents delivery / Receipt |  |  | 2025-09-19
9 | List of documents provided |  |  | Approved Plan Builder Profile Cost Sheet Sale Plan
10 | Queries communicated to YBL regarding discrepancies in documentation, details etc |  |  | None
11 | Date of query resolution from YBL |  |  | None
12 | Any further documentation that needs to be complied prior to start of disbursement in the project? Provide complete details. |  |  | None
13 | Name of developer personnel for site visit coordination with contact details (Mobile, landline, email) |  |  | Mr. Ganesh Rane 7767052456
14 | Date of contacting concerned developer personnel for site visit |  |  | 2025-09-20
15 | Date, day & timing of Site visit |  |  | 20/09/2025, Saturday at 02:18PM
16 | Name of the person conducting the site visit & contact details |  |  | Mr. Sudhir Bhosale 9096679149
17 | Name of person met at site (Full Name, Designation, Mobile Number, Landline Number, email id) |  |  | Ms. Pooja 7030002074
18 | Details of Financial Institutions who's APF Approval Letters / Boards were displayed on site |  |  | None
19 | Details of sold v/s unsold units |  |  | Unsold = 56, Sold = 0
20 | Has the developer availed any kind of construction / project finance? If yes, details are required. |  |  | None
21 | Developer name |  |  | M/s. Shree Viraj Enterprises
22 | Developer group parent company |  |  | M/s. Shree Viraj Enterprises
23 | Developer office address along with contact details |  |  | Unit No. 1-2, Shree Viraj House, 171, LBS Marg, Sarvodaya Hospital, Ghatkopar (West), Kurla, Mumbai - 400086
24 | Architect details ( Name, office address, mobile number, registration number ) |  |  | Raj Associates, Office No. 102/103, 1st Floor, Vighnaharta Arcade, Near Spandan Hospital, New DP Road, Katrap, Badlapur (East) 421503 Reg No. CA/2001/27259
25 | Authority jurisdiction for the project location |  |  | Kulgaon Badlapur Municipal Council |  |  |  | Same
26 | Zoning Approval for the project location as per the MDP |  |  | Kulgaon Badlapur Municipal Council
27 | Does the proposed development match with the Zoning Approval? Detailed feedback |  |  | Yes its comes under Residential zone
28 | Project type ( Residential / Mixed / Flats / Villas / Row Houses etc ) |  |  | Residential
29 | Plot Area (Sq.M) |  |  | 3881.56
30 | Does the Plot Area match as per the legal documentation? |  |  | Yes
31 | Does the Plot Area match as per the Non Agriculture documentation? |  |  | Yes as per plan. But NA order not provided to verify.
32 | Does the ongoing construction match with the Approved Site Layout? If no, details expected. |  |  | Yes
33 | Net Plot Area (Sq.M) |  |  | 3881.56
| Total Builtup Area (Sq.M) |  |  | 7242.31 |  |  |  | 1.8658
| Proposed Builtup Area of Wing D (Sq.M) |  |  | 2615.28
34 | Permissible FSI / FAR |  |  | 1.1
35 | Premium FSI / FAR |  |  | 0.3
36 | Ancillary FSI / FAR |  |  | 0.25409
37 | Permissible TDR |  |  | 0.21554
38 | Total FSI |  |  | 1.8696
39 | Project launch date |  |  | 2025-06-16 |  |  |  | As per site person Ms. Pooja 7030002074
| Project Construction Start date |  |  | March 2023 |  |  |  | provided docs.
40 | Average weighted stage of construction for the project with construction stages of individual wings
Construction Details: |  | Wing D = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 63.57% |  | 73.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 71.43% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction Details: |  | Building No.6 (Wing B) = Stilt + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 20% |  | 30% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
41 | Expected Completion Date |  |  | As projected by the RERA |  |  | 2027-12-31
|  |  |  | As projected by the Developer |  |  | Dec 2027 | As per site person Ms. Pooja 7030002074
42 | Permissions applicable v/s available (Detailed analysis) |  |  | NA
43 | Physical & social infrastructure availability details ( Bus stop, railway station, public park, main road, airport, hospital, public transport, school, market etc ) |  |  | SCHOOL : Dwarkabai Ganesh Naik School - 1Km Aniruddha High School & Junior College - 1.7Km SHOPPING : Reliance SMART Bazaar - 0.75Km BMart - 0.5Km HOSPITALS : Vaishnavi Multispeciality Hospital - 0.85Km Shreeji Multispeciality Hospital - 1.4Km PETROL PUMP : Nayana Energy Petrol Pump - 1.3Km BP Petrol Pump - 1.5Km
44 | Proposed Amenities |  |  | Childerns play Area with outdoor Activity Lift Stilt Parking Power backup for Lobby, Lift & Common Areas 24 X 7 CCTV Decorative Entrance Gate Attractive Entrance Lobby |  |  |  | Sale plan
45 | Boundary details ( Are they matching as per the legal & technical documentation ) |  |  | Yes
46 | Phase, building & wingwise structure details ( Approvals v/s proposed v/s constructed ( If 100 % complete ) ( Deviations to be pointed out ) |  |  | Approved Floor
Wing D = G + 1st to 7th Floor
Proposed Floor
Wing D = G + 1st to 7th Floor
Building No.6 (Wing B) = Stilt + 1st to 21st Floor
Approval Detail : Plan approval
Layout Plan No. |  | KBNP/NRV/BD/505-182 |  |  | Dated | 2023-03-06
Approved Floor Plan No |  | KBNP/NRV/BD/505-182 |  |  | Dated | 2023-03-06
Commencement Certificate No. Valid Up to: |  | KBNP/NRV/BP/505/2022-2023 Unique No.182 |  |  | Dated | 2023-03-06
Wing D = Stilt + 1st to 7th Floor
Fire Noc No Valid Up to: |  |  |  |  | Dated
Environmental Clearance Certificate (EC) No Valid Up for: |  |  |  |  | Dated
Airport Noc No Valid Up for: |  |  |  |  | Dated
Valid Upto Date
O. Certificate No.: |  | NA Approved upto : |  | Date of approval: | Dated | NA | NA
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing D |  | 56 |  | 26733.0937 |  | 38762.9858
Total |  | 56 |  | 26733.0937 |  | 38762.9858
Grand Total |  | 56 |  | 26733.0937 |  | 38762.9858
Building Details Floor Wise
Details of Commercial in Building
Flat No. (Approved Plan) | Description | Carpet Area | Otla Area | Loft Area | Gross Carpet Area | Attached Terrace Area | Saleable Area Loading :
[7 empty] | 50% | [5 empty] | #REF! | #REF! | #REF!
Ground Floor For Commercial & Parking | [12 empty] | #REF! | #REF! | #REF!
1 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | #REF! | #REF! | #REF!
2 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | #REF! | #REF! | #REF!
3 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | #REF! | #REF! | #REF!
4 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | #REF! | #REF! | #REF!
5 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | #REF! | #REF! | #REF!
[13 empty] | #REF! | #REF! | #REF!
Details of Residential in Building | [12 empty] | #REF! | #REF! | #REF!
Flat No. (Approved Plan) | Description | RERA Carpet Area | Balcony Area | A.P Area | Gross Carpet Area | Attached Terrace Area | Saleable Area Loading : | 10.764 |  |  |  |  | #REF! | #REF! | #REF!
45%
Wing D | [8 empty] | Vist | 2484000 | 3404000
Ground Floor For Entrance Lobby, Driver Room, Meter Room, Society Office & Parking | [11 empty] | 2552000 | #REF! | #REF! | #REF!
1st to 7th Floor For Residential | [7 empty] | 7 |  | 3700 |  |  | #REF! | #REF! | #REF!
1 | 1BHK | 386.2123 | 0 | 82.3177 | 468.53 | 0 | 679.3685 | 33.005 |  | 2513663.5036 |  |  | #REF! | #REF! | #REF!
2 | 1BHK | 373.4032 | 0 | 82.9366 | 456.3398 | 0 | 661.6927 | 4080.4441 |  | 2448262.9197 |  |  | #REF! | #REF! | #REF!
3 | 1BHK | 373.4032 | 0 | 82.9366 | 456.3398 | 0 | 661.6927 | 4080.4441 |  | 2448262.9197 |  |  | #REF! | #REF! | #REF!
4 | 1BHK | 361.1322 | 0 | 96.5531 | 457.6853 | 0 | 663.6437 |  |  | 2455481.5272 |  |  | #REF! | #REF! | #REF!
5 | 1BHK | 373.4032 | 0 | 82.3177 | 455.7208 | 0 | 660.7952 | 3707.6539 |  | 2444942.3602 |  | 4085.9859 | #REF! | #REF! | #REF!
6 | 1BHK | 373.4032 | 0 | 82.3177 | 455.7208 | 0 | 660.7952 |  |  | 2444942.3602 |  |  | #REF! | #REF! | #REF!
7 | 2BHK | 476.5223 | 0 | 118.2156 | 594.7379 | 0 | 862.37 | 42.495 |  | 3190768.8872 |  |  | #REF! | #REF! | #REF!
8 | 1BHK | 389.7644 | 0 | 84.1745 | 473.9389 | 0 | 687.2114 | 3637.8906 |  | 2542682.3058 |  |  | #REF! | #REF! | #REF!
48 | Phase, building & wingwise naming & numbering details |  |  | Wing D = G + 1st to 7th Floor
49 | Phase, building, wing, unit wise pricing details (Base pricing, floor rise, location / view specific, etc) |  |  | Flat = 56
50 | Are there any deviations between the ongoing construction & the available plans & permissions. If yes, details are expected. |  |  | No
51 | Pricing comparisons ( Builder pricing v/s Resale v/s Nearby Projects with Rationale & justification ) |  |  | As per Site Details :
|  |  |  | Realizable Rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 3700
52 | Transaction documentation details ( Black / White percentages etc ) |  |  | No
53 | All details payable |  |  | As per Market Enquiry :
|  |  |  | Realizable Rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 3700
|  |  |  | Recommended rate of Parking |  |  | 200000
54 | Different types of payment schemes offered such as CLPP, TLPP, C & TLPP, Interest Subvention Plans etc |  |  | NA
55 | Schedule of Payment as per the developer |  |  | NA
|  |  |  | At Booking |  |  | 10%
|  |  |  | Plinth |  |  | 20% | 0.020816 | 48.0392
|  |  |  | 1st Slab |  |  | 5%
|  |  |  | 2nd Slab |  |  | 5% |  | 0.2
|  |  |  | 3rd Slab |  |  | 5%
|  |  |  | 4th Slab |  |  | 10%
|  |  |  | 5th Slab |  |  | 10%
|  |  |  | Brick work |  |  | 5%
|  |  |  | Internal/External Plaster |  |  | 10%
|  |  |  | Flooring & Tiling |  |  | 5%
|  |  |  | Electric & Sliding Window |  |  | 5%
|  |  |  | Painting & Sliding Window |  |  | 5%
|  |  |  | On Possession |  |  | 5%
|  |  |  | Total |  |  | 100%
56 | Are there any discrepancies in the legal / technical documentation that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
57 | Any evidences of social disturbances at the project site that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
58 | Any notices or boards of litigation at project site / developer office that may affect the business interests of YBL? If yes, please elaborate. |  |  | None
59 | Any further documentation that needs to be tracked by the Financial Institution & obtained from the customer / developer post project completion? Provide complete details. |  |  | None
60 | Declarations :-
(a) | Have you done APF technical for this project for any other Financial Institution? |  |  | None
(b) | Have you done evaluation of this project for the Project / Construction Finance perspective for any Financial Insitution? |  |  | No
Remarks:
1 | Construction work is in process at the time of Visit (labour found).
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + AP Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | We have referred approved CC from RERA site.
PHOTOGRAPHS OF PROPERTY : |  |  | Shree Viraj Residency Wing-D Phase 3
Layout
Google Map :
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
Name of Engineer Visited the property |  | Mr. Sudhir Bhosale |  | Authorized Signatory Name & Seal of the Agency
Formulas:
P51700080527 = [P51700080527, row above]
Wing A
Wing B
Wing C
Wing D (Phase III)
N
Shree Viraj Residency
Wing D Phase 3
A
B
C
Note on E22: Visit Date
Note on E23: Visitor Name
Note on E24: Met person & No
Note on E26: mention it if provided by builder or else NA
Note on E82: 2 School 2 Shopping Centre or mall 2 Hospital
Note on E138: Proposed Structure

## Valuation
Lifestyle Amenities : Internal Paved roads. Decorative compound Walls with security features Power backup for lifts & common areas Modern Amenities ; FLOORING Vitrified flooring in all rooms Anti-skid tiles in attached terrace area KITCHEN Granite kitchen platform Stainless steel and sink mixture TOILETS Designer bathroom with branded sanitary ware Concealed plumbing with premium C. P. fittings Geyser connection to all bathrooms WINDOWS Powdered Aluminium Sliding windows
SECURITY Modern security system with CCTV at security cabin Intercom facility in each flat ELECTRIFICATION Branded concealed copper wiring with isolater / MCB TV, telephone & internet points in all rooms WALLS AND PAINTS Gypsum finished internal walls with plastic paints