## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 24/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-20
Name of the builder group |  |  |  | M/s.Gargi Builder and Developers
Name of the builder company |  |  |  | M/s.Gargi Builder and Developers
Name of the Project |  |  |  | Gargi Hills
Contect Details ( Name & Contect No.) |  |  |  | 9765388488/9607388488
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Chetan : 9765388488
Name / No of the Building |  |  |  | Bldg No. 1 - Residential Bunglow Bldg No. 2 (Gargi Classic) - A, B & C Wing
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000018173
Project location details |  | Gargi Hills, Survey No.21/6/A, Waliv Road, Waliv, Vasai Road, Vasai, Palghar.
Survey No |  | 21/6/A
Road |  | Waliv Road |  | Village |  | Waliv
City |  | Vasai Road |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Near by Landmark |  | Om Shiv Shakti Complex |  | Distance from city centre: |  | 6.6 Km from Vasai Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Waliv Road
West | NA | NA |  |  | Open Space
North | NA | NA |  |  | Building
South | NA | NA |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.4185 |  | Longitude |  | 72.8612
Location Link |  | https://goo.gl/maps/RX7wbZoUmnxJA3LL9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3511.78
Permissible FSI |  |  |  | 1.1 |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1407
Total FSI availaible for the project |  |  |  | 2.2407
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7868.86
Total number of Buildings |  |  |  | 4 Buildings
Approval Detail : Plan approval
Layout Approval No |  | VVCMC/TP/AMEND/VP/5978/216/2022-23 |  |  | Dated | 2022-07-25
Approved Floor plan No : Building No.1 |  | VVCMC/TP/CC/VP-5978/58/2018-19 |  |  | Dated | 11/06/2018
Approved Floor plan No: Building No.2 |  | VVCMC/TP/AMEND/VP/5978/216/2022-23 |  |  | Dated | 2022-07-25
Commencement Certificate No. |  | VVCMC/TP/RDP/VP-5978/215/2022-23 |  |  | Dated | 2022-07-25
Valid Up to: Building No.1 = Gr. + 1st Floor Building No.2 = Wing A to C = Stilt + 1st to 14th Floor
Commencement Certificate No. Building No.2 |  | VVCMC/TP/CC/VP-5978/59/2018-19 |  |  | Dated | 11/06/2018.
Valid Up to: Building No.2(Wing A,B& C) - Gr. + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7868.86
Approved no of units |  |  | Flats - 159
Approved no of Floors |  |  | Building No.1 : Gr. + 1st Floor Building No.2 : Wing A to C = Gr. + 1st to 14th Floor
Proposed no of Floors |  |  | Building No.1 : Gr. + 1st Floor Building No.2 : (Wing A, B & C) = Gr. + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.1 = Gr + 1st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 2 Slab completed, Brickwork upto 1 Floor completed, Internal Plaster upto 1 Floor completed, External Plaster upto 1 Floor completed, Flooring upto 1 Floor completed, Painting upto 1 Floor completed, Finishing upto 1 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 1 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [5 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 1 | 100% | 100% |  | 100%
Plinth |  | 1 | 100%
RCC |  | 2 | 100% |  |  |  |  | Excavation in process | 0.5
Brickwork | Brickwork & Internal Plaster | 1 | 100% |  |  |  |  | Excavation Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 1 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 100% |  |  |  |  | Footing in Process | 0.25
Flooring & Fitting | Flooring & Fitting | 1 | 100% |  |  |  |  | Footing Completed | 0.5
Painting & Wooden |  | 1 | 100% |  |  |  |  | Plinth in process | 0.75
Building Common Amenities | Building Common Amenities | 1 | 100% |  |  |  |  | Plinth completed | 1
Possession |  | 1 | 100%
Construction details: |  | Building No.2 (Wing A & B) = Gr + 1st to 14th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 15 Slab completed, Brickwork upto 14 Floor completed, Internal Plaster upto 14 Floor completed, External Plaster upto 14 Floor completed, Flooring upto 14 Floor completed, Painting upto 14 Floor completed, Finishing upto 14 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 14 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [5 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 14 | 100% | 100% |  | 100%
Plinth |  | 14 | 100%
RCC |  | 15 | 100% |  |  |  |  | Excavation in process | 7
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Excavation Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 14 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Footing in Process | 3.5
Flooring & Fitting | Flooring & Fitting | 14 | 100% |  |  |  |  | Footing Completed | 7
Painting & Wooden |  | 14 | 100% |  |  |  |  | Plinth in process | 10.5
Building Common Amenities | Building Common Amenities | 14 | 100% |  |  |  |  | Plinth completed | 14
Possession |  | 14 | 100%
Construction details: |  | Building No.2(Wing C) = Gr + 1st to 14th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 15 Slab completed, Brickwork upto 14 Floor completed, Internal Plaster upto 14 Floor completed, External Plaster upto 14 Floor completed, Flooring upto 13 Floor completed, Painting upto 9 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 14 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 15 Slab completed, Brickwork upto 14 Floor completed, Internal Plaster upto 14 Floor completed, External Plaster upto 14 Floor completed, Flooring upto 13 Floor completed, Painting upto 9 Floor completed | [5 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 14 | 100% | 87.5% |  | 94.64%
Plinth |  | 14 | 100%
RCC |  | 15 | 100% |  |  |  |  | Excavation in process | 7
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Excavation Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 14 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Footing in Process | 3.5
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Footing Completed | 7
Painting & Wooden |  | 9 | 64.29% |  |  |  |  | Plinth in process | 10.5
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 14
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5600 |  |  | rate 5600 by akash verbal on 24/09/2025
Recommended rate of the Bungalow Per Sq. Ft.(on Saleable area) |  |  |  |  | 5500
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society & Development Charges |  |  |  |  | 125000
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 4480
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 1 | 1710.7494 |  | 4000
Building No.2 - A Wing |  | 52 | 21255.8161 |  | 35281.7645
Building No.2 - B Wing |  | 52 | 21222.9052 |  | 35235.8962
Building No.2 - C Wing |  | 54 | 24084.8375 |  | 39739.9819
Total |  | 159 | 68274.3082 |  | 114257.6426
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. As per Sale Plan |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Building No.1
Ground Floor & 1st Floor
1 |  | 3BHK (Bungalow) | 1710.7494 | 390.4103 | 4000 | Ground Floor & 1st Floor |  | 3418.4368 | 2.1099
Building No.2
A Wing
Ground Floor for Parking
1st to 4th, 6th & 7th Floor
101,…401,601 & 701 |  | 1BHK | 347.6234 | 0 | 585 | 1st to 4th, 6th & 7th Floor |  | 5300 | 1.6829
102,…402,602 & 702 |  | 1BHK | 351.6922 | 0 | 585 |  |  | 5300 | 1.6634
103,…403,603 & 703 |  | 2BHK | 455.8446 | 0 | 755 |  |  | 5300 | 1.6563
104,…404,604 & 704 |  | 1BHK | 342.0261 | 0 | 580 |  |  | 5345.6897 | 1.6958
5th Floor
501 |  | 1BHK | 347.6234 | 0 | 585 | 5th Floor |  |  | 1.6829
502 |  | 1BHK | 351.6922 | 0 | 585 |  |  |  | 1.6634
503 |  | 2BHK | 474.2618 | 0 | 755 |  |  |  | 1.5919
504 |  | 1BHK | 343.5061 | 0 | 580 |  |  |  | 1.6885
8th Floor (Part Refuge Area)
801 |  | 1BHK | 367.1762 | 0 | 605.8407 | 8th Floor (Part Refuge Area) |  |  | 1.65
802 |  | 1BHK | 367.1762 | 0 | 605.8407 |  |  |  | 1.65
803 |  | Refuge Area
804 |  | 1BHK | 402.5467 | 0 | 664.202 |  |  |  | 1.65
9th & 10th Floor
901 & 1001 |  | 1BHK | 367.1762 | 0 | 605.8407 | 9th & 10th Floor |  |  | 1.65
902 & 1002 |  | 1BHK | 367.0793 | 0 | 605.6809 |  |  |  | 1.65
903 & 1003 |  | 2BHK | 538.0385 | 0 | 887.7636 |  |  |  | 1.65
904 & 1004 |  | 1BHK | 402.5467 | 0 | 664.202 |  |  |  | 1.65
11th Floor
1101 |  | 2BHK Duplex with 12th Floor | 867.5246 | 0 | 1431.4156 | 11th Floor |  |  | 1.65
1102 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1103 |  | 2BHK | 491.6188 | 0 | 811.171 |  |  |  | 1.65
1104 |  | 1BHK | 380.3459 | 0 | 627.5708 |  |  |  | 1.65
13th Floor (Part Refuge Area)
1301 |  | 2BHK Duplex with 14th Floor | 867.5246 | 0 | 1431.4156 | 13th Floor (Part Refuge Area) |  |  | 1.65
1302 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1303 |  | Refuge Area
1304 |  | 1BHK | 380.3459 | 0 | 627.5708 |  |  |  | 1.65
12th & 14th Floor
1201 & 1401 |  | 2BHK Duplex with 11th & 13th Floor |  |  |  | 12th & 14th Floor
1202 & 1402 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1203 & 1403 |  | 2BHK | 491.6188 | 0 | 811.171 |  |  |  | 1.65
1204 & 1404 |  | 1BHK | 380.3459 | 0 | 627.5708 |  |  |  | 1.65
B Wing
Ground Floor for Parking
1st to 4th, 6th & 7th Floor
101,…401,601 & 701 |  | 1BHK | 348.6998 | 0 | 585 | 1st to 4th, 6th & 7th Floor |  |  | 1.6777
102,…402,602 & 702 |  | 1BHK | 351.6922 | 0 | 585 |  |  |  | 1.6634
103,…403,603 & 703 |  | 1BHK | 350.2067 | 0 | 585 |  |  |  | 1.6704
104,…404,604 & 704 |  | 1BHK | 348.6998 | 0 | 585 |  |  |  | 1.6777
5th Floor
501 |  | 1BHK | 348.6998 | 0 | 585 | 5th Floor |  | 4000 | 1.6777
502 |  | 1BHK | 351.6922 | 0 | 585 |  |  |  | 1.6634
503 |  | 1BHK | 350.2067 | 0 | 585 |  |  |  | 1.6704
504 |  | 1BHK | 348.6998 | 0 | 585 |  |  |  | 1.6777
8th Floor
501 |  | 1BHK | 406.637 | 0 | 670.9511 | 8th Floor |  |  | 1.65
502 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
503 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
504 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
9th to 10th Floor
901 & 1001 |  | 1BHK | 406.637 | 0 | 670.9511 | 9th to 10th Floor |  |  | 1.65
902 & 1002 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
903 & 1003 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
904 & 1004 |  | 1BHK | 406.637 | 0 | 670.9511 |  |  |  | 1.65
11th Floor
1101 |  | 2BHK Duplex with 12th Floor | 868.8163 | 0 | 1433.5468 | 11th Floor |  |  | 1.65
1102 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1103 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1104 |  | 2BHK Duplex with 12th Floor | 867.5246 | 0 | 1431.4156 |  |  |  | 1.65
13th Floor
1301 |  | 2BHK Duplex with 14th Floor | 868.8163 | 0 | 1433.5468 | 13th Floor |  |  | 1.65
1302 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1303 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1304 |  | 2BHK Duplex with 14th Floor | 867.5246 | 0 | 1431.4156 |  |  |  | 1.65
12th & 14th Floor
1201 & 1401 |  | 2BHK Duplex with 11th & 13th Floor |  |  |  | 12th & 14th Floor
1202 & 1402 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1203 & 1403 |  | 1BHK | 384.4363 | 0 | 634.3198 |  |  |  | 1.65
1204 & 1404 |  | 2BHK Duplex with 11th & 13th Floor
C Wing
Ground Floor for Parking
1st to 4th, 6th & 7th Floor for Residential
101,…401,601 & 701 |  | 1BHK | 390.8947 | 0 | 644.9762 | 1st to 4th, 6th & 7th Floor for Residential |  | 32.2425
102,…402,602 & 702 |  | 2BHK | 480.1282 | 0 | 792.2116
103,…403,603 & 703 |  | 1BHK | 351.6922 | 0 | 580.2921
104,…404,604 & 704 |  | 1BHK | 348.6998 | 0 | 575.3546
5th Floor
501 |  | 1BHK | 390.8947 | 0 | 644.9762 | 5th Floor
502 |  | 2BHK | 480.1282 | 0 | 792.2116 |  |  | 3483.9178
503 |  | 1BHK | 351.6922 | 0 | 580.2921
504 |  | 1BHK | 348.6998 | 0 | 575.3546
8th Floor (Part Refuge Area)
801 |  | 1BHK | 459.4075 | 0 | 758.0224 | 8th Floor (Part Refuge Area)
802 |  | 1.5BHK | 575.3627 | 0 | 949.3485
803 |  | 1BHK | 396.8687 | 0 | 654.8333
804 |  | 1BHK | 419.0694 | 0 | 691.4646
9th & 10th Floor
901 & 1001 |  | 1BHK | 459.4075 | 0 | 758.0224 | 9th & 10th Floor
902 & 1002 |  | 1.5BHK | 575.3627 | 0 | 949.3485
903 & 1003 |  | 1BHK | 396.8687 | 0 | 654.8333
904 & 1004 |  | 1BHK | 419.0694 | 0 | 691.4646
11th Floor
1101 |  | 1BHK | 459.4075 | 0 | 758.0224 | 11th Floor
1102 |  | 1.5BHK | 575.3627 | 0 | 949.3485
1103 |  | 1BHK | 419.0694 | 0 | 691.4646
1104 |  | 2BHK Duplex with 12th Floor | 858.725 | 0 | 1416.8963
13th Floor
1301 |  | 1BHK | 459.4075 | 0 | 758.0224 | 13th Floor
1302 |  | 1.5BHK | 575.3627 | 0 | 949.3485
1303 |  | 1BHK | 419.0694 | 0 | 691.4646
1304 |  | 2BHK Duplex with 12th Floor | 858.725 | 0 | 1416.8963
12th & 14th Floor
1201 & 1401 |  | 1BHK | 459.4075 | 0 | 758.0224 | 12th & 14th Floor
1202 & 1402 |  | 1.5BHK | 575.3627 | 0 | 949.3485
1203 & 1403 |  | 1BHK | 419.0694 | 0 | 691.4646
1204 & 1404 |  | 2BHK Duplex with 11th & 13th Floor
Building No.3
Ground Floor | [8 empty] | #DIV/0!
1 |  | Shop | 814.7272 | 0 | 1303.5635 | Ground Floor |  |  | 1.6
1st to 3th Floor | [8 empty] | #DIV/0!
1 |  | Office | 911.5224 | 0 | 1458.4359 | 1st to 3th Floor |  |  | 1.6
4th Floor | [8 empty] | #DIV/0!
1 |  | Office | 911.5224 | 0 | 1458.4359 | 4th Floor |  |  | 1.6
Remarks:
1. Bldg No.1 (Bunglow) & Bldg No.2 (A & B Wing) - All work completed. Please povide OC. Bldg No.2 (C Wing) - Construction work is in process. 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + A.F Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have considered Other charges from cost sheet. 8. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 9. We have updated revised approved floor plan & C.C of Building No. 2 Wing A, B & C (on 09/03/2022). 10. We have updated latest approved floor plans & CC for Building No. 2 Wing C (On 04/10/2023). 11. Recommended Rates of the Property have been revised on 24/09/2025. 9. On Site, we meet Mr. Pradnesh Patil : 9705588488.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Gargi Hills
Layout :
Google Map :
A & B
A & B
Wing C
Wing B
Wing A
Building No.02
Building No.01
A Wing
C Wing
C Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
proptiger. | Gargi Hills | 1BHK | 0 | 585 | 4600 | 2691000
proptiger. | Gargi Hills | 1BHK | 0 | 600 | 4600 | 2760000
addressofchoice | Gargi Hills | 1BHK | 0 | 585 | 4600 | 2691000
3brick | Gargi Hills | 1BHK | 0 | 585 | 4600 | 2691000
3brick | Gargi Hills | 1BHK | 0 | 600 | 4600 | 2760000
Average |  |  | 0 | 0 | 4600
Valuation Adopted |  |  |  |  | 4600

## Flat detail
| Floor No | Building 1
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall | 6.4 | 5.05 | 32.32 | CB |  |  | 0 | 1.5 | 4.75 | 7.125
|  |  |  | 0 | FB |  |  | 0 | 2.9 | 10.05 | 29.145
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 3.05 | 8.25 | 25.1625 | CB |  |  | 0 |  |  | 0
| Bal 1 | 3.05 | 1.5 | 4.575 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.65 | 3.05 | 11.1325 | CB |  |  | 0 |  |  | 0
| Bal 2 | 3.65 | 1.5 | 5.475 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 4.25 | 15.5125 | CB |  |  | 0 |  |  | 0
| Bal 3 | 3.65 | 0.9 | 3.285 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 | 3.65 | 3.65 | 13.3225 | CB |  |  | 0 |  |  | 0
| Bal 4 | 3.65 | 0.9 | 3.285 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.25 | 2.95 | 3.6875 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.3 | 1.95 | 2.535 | DB |  |  | 0 |  |  | 0
| toilet3 | 2.7 | 2.95 | 7.965 | DB |  |  | 0 |  |  | 0
|  | 2.7 | 2.95 | 7.965 |  |  |  | 0 |  |  | 0
| passage1 | 1.3 | 0.9 | 1.17 |  |  |  | 0 |  |  | 0
| passage2 | 1.5 | 4.35 | 6.525 |  |  |  | 0 |  |  | 0
| passage3 | 2.1 | 2.65 | 5.565 |  |  |  | 0 |  |  | 0
| passage4 | 2.7 | 3.5 | 9.45 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 1710.7494 | 158.9325 |  |  | 0 | 0 |  | 390.4103 | 36.27
|  |  | 1710.7494 | 158.9325