## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-19
Branch Name/ID |  | Mahindra Rural Housing Finance - Thane |  |  | Date & Time of Site Visit | 22/09/2025 at 12.15 PM
Name of the person met at site & Contact No |  | Mr. Siddhesh - 8652734528 |  |  | Date of Report Release | 26/09/2025
Project Details
Name of the project |  | Arkade Rare
Address |  | Arkade Rare, CTS No.403B/1, 403B, 403B/2, 403B/3 and 403B/4, near Samriddhi Garden, Samriddhi Garden Road, Kanjur West, Bhandup West, Kurla, Mumbai - 400078. | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune
CTS No |  | 403B/1, 403B, 403B/2, 403B/3 and 403B/4 | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Kanjur West | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Samriddhi Garden Road | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Bhandup West | [9 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Kurla | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Mumbai | [9 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 400078 | [9 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51800077307 | [12 empty] | Mahad | Daund
Landmark |  | Samriddhi Garden | [12 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.144783,72.931719 | [9 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/sZKauiJa5SqJq3CZ9 | [12 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Arkade Developers Limited | [12 empty] | Mahasala | Bhor
Office address (agreement) |  | 2nd Floor, Arkade House, A.S Marg, Next to Children's Academy, Ashok Nagar, Kandivali East, Borivali, Mumbai - 400101 | [5 empty] | As per RERA | [6 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [12 empty] | Murud | Velhe
Builder Bank Details |  | HDFC BANK IFSC Code - HDFC0000667
Contact No. |  | Mr. Siddhesh - 9653169939
Location of the project Municipal Limit : |  | Municpal Council of Greater Mumbai (MCGM)
Project Type (Apartments/Plot/ Combined) |  | Apartments + Shops
No of Wings / Buildings |  | Wing A to G |  |  | Other HFC's Approval / Funding | None |  | https://www.arkaderarebhandupwest.com/?utm_source=google&utm_medium=cpc&utm_campaign=Arkade+Rare+Central&utm_term=arkade%20rare&utm_Physical_Location=9062223&utm_Targetid=kwd-2321075479859&utm_Target=&utm_Placement=&utm_Adposition=&gad_source=1&gad_campaignid=21616592589&gbraid=0AAAAA9iUuL4ddRxdBNH9G9dpK8gf7qML2&gclid=CjwKCAjwv5zEBhBwEiwAOg2YKHwft_d7XSWvehr_4DS5HwhpdO0ZiDi51NnaGwuXr6Mu0mS_moXnEhoCZekQAvD_BwE
No. of Tenements / Units in Project |  | Flats - 432 Offices - 47 |  |  | Exposure Limit (Proposed) | 64 |  | 64.8
Approved No. of Floor |  | Wing A to G = Gr + P1 to P5 + 6th to 21st Floor
Proposed No. of Floor |  | Wing A to G = Gr + P1 to P5 + 6th to 21st Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot | Other Plot | Other Plot / 12.20m Existing Road | Other Plot
|  | Physical on site |  | Devi Dayal Compound | Ashtavinayak Group Auto Consultant | Samriddhi Garden Road / Samriddhi Garden | Shreegan Apartment
Verification of survey No. (Title document) |  | CTS No. 403B/1, 403B, 403B/2, 403B/3 and 403B/4
Plot area mentioned in the sale deed (As per 7/12) |  | 11967.4 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 10734.51
Approach road |  | Yes, Approx 40ft
Connectivity |  | 1. 1.2km from Cosmos English High School & Junior College 2. 1.6km from NES High School 3. 1.0km from Saarthi Hospital 4. 1.3Km from Dr. Meena's Multi Speciality Hospital Bhandup 5. 1.3km from Neptune Magnet Mall 6. 1.1km from Mallu Mini Super Market 7. 1.3km from Shree Pimpleshwar Mahadev Mandir 8. 1.8km from Shree Maruti Mandir 9. 0.4km from Ishwar Nagar or Bhandup (W) Bus stop 10. 0.8km from Bhandup Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 10734.51
|  | Permissible FSI |  |  |  | 1
|  | Permissible TDR/Paid FSI |  |  |  | 1.9699
|  | Total FSI availaible for the project |  |  |  | 2.9699
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 31880.9
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 31880.9
Building plan approvals - Approval No : |  | P-18427/2023/(403B And Other)/S Ward/KANJURW/337/3/Amend |  |  |  | Date | 2025-01-15
Building height / No. of Floors |  | Wing A to G = St + 5P + 6th to 21st Floor (Height = 69.95m) | [5 empty] | Excl. OHT
Construction/Building Permission Valid Upto |  | P-18427/2023/(403B And Other)/S Ward/KANJUR-W/FCC/1/Amend |  |  |  | Date | 2025-08-26
[6 empty] | Valid Upto Date | 2026-07-04
Full C.C. is re-endorsed for Wings D, E, F & G including top podium; Further CC is granted for Ground to 4th commercial upper floors below Wings A,B & C; up to 16th residential floors for Wings-A & B & up to 17th residential floors for Wing-C (C.C. of FSI benefit of Amenity open space and BUA of Temporary structure is restricted) as per amended approved plans dated 15.01.2025, subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
NA / Land conversion |  | Name of the authority : |  | -
|  | Reference No : |  | - |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | - |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: |  | P-18427/2023/(403B And Other)/S Ward/ KANJUR-W-CFO/1/New. Wing A to G = St + 1st to 5th Podium + 6th to 21st Floor (Height = 69.95 Mtrs) |  |  |  | Date | 2023-11-07
Environmental Clearance Certificate (EC) No Valid Up for: |  | IA/MH/INFRA2/461068/2024 |  |  |  | Date | 2024-07-18
CTS no 403/B, 403/B/1, 403B/2, 403B/3 and 403/B/4 Total Plot Area = 11,967.40 sq. m
Airport Noc No Valid Up for: |  | SNCR/WEST/B/021924/918016 |  |  |  | Date | 2024-04-02
[6 empty] | Valid upto Dated | 2032-03-31
|  | Site Elevation (AMSL) = 16.9M Permissible Top Elevation (AMSL) = 166.9M | [5 empty] | 150
CONSTRUCTION PROGRESS
Baseline start date |  | 2024-08-06 |  | Baseline finish date |  | 2028-12-31 |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Construction Details:
Wing A = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [5 empty] | Excavation in process | 10.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21
Excavation |  | 0% |  | 21 | 100% | 15.45% |  | Footing in Process | 5.25
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5 | Visi identified Wing A to C On site visit dtd. 22/09/2025
RCC (Including podiums) |  | 40% |  | 3 | 13.64% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing B = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [5 empty] | Excavation in process | 10.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21
Excavation |  | 0% |  | 21 | 100% | 15.45% |  | Footing in Process | 5.25
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 3 | 13.64% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing C = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | Excavation in process | 10.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21
Excavation |  | 0% |  | 21 | 100% | 11.82% |  | Footing in Process | 5.25
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 1 | 4.545% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing D = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25 | Internal Visit Not Allowed Data referred from Youtube Construction Update
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed | [5 empty] | Excavation in process | 10.5 | https://www.youtube.com/shorts/EjPFy_uFvSs
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21
Excavation |  | 0% |  | 21 | 100% | 22.73% |  | Footing in Process | 5.25
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 7 | 31.82% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing E = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed | [5 empty] | Excavation in process | 10.5 | Internal Visit Not Allowed Data referred from Youtube Construction Update
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21 | https://www.youtube.com/shorts/EjPFy_uFvSs
Excavation |  | 0% |  | 21 | 100% | 20.91% |  | Footing in Process | 5.25
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 6 | 27.27% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing F = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed | [5 empty] | Excavation in process | 10.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21 | Internal Visit Not Allowed Data referred from Youtube Construction Update
Excavation |  | 0% |  | 21 | 100% | 22.73% |  | Footing in Process | 5.25 | https://www.youtube.com/shorts/EjPFy_uFvSs
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 7 | 31.82% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed
Possession |  | 5% |  | 0 | 0%
Wing G = Gr + P1 to P5 + 6th to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 21 | Piling Work in process | 5.25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed | [5 empty] | Excavation in process | 10.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 21 | Internal Visit Not Allowed Data referred from Youtube Construction Update
Excavation |  | 0% |  | 21 | 100% | 24.55% |  | Footing in Process | 5.25 | https://www.youtube.com/shorts/EjPFy_uFvSs
Plinth |  | 10% |  | 21 | 100% |  |  | Footing Completed | 10.5
RCC (Including podiums) |  | 40% |  | 8 | 36.36% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 0 | 0% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 15.75
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details : (Office)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A, B & C |  | 47 |  | 19623.4178 |  | 30416.2977
Total |  | 47 |  | 19623.4178 |  | 30416.2977
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 62 |  | 36567.6761 |  | 54851.5141
Wing B |  | 62 |  | 34359.5491 |  | 51539.3237
Wing C |  | 77 |  | 59303.9351 |  | 88955.9026
Wing D |  | 30 |  | 31881.8916 |  | 47822.8374
Wing E |  | 77 |  | 58612.8863 |  | 87919.3294
Wing F |  | 62 |  | 34759.7546 |  | 52139.632
Wing G |  | 62 |  | 36556.4815 |  | 54834.7223
Total |  | 432 |  | 292042.1743 |  | 438063.2615
Grand Total |  | 479 |  | 311665.5922 |  | 468479.5591
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
55%
Wing A, B & C
Commercial Wing 1 + 2
Ground Floor For Entrance Lobby, Commercial & Parking
1 |  | Office | 518.8248 | 0 | 518.8248 | 0 | 804.1784
2 |  | Office | 590.836 | 0 | 590.836 | 0 | 915.7957
3 |  | Office | 427.9766 | 0 | 427.9766 | 0 | 663.3638
4 |  | Office | 583.0859 | 0 | 583.0859 | 0 | 903.7831
5 |  | Office | 674.9028 | 0 | 674.9028 | 0 | 1046.0993
6 |  | Office Duplex (With 1st Floor) | 1015.691 | 0 | 1015.691 | 0 | 1574.3211
1st Podium Floor For Commercial
Office Duplex (With Ground Floor)
1 |  | Office | 213.6654 | 0 | 213.6654 | 0 | 331.1814
2 |  | Office | 262.534 | 0 | 262.534 | 0 | 406.9276
3 |  | Office | 210.6515 | 0 | 210.6515 | 0 | 326.5098
4 |  | Office | 471.0326 | 0 | 471.0326 | 0 | 730.1006
5 |  | Office | 489.3314 | 0 | 489.3314 | 0 | 758.4637
6 |  | Office | 411.9383 | 0 | 411.9383 | 0 | 638.5043
7 |  | Office | 302.0378 | 0 | 302.0378 | 0 | 468.1587
8 |  | Office | 465.9736 | 0 | 465.9736 | 0 | 722.259
2nd Podium Floor
1 |  | Office | 585.6692 | 0 | 585.6692 | 0 | 907.7873
2 |  | Office | 413.6605 | 0 | 413.6605 | 0 | 641.1738
3 |  | Office | 213.6654 | 0 | 213.6654 | 0 | 331.1814
4 |  | Office | 262.534 | 0 | 262.534 | 0 | 406.9276
5 |  | Office | 210.6515 | 0 | 210.6515 | 0 | 326.5098
6 |  | Office | 471.0326 | 0 | 471.0326 | 0 | 730.1006
7 |  | Office | 489.3314 | 0 | 489.3314 | 0 | 758.4637
8 |  | Office | 411.9383 | 0 | 411.9383 | 0 | 638.5043
9 |  | Office | 302.0378 | 0 | 302.0378 | 0 | 468.1587
10 |  | Office | 308.0657 | 0 | 308.0657 | 0 | 477.5018
11 |  | Office | 659.7256 | 0 | 659.7256 | 0 | 1022.5746
3rd & 4th Podium Floor
1 |  | Office | 585.6692 | 0 | 585.6692 | 0 | 907.7873
2 |  | Office | 413.6605 | 0 | 413.6605 | 0 | 641.1738
3 |  | Office | 213.6654 | 0 | 213.6654 | 0 | 331.1814
4 |  | Office | 262.534 | 0 | 262.534 | 0 | 406.9276
5 |  | Office | 210.6515 | 0 | 210.6515 | 0 | 326.5098
6 |  | Office | 471.0326 | 0 | 471.0326 | 0 | 730.1006
7 |  | Office | 489.3314 | 0 | 489.3314 | 0 | 758.4637
8 |  | Office | 411.9383 | 0 | 411.9383 | 0 | 638.5043
9 |  | Office | 302.0378 | 0 | 302.0378 | 0 | 468.1587
10 |  | Office | 308.0657 | 0 | 308.0657 | 0 | 477.5018
11 |  | Office | 659.7256 | 0 | 659.7256 | 0 | 1022.5746
12 |  | Shop |  |  | 0 | 0 | 0
5th Floor (Service Floor)
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Wing A
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenity & Society Office | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 2BHK | 523.4533 | 0 | 523.4533 | 0 | 785.18
2 |  | 2BHK | 625.9266 | 0 | 625.9266 | 0 | 938.8899
3 |  | 2BHK | 627.2183 | 0 | 627.2183 | 0 | 940.8274
4 |  | 2BHK | 587.2838 | 0 | 587.2838 | 0 | 880.9258
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 2BHK | 523.4533 | 0 | 523.4533 | 0 | 785.18
2 |  | 2BHK | 625.9266 | 0 | 625.9266 | 0 | 938.8899
3 |  | Refuge Area
4 |  | 2BHK | 587.2838 | 0 | 587.2838 | 0 | 880.9258
Wing B
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenity & Society Office | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 2BHK | 524.2068 | 0 | 524.2068 | 0 | 786.3102
2 |  | 2BHK | 525.3908 | 0 | 525.3908 | 0 | 788.0863
3 |  | 2BHK | 585.131 | 0 | 585.131 | 0 | 877.6966
4 |  | 2BHK | 585.8845 | 0 | 585.8845 | 0 | 878.8268
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 2BHK | 524.2068 | 0 | 524.2068 | 0 | 786.3102
2 |  | 2BHK | 525.3908 | 0 | 525.3908 | 0 | 788.0863
3 |  | Refuge Area
4 |  | 2BHK | 585.8845 | 0 | 585.8845 | 0 | 878.8268
Wing C
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenities | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
2 |  | 2BHK | 679.2084 | 0 | 679.2084 | 0 | 1018.8126
3 |  | 2BHK | 681.7918 | 51.129 | 732.9208 | 0 | 1099.3811
4 |  | 2BHK | 726.8929 | 0 | 726.8929 | 0 | 1090.3394
5 |  | 3BHK | 864.7798 | 48.3304 | 913.1101 | 0 | 1369.6652
7th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
2 |  | 2BHK | 679.2084 | 0 | 679.2084 | 0 | 1018.8126
3 |  | 2BHK | 681.7918 | 51.129 | 732.9208 | 0 | 1099.3811
4 |  | 2BHK | 726.8929 | 0 | 726.8929 | 0 | 1090.3394
5 |  | Refuge Area
14th Floor (Part Refuge Area & Society Office) | [7 empty] | 1
1 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
2 |  | 2BHK | 679.2084 | 0 | 679.2084 | 0 | 1018.8126
3 |  | Refuge Area
4
- |  | Society Office
5 |  | 3BHK | 864.7798 | 48.3304 | 913.1101 | 0 | 1369.6652
Wing D
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenity | [7 empty] | 1
6th Floor For Void | [7 empty] | 1
8th, 10th, 12th, 14th, 16th, 18th, 20th & 21st Floor | [7 empty] | 8
1 |  | 3BHK | 1014.1841 | 47.7922 | 1061.9762 | 0 | 1592.9644
2 |  | 3BHK | 1015.691 | 47.7922 | 1063.4832 | 0 | 1595.2248
7th, 9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge Area at Midlanding of Staircase) | [7 empty] | 7
1 |  | 3BHK | 1014.1841 | 47.7922 | 1061.9762 | 0 | 1592.9644
2 |  | 3BHK | 1015.691 | 47.7922 | 1063.4832 | 0 | 1595.2248
Wing E
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenity & Society Office (Wing D & Wing E) | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 3BHK | 863.4881 | 48.3304 | 911.8184 | 0 | 1367.7277
2 |  | 2BHK | 676.8403 | 0 | 676.8403 | 0 | 1015.2605
3 |  | 2BHK | 679.639 | 0 | 679.639 | 0 | 1019.4584
4 |  | 2BHK | 682.8682 | 51.2366 | 734.1048 | 0 | 1101.1572
5 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
7th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Refuge Area
2 |  | 2BHK | 676.8403 | 0 | 676.8403 | 0 | 1015.2605
3 |  | 2BHK | 679.639 | 0 | 679.639 | 0 | 1019.4584
4 |  | 2BHK | 682.8682 | 51.2366 | 734.1048 | 0 | 1101.1572
5 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
14th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | 3BHK | 863.4881 | 48.3304 | 911.8184 | 0 | 1367.7277
2 |  | Refuge Area
3
4 |  | 2BHK | 682.8682 | 51.2366 | 734.1048 | 0 | 1101.1572
5 |  | 3BHK | 802.6715 | 0 | 802.6715 | 0 | 1204.0072
Wing F
Basement Floor For Plant Room
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 1
2nd & 3rd Podium Floor For Parking | [7 empty] | 2
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 1
5th Podium Floor For Amenity & Society Office | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 2BHK | 609.673 | 0 | 609.673 | 0 | 914.5094
2 |  | 2BHK | 586.5304 | 0 | 586.5304 | 0 | 879.7955
3 |  | 2BHK | 525.3908 | 0 | 525.3908 | 0 | 788.0863
4 |  | 2BHK | 524.2068 | 0 | 524.2068 | 0 | 786.3102 | 17041.6205
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 2BHK | 609.673 | 0 | 609.673 | 0 | 914.5094
2 |  | Refuge Area
3 |  | 2BHK | 525.3908 | 0 | 525.3908 | 0 | 788.0863
4 |  | 2BHK | 524.2068 | 0 | 524.2068 | 0 | 786.3102
Wing G
Ground Floor For Entrance Lobby (Double Heighted), Meter Room & Parking
1st Podium Floor For Entrance Lobby Below | [7 empty] | 1
2nd Podium Floor For Fitness Center/Badminton Court & Parking | [7 empty] | 1
3rd & 4th Podium Floor For Parking | [7 empty] | 2
5th Podium Floor For Amenity & Society Office | [7 empty] | 1
6th, 8th to 13th, 15th to 21st Floor For Residential | [7 empty] | 14
1 |  | 2BHK | 587.2838 | 0 | 587.2838 | 0 | 880.9258
2 |  | 2BHK | 625.9266 | 0 | 625.9266 | 0 | 938.8899
3 |  | 2BHK | 625.9266 | 0 | 625.9266 | 0 | 938.8899
4 |  | 2BHK | 523.8839 | 0 | 523.8839 | 0 | 785.8258
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 2BHK | 587.2838 | 0 | 587.2838 | 0 | 880.9258
2 |  | Refuge Area
3 |  | 2BHK | 625.9266 | 0 | 625.9266 | 0 | 938.8899
4 |  | 2BHK | 523.8839 | 0 | 523.8839 | 0 | 785.8258
Ground Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
1st Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 18000 |  |  | 16000 to 18000 change rate on 26/09/2025
Recommended of Parking ( If Available) |  |  |  |  | 7,50,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. (Internal visit was not allowed)
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit. | [6 empty] | On Carpet
4 | We considered Carpet area as per Approved Plan. | [6 empty] | 25572.5191 | 2BHK
5 | We considered Gross carpet area = Net carpet + Balcony Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50% |  |  | 25625 | 3BHK
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding Stamp duty & legal charges)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Siddhesh - 8652734528
11 | As per Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) = 13213 | [6 empty] | 13213.4894
12 | As per the approved plans dated 15/01/2025 in Wing A, B & C are partially used for Commercial area (i.e Offices) from Gr + 1st to 4th Podium Floor And is mentioned in approved plans as Commercial Wing 1 & 2. | [9 empty] | https://www.99acres.com/arkade-rare-bhandup-west-central-mumbai-suburbs-npxid-r432448
13 | We have referred approved plans, CC & Airport Noc from MCGM site.
Photographs Of Property : |  | Arkade Rare
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Pravin Mestri |  | Authorized Signatory Name & Seal of the agency
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C62: RERA Start date
Note on H164: if multiple buildings are in project and are connected internally
Note on C166: AAC Block or Brick
Note on H168: If present on slopy area
Wing A
Wing B
Wing C
Wing D
Wing E
Wing F
Wing G
Arkade Rare (Wing A to G)
A
B
C
D
E
F
G
Wing A
Wing B
Wing C
Wing C
Wing B
Wing D

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3