## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 25/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-25
Name of the builder group |  |  |  |  | M/s. Shantee Homes Realty LLP
Name of the builder company |  |  |  |  | M/s. Shantee Homes Realty LLP
Name of the Project |  |  |  |  | Spring Field (Type A, B1 B2, C & D)
Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Ashwin-80072 54890 & Mr. Ashif Shaikh - 8983302092
Site Person - Contact Details (Name & Contact No.) |  |  |  |  | Mr. Gharat : 7499509179
RERA No. |  |  |  |  | P99000020393 Cluster 1 - Type A - (RH 1 to 31) Cluster 2 - Type B1 - (RH 1 to 36) Cluster 3 - Type B2 - (RH 1 to 15) Cluster No.12 & 13 - Type D - (RH-116 to 135) Cluster No.5 to 9 - Type C1 - (RH-48 to 102) Cluster No.4 - Type C2 - (RH 32 to 42) Cluster No.10 - Type C3 - (RH 103 to 108) Cluster No.11 - Type C4 - (RH 109 to 115)
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Spring Field (Type A, B1, B2, C & D), Survey No. 116, at village Kaman, Tal - Vasai, Dist. Palghar - 401 208
S. No | 116 |  |  | Plot No. | NA | Locality | Kaman
Road | Chinchoti Anjur Phata Road |  |  |  | District | Palghar
City | Vasai (East) |  |  |  | Pin Code | 401 208
Near by Landmark |  | Shailendra College Vasai Campus |  |  | Distance from city centre: |  | About 5.2Km Distance From Kaman Road Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Internal Road |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 19.3654 |  | Longitude |  | 72.9177
Location Link |  | https://goo.gl/maps/GoijjjJgDTZvrV1k6
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 27720
Permissible FSI |  |  |  |  | 0.3
Permissible TDR/Paid FSI |  |  |  |  | Not provided
Total FSI availaible for the project |  |  |  |  | Not provided
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 6893.06
Total number of Buildings |  |  |  |  | 13 Clusters (177 Rowhouses)
Approval Detail : Plan approval
Layout Approval No |  | VVCMC/AMEND/BP/VP-5915/89/2019-20 |  |  |  | Dated | 18/09/2019.
Building plan approval No |  | VVCMC/AMEND/BP/VP-5915/89/2019-20 |  |  |  | Dated | 18/09/2019.
C.certificate No |  | VVCMC/TP/CC/VP-5915/339/2018-19 |  |  |  | Dated | 18/02/2019. | Expiry date: One year from date of issue
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 18/02/2019. |  | Expected Completion |  | 31/01/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 6893.06 |  | Approved no of units |  |  | NA
Approved no of Floors |  | Cluster 1 - Type A - (RH 1 to 31) – Stilt + 1st to 2nd floor Cluster 2 - Type B1 - (RH 1 to 36) – Stilt + 1st floor Cluster 3 - Type B2 - (RH 1 to 15) – Stilt + 1st floor Cluster No.5 to 9 - Type C1 - (RH-43 to 102) – Ground floor Cluster No.4 - Type C2 - (RH 32 to 42) – Ground floor Cluster No.10 - Type C3 - (RH 103 to 108) – Ground floor Cluster No.11 - Type C4 - (RH 109 to 115) – Ground floor Cluster No.12 & 13 - Type D - (RH-116 to 135) – Stilt + 1st to 2nd floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Cluster 1 - Type A - (RH 1 to 31) = Stilt + 1st to 2nd floor Cluster No.6 - Type C1 - (RH 55 to 66) = Ground floor Cluster No.7 - Type C1 - (RH 67 to 78) = Ground floor Cluster No.12 - Type D - (RH-116 to 131) = Stilt + 2nd floor Cluster No.13 - Type D - (RH-132 to 135) = Stilt + 2nd floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 2
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% |  | 100% |  | 100% |  | Excavation in process | 1
Plinth |  | 2 | 100% | [5 empty] | Excavation Completed | 2
RCC (Including podiums) |  | 3 | 100% | [5 empty] | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 100% | [5 empty] | Plinth in process | 1.5
Possession |  | 2 | 100% | [5 empty] | Plinth completed | 2
Construction details: |  | Cluster 2 - Type B1 - (RH 1 to 36) |  |  |  | Stilt + 1st floor |  |  | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 1
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 10% |  | 45% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster 3 - Type B2 - (RH 1 to 15) |  |  |  | Stilt + 1st floor |  |  | Excavation work Completed. Footing work Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 1
Stage of construction: |  | Excavation work Completed. Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 5% |  | 32.5% |  | Excavation in process | 0.5
Plinth |  | 0.5 | 50% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster No.4 - Type C2 - (RH 32 to 42) Cluster No.5 - Type C1 - (RH 43 to 54) |  |  |  | Ground floor |  |  | Work not yet Started.
Basement |  | 0 |  | Ground Floor |  |  |  | 1
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 0.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster No.8 - Type C1 - (RH 79 to 90) = Ground floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
Basement |  | 0 |  | Ground Floor |  |  |  | 1
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 75% |  | 90% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 1 | 100% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 1 | 100% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 1 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster No.9 - Type C1 - (RH 91 to 102) |  |  |  | Ground floor |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 0.5 Floor Completed
Basement |  | 0 |  | Ground Floor |  |  |  | 1
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 0.5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 61.25% |  | 82.5% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 1 | 100% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 1 | 100% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0.5 | 50% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster No.10 - Type C3 - (RH 103 to 108) |  |  |  | Ground floor |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed
Basement |  | 0 |  | Ground Floor |  |  |  | 1
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 57.5% |  | 80% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 1 | 100% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 1 | 100% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Construction details: |  | Cluster No.11 - Type C4 - (RH 109 to 115) = Ground floor | [6 empty] | Excavation work Completed. Footing work Completed
Basement |  | 0 |  | Ground Floor |  |  |  | 1
Stage of construction: |  | Excavation work Completed. Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% |  | 5% |  | 32.5% |  | Excavation in process | 0.5
Plinth |  | 0.5 | 50% | [5 empty] | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 1
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Description |  |  | Row House |  | Cottage | Studio | Signature
Rate of the flat Per Sq. Ft. ( on Carpet area) |  |  | 8500 |  | 6500 | 5000 | 10500 |  | 8800 to 10500 by trupti on 23/07/2024 (Verbal)
Development Charges |  |  | 2,00,000/- |  | 1,00,000/- | 1,00,000/- | 2,00,000/- |  | Row House Rate 8500 by Trupti from index2 on 30/06/2025
Maintenance Charges |  |  | 40,000/- |  | 30,000/- | 20,000/- | 50,000/-
Water & Electrical Charges |  |  | 1,00,000/- |  | 50,000/- | 50,000/- | 1,00,000/-
Other Charges |  |  | 40,000/- |  | 30,000/- | 30,000/- | 50,000/-
Society Formation Charges |  |  | 80,000/- |  | 50,000/- | 50,000/- | 1,00,000/-
Parking |  |  | 1,00,000/- |  | 70,000/- | 50,000/- | 1,50,000/-
Parking |  |  | 1,00,000/- |  | 70,000/- | 50,000/- | 1,50,000/-
Distressed valuation of the Property |  |  | 6800 |  | 5200 | 4000 | 8400 |  |  |  |  | 1000000
Remarks:
1. Cluster No.12 - Type D - (RH-116 to 131) Cluster No.13 - Type D - (RH-132 to 135) Cluster No.6 - Type C1 - (RH 55 to 66) Cluster No.7 - Type C1 - (RH 67 to 78) Cluster No.1- Type A - (RH 11 to 31) |  |  |  |  | All work Completed. Please provide OC. |  |  |  | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
Cluster No.8 - Type C1 - (RH 79 to 90) Cluster No.9 - Type C1 - (RH 91 to 102) Cluster No.10 - Type C3 - (RH 103 to 108) |  |  |  |  | Construction work is in process at the time of visit.
Cluster 2 - Type B1 - (RH 1 to 36) Cluster 3 - Type B2 - (RH 1 to 15) Cluster No.11 - Type C4 - (RH 109 to 115) |  |  |  |  | Construction work is same from visit (16/12/2020).
Cluster No.6 - Type C1 - (RH 55 to 66) Cluster No.7 - Type C1 - (RH 67 to 78) |  |  |  |  | Construction work is same from visit (09/06/2022).
Cluster No.4 - Type C2 - (RH 32 to 42) Cluster No.5 - Type C1 - (RH 43 to 54) |  |  |  |  | Work not yet started. | [5 empty] | Cluster No.1- Type A - (RH 11 to 31)
2. We have given rate verify by Market Inquire. 3. We have considered Other charges from cost sheet. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 5. On site we meet Mr.Ashwin-80072 54890 6. Since the project has received first CC on 18/02/2019, but still project is under construction. 7. Recommended Rates/Other Charges of the Property have been revised on 23/07/2024 & 30/06/2025. | [8 empty] | The construction work on the other clusters has been hold because all workers are working on Cluster No. 1 (Type A) (RH 11 to 31), Cluster No. 12 (Type D) (RH 116 to 131), & Cluster No. 13 (Type D) (RH 132 to 135). |  | Cluster No.6 - Type C1 - (RH 55 to 66)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Spring Field (Type A, B1 B2, C & D)
Google Map :
Cluster 1
Cluster 6
Cluster 12
Cluster 7
Cluster 13

## Note
20/10/2021. | Asmi | Rakesh