## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 24/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-23 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | SVB Lifespaces LLP | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | SVB Lifespaces LLP | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Amansara Earthstar | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Omkar 9325821506/ Mr. Aditya 9145023840
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Patil : 9145459833
Name / No of the Building |  |  |  | 91 Plots
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000054002 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Amansara Earthstar, New Gut No.315, 353/A, 353/B, 325, 344, 351, 352, Old Gut No. 490, 528/A, 528/B, 500, 519, 526, 527, near Imagica Theme Park, Gorthan Road, Khanav, Ganeshnagar, Khopoli West, Khalapur, Raigad - 410203. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
New Gut No |  | 315, 353/A, 353/B, 325, 344, 351, 352, Old Gut No. 490, 528/A, 528/B, 500, 519, 526, 527 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Khanav | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Gorthan Road |  | Locality/Village |  | Ganeshnagar | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Khopoli West |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Khalapur |  | Pin Code |  | 410203 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Imagica Theme Park |  | Distance from city centre: |  | 12.40KM from Khopoli Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | FALSE
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Gut No. 345 & 350 |  |  | Open Plot
West | NA | Gut No. 318 & 324 |  |  | Open Plot/Village
North | NA | Existing Road |  |  | Gorthan Road
South | NA | Gut No. 361 & 367 |  |  | Open Plot/Village
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.756485,73.279761
Location Link |  | https://maps.app.goo.gl/nzKKhVcU8K1Rxsta8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 41683.1
Pro-Rata FSI |  |  |  | 1.46
Permissible TDR/Paid FSI |  |  |  | -1.46
Total FSI availaible for the project |  |  |  | 0
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 0
Total number of Buildings |  |  |  | 91 Plots
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Raigad | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | SSNR-RA/Binsheti Mojni/Mauje Ganeshnagar/Tal. Khalapur/S. No.315/2 & Other/Mojnivaril Shifaras/662 |  |  | Dated | 2023-04-11 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | SSNR-RA/Binsheti Mojni/Mauje Ganeshnagar/Tal. Khalapur/S. No.315/2 & Other/Mojnivaril Shifaras/662 |  |  | Dated | 2023-04-11 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
NA Order No Valid Up to: |  | MS/L.N.A./A-1(B)/Token No. 16635/S.R.151/2022 315/2, 325, 344/2, 351, 352, 353/A, 353/B/1 |  |  | Dated | 2023-10-23 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | 0 |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | NA |  |  |  |  | 0
Approved no of units |  |  | Plots = 91
Approved no of Floors |  |  | NA
Proposed no of Floors |  |  | Building No.1 (A Wing) = 1B + G + 1st to 20th Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 06/11/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Indoor Games, Library, Fitness Centre, Banquet, SPA Facility, Pet Area, Kids Play Area, Gaming Zone, Restaurant/Café, Artroom, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc |  |  |  |  | https://amansaraearthstar.com/
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (A Wing) = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Plot Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Land Per Sq. Ft. |  |  |  |  | 5000 | [11 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 600000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 4000 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Plot Area |  | Total Carpet Area
Plots |  | 91 |  | 448041.8124 |  | -
Total
Grand Total |  | 0 |  | 0 |  | 0
Building details Floor Wise
Details of Plots
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Plot No. (Approved Plan) | Description | Plot Area (In Sq.M.) | Plot Area (In Sq.Ft.) | Gross Carpet area | Terrace Area | Demarkation/Plot marking date as per site inspection |  |  | BuiltUp Area
1 | Plot | 834.5 | 8982.558 | 0 | - | 2024-09-20 |  | #VALUE! | 1218.37
2 | Plot | 818 | 8804.952 | 0 | - | 2024-09-20 |  |  | 1194.28
3 | Plot | 324.6 | 3493.9944 | 0 | - | 2024-09-20 |  |  | 473.916
4 | Plot | 352.5 | 3794.31 | 0 | - | 2024-09-20 |  |  | 514.65
5 | Plot | 352.5 | 3794.31 | 0 | - | 2024-09-20 |  |  | 514.65
6 | Plot | 350.5 | 3772.782 | 0 | - | 2024-09-20 |  |  | 511.73
7 | Plot | 350.5 | 3772.782 | 0 | - | 2024-09-20 |  |  | 511.73
8 | Plot | 352.5 | 3794.31 | 0 | - | 2024-09-20 |  |  | 514.65
9 | Plot | 352.5 | 3794.31 | 0 | - | 2024-09-20 |  |  | 514.65
10 | Plot | 352.5 | 3794.31 | 0 | - | 2024-09-20 |  |  | 514.65
11 | Plot | 420.3 | 4524.1092 | 0 | - | 2024-09-20 |  |  | 613.638
12 | Plot | 568 | 6113.952 | 0 | - | 2024-09-20 |  |  | 829.28
13 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
14 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
15 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
16 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
17 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
18 | Plot | 423.5 | 4558.554 | 0 | - | 2024-09-20 |  |  | 618.31
19 | Plot | 410 | 4413.24 | 0 | - | 2024-09-20 |  |  | 598.6
20 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
21 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
22 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
23 | Plot | 427.5 | 4601.61 | 0 | - | 2024-09-20 |  |  | 624.15
24 | Plot | 907.2 | 9765.1008 | 0 | - | 2024-09-20 |  |  | 1324.512
25 | Plot | 769.8 | 8286.1272 | 0 | - | 2024-09-20 |  |  | 1123.908
26 | Plot | 729.6 | 7853.4144 | 0 | - | 2024-09-20 |  |  | 1065.216
27 | Plot | 807.7 | 8694.0828 | 0 | - | 2024-09-20 |  |  | 1179.242
28 | Plot | 951.9 | 10246.2516 | 0 | - | 2024-09-20 |  |  | 1389.774
29 | Plot | 1082.2 | 11648.8008 | 0 | - | 2024-12-28 |  |  | 1580.012
30 | Plot | 996.9 | 10730.6316 | 0 | - | 2024-12-28 |  |  | 1455.474
31 | Plot | 1024.7 | 11029.8708 | 0 | - | 2024-12-28 |  |  | 1496.062
32 | Plot | 621.7 | 6691.9788 | 0 | - | 2024-12-28 |  |  | 907.682
33 | Plot | 570 | 6135.48 | 0 | - | 2024-12-28 |  |  | 832.2
34 | Plot | 558.7 | 6013.8468 | 0 | - | 2024-12-28 |  |  | 815.702
35 | Plot | 1100.2 | 11842.5528 | 0 | - | 2024-12-28 |  |  | 1606.292
36 | Plot | 736.1 | 7923.3804 | 0 | - | 2024-12-28 |  |  | 1074.706
37 | Plot | 700.8 | 7543.4112 | 0 | - | 2024-12-28 |  |  | 1023.168
38 | Plot | 305.9 | 3292.7076 | 0 | - | 2024-12-28 |  |  | 446.614
39 | Plot | 596.9 | 6425.0316 | 0 | - | 2024-12-28 |  |  | 871.474
40 | Plot | 435 | 4682.34 | 0 | - | 2024-12-28 |  |  | 635.1
41 | Plot | 433 | 4660.812 | 0 | - | 2024-12-28 |  |  | 632.18
42 | Plot | 433 | 4660.812 | 0 | - | 2024-12-28 |  |  | 632.18
43 | Plot | 569 | 6124.716 | 0 | - | 2024-12-28 |  |  | 830.74
44 | Plot | 520.2 | 5599.4328 | 0 | - | 2024-12-28 |  |  | 759.492
45 | Plot | 550.8 | 5928.8112 | 0 | - | 2024-12-28 |  |  | 804.168
46 | Plot | 545.1 | 5867.4564 | 0 | - | 2024-12-28 |  |  | 795.846
47 | Plot | 433 | 4660.812 | 0 | - | 2024-12-28 |  |  | 632.18
48 | Plot | 433 | 4660.812 | 0 | - | 2024-12-28 |  |  | 632.18
49 | Plot | 435 | 4682.34 | 0 | - | 2024-12-28 |  |  | 635.1
50 | Plot | 435 | 4682.34 | 0 | - | 2024-12-28 |  |  | 635.1
51 | Plot | 715 | 7696.26 | 0 | - | 2024-12-28 |  |  | 1043.9
52 | Plot | 337.6 | 3633.9264 | 0 | - | 2025-09-23 |  |  | 492.896
53 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
54 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
55 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
56 | Plot | 294.6 | 3171.0744 | 0 | - | 2025-09-23 |  |  | 430.116
57 | Plot | 311.5 | 3352.986 | 0 | - | 2025-09-23 |  |  | 454.79
58 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
59 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
60 | Plot | 392 | 4219.488 | 0 | - | 2024-09-20 |  |  | 572.32
61 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
62 | Plot | 311.5 | 3352.986 | 0 | - | 2025-09-23 |  |  | 454.79
63 | Plot | 294.6 | 3171.0744 | 0 | - | 2025-09-23 |  |  | 430.116
64 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
65 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
66 | Plot | 296.6 | 3192.6024 | 0 | - | 2025-09-23 |  |  | 433.036
67 | Plot | 456 | 4908.384 | 0 | - | 2025-09-23 |  |  | 665.76
68 | Plot | 506.3 | 5449.8132 | 0 | - | 2025-09-23 |  |  | 739.198
69 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
70 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
71 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
72 | Plot | 292.5 | 3148.47 | 0 | - | 2025-09-23 |  |  | 427.05
73 | Plot | 306.9 | 3303.4716 | 0 | - | 2025-09-23 |  |  | 448.074
74 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
75 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
76 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
77 | Plot | 313.5 | 3374.514 | 0 | - | 2025-09-23 |  |  | 457.71
78 | Plot | 294.4 | 3168.9216 | 0 | - | 2025-09-23 |  |  | 429.824
79 | Plot | 304.8 | 3280.8672 | 0 | - | 2025-09-23 |  |  | 445.008
80 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
81 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
82 | Plot | 300.5 | 3234.582 | 0 | - | 2025-09-23 |  |  | 438.73
83 | Plot | 454.3 | 4890.0852 | 0 | - | 2025-09-23 |  |  | 663.278
84 | Plot | 258.1 | 2778.1884 | 0 | - | - |  |  | 376.826 |  | 5363.2072
85 | Plot | 258.1 | 2778.1884 | 0 | - | - |  |  | 376.826
86 | Plot | 258.1 | 2778.1884 | 0 | - | - |  |  | 376.826
87 | Plot | 258.1 | 2778.1884 | 0 | - | - |  |  | 376.826
88 | Plot | 261.2 | 2811.5568 | 0 | - | - |  |  | 381.352
89 | Plot | 338.4 | 3642.5376 | 0 | - | - |  |  | 494.064
90 | Plot | 355.1 | 3822.2964 | 0 | - | - |  |  | 518.446
91 | Plot | 795.6 | 8563.8384 | 0 | - | 2024-09-20 |  |  | 1161.576
Remarks:
* | Demarcation work is in process.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Plot area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | We have refered approved C.C from RERA Site.
* | We considered Plot area as per Approved Plan.
* | Visit Date | Plot No. |  | Site Inspection
* | 2024-09-20 | 1 to 28, 60 & 91 |  | Demarkation/Plot marking has completed.
* | 2024-12-28 | 29 to 51 |  | Demarkation/Plot marking work is in process.
* | 2024-12-28 | 52 to 59, 61 to 90 |  | Work not yet started.
* | 2025-03-11 | 52 to 59, 61 to 90 |  | Plot Levelling work is in process.
* | 2025-06-18 | 52 to 59, 61 to 90 |  | Plot Levelling work is in process.
* | 2025-06-18 | 29 to 51 |  | Demarkation/Plot marking work is in process.
* | 2025-09-23 | 1 to 51 52 to 83 |  | Demarkation/Plot marking has completed
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Amansara Earthstar
Layout :
Google Map :
Formulas:
Ganeshnagar = [Ganeshnagar, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C50: kunal kadam: Layout no not mentioned in NA Order
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F122: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate