## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 21/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-20
Name of the builder group |  |  |  | Mantram Venture LLP
Name of the builder company |  |  |  | Mantram Venture LLP
Name of the Project |  |  |  | Mantram
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Bhimesh Mehta 9819538134
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Satyanarayan : 8828245068
Name / No of the Building |  |  |  | Tower A, B, C & Commercial Building,
Name / No of the Existing Building |  |  |  | NA | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area & Cost Sheet. | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052044 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Mantram, Gut No.118/2/A, near Shree Mahaganpati Ashtavinyak Mandir, National Highway 4, Thombare Vadi, Khanavale, Shedung, Panvel, Raigad - 410221. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Gut No |  | 118/2/A | [10 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Thombare Vadi | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | National Highway 4 |  | Locality/Village |  | Khanavale | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Shedung |  | District |  | Raigad | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410221 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Shree Mahaganpati Ashtavinyak Mandir |  | Distance from city centre: |  | 5.70KM from Somatne Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | NH-4 Pune Road |  |  | National Highway 4/wadwa Wise City
West | NA | Other Plot |  |  | Open Plot
North | NA | Survey No. 124 |  |  | Ganesh Mandir
South | NA | Survey No. 120 |  |  | Houses
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.941783,73.183002
Location Link |  | https://maps.app.goo.gl/LKEUUQSniQMsAi1cA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9284.723
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.6554
Total FSI availaible for the project |  |  |  | 2.7554
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 25582.713
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra State Road Development Corporation Limited (MSRDC) | [8 empty] | W
Layout Approval No |  | MSRDC/SPA/Khanavale/BP-440/ CC/2023/867 |  |  | Dated | 2023-05-22
Approved Floor plan No. |  | MSRDC/SPA/Khanavale/BP-440/ CC/2023/867 |  |  | Dated | 2023-05-22
Commencement-CC No Valid Up to: |  | MSRDC/SPA/Khanavale/BP-440/ CC/2023/867 |  |  | Dated | 2023-05-22
Builtup Area = 25582.713 Sq.M. Tower A = Gr + 1st to 21st Floor Tower B = Gr + 1st to 21st Floor Tower C = Gr + 1st to 21st Floor Commercial Wing = Gr + 1st to 2nd Floor
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/INFRA2/424965/2023 |  |  | Dated | 2023-09-27
Plot Area = 10500.00 Sqmt Built up Area = 45000.00 Sqmt Tower A, B & C = Gr + 5P + 1st to 20th Floor Commercial Wing = LG + UG + G + 1st to 2nd Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 25582.713
Approved no of units |  |  | Flats - 345, Shops - 29, Restaurant - 01
Approved no of Floors |  |  | Tower A, B & C = Gr + 1st to 5th Podium + 1st to 20th Floor Commercial Wing = LG + UG + 1st & 2nd Floor
Proposed no of Floors |  |  | Tower A, B & C = Gr + 1st to 5th Podium + 1st to 21st Floor
Commercial Wing = LG + UG + 1st & 2nd Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance & Landscape Garden, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower A = Gr + 1st to 5th Podium + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 0 | Ground | 1 | Podium | 5 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 14.44% |  | 48.33% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 3 | 11.11% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Tower B = Gr + 1st to 5th Podium + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 | Podium | 5 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 12.96% |  | 47.22% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 2 | 7.407% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Tower C = Gr + 1st to 5th Podium + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab Completed | , RCC upto 6 Slab
Basement | 0 | Ground | 1 | Podium | 5 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 18.89% |  | 51.67% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 6 | 22.22% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Commercial Wing = LG + UG + 1st & 2nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
Basement | 0 | Ground | 2 | Podium | 0 | Floors | 2 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 75% |  | 90% |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 4 | 100% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 2 | 100% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 2 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6100 |  |  | 5800 to 6100 | 2024-09-24 | smith
Recommended rate of the Shop (Ground Floor) Per Sq. Ft. |  |  |  |  | 10000
Recommended rate of the Shop (1st Floor) Per Sq. Ft. |  |  |  |  | 8000
Floor Rise Rate from Floor
Development Charges
Club Charges |  |  |  |  | 100000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Development & Society Formation Charges |  |  |  |  | 200000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 350000 |  |  | 2L to 3.5L on 09/10/2024 by smith verbal
Distressed valuation of the Property |  |  |  |  | 4880
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Commercial Building |  | 29 |  | 15934.4443 |  | 31868.869
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower A |  | 116 |  | 52145.3261 |  | 86855.448
Tower B |  | 116 |  | 56072.4962 |  | 93640.932
Tower C |  | 113 |  | 57225.5897 |  | 95566.73
Total |  | 345 |  | 165443.412 |  | 276063.11
Grand Total |  | 374 |  | 181377.8563 |  | 307931.979
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Builder Saleable Area :
45%
Commercial Building | [7 empty] | 10.764
Lower Ground Floor For Meter Room & Parking
Upper Ground Floor For Commercial & Entrance Lobby
1 |  | Shop | 62.6465 | 0 | 62.6465 | 0 | 125.293 | 5.8212 |  |  | 2
2 |  | Shop | 826.363 | 0 | 826.363 | 0 | 1652.726 | 70.2733 |  |  | 2
3 |  | Shop | 439.9785 | 0 | 439.9785 | 0 | 879.957 | 40.595 |  |  | 2
4 |  | Shop | 439.9785 | 0 | 439.9785 | 0 | 879.957 |  |  |  | 2
5 |  | Shop | 416.513 | 0 | 416.513 | 0 | 833.026 |  |  |  | 2
6 |  | Shop | 1071.0503 | 0 | 1071.0503 | 0 | 2142.101 | 100.3726 |  |  | 2
7 |  | Shop | 436.9323 | 0 | 436.9323 | 0 | 873.865 |  |  |  | 2
8 |  | Shop | 464.2406 | 0 | 464.2406 | 0 | 928.481 |  |  |  | 2
9 |  | Shop | 449.6015 | 0 | 449.6015 | 0 | 899.203 |  |  |  | 2
10 |  | Shop | 1233.0808 | 0 | 1233.0808 | 0 | 2466.14 |  |  |  | 2
11 |  | Shop | 555.9929 | 0 | 555.9929 | 0 | 1111.986 |  |  |  | 2
12 |  | Shop | 555.9929 | 0 | 555.9929 | 0 | 1111.986 |  |  |  | 2
13 |  | Shop | 555.9929 | 0 | 555.9929 | 0 | 1111.986 |  |  |  | 2
14 |  | Shop | 555.9929 | 0 | 555.9929 | 0 | 1111.986 |  |  |  | 2
15 |  | Shop | 456.4582 | 0 | 456.4582 | 0 | 912.916 |  |  |  | 2
1st Floor
1 |  | Shop | 858.9457 | 0 | 858.9457 | 0 | 1717.891 |  |  |  | 2
2 |  | Shop | 353.1991 | 0 | 353.1991 | 0 | 706.398 |  |  |  | 2
3 |  | Shop | 353.1991 | 0 | 353.1991 | 0 | 706.398 | 32.5325 |  |  | 2
4 |  | Shop | 334.3621 | 0 | 334.3621 | 0 | 668.724 |  |  |  | 2
5 |  | Shop | 968.986 | 0 | 968.986 | 0 | 1937.972 |  |  |  | 2
6 |  | Shop | 362.876 | 0 | 362.876 | 0 | 725.752 |  |  |  | 2
7 |  | Shop | 385.5557 | 0 | 385.5557 | 0 | 771.111 |  |  |  | 2
8 |  | Shop | 370.9167 | 0 | 370.9167 | 0 | 741.833 |  |  |  | 2
9 |  | Shop | 1135.6128 | 0 | 1135.6128 | 0 | 2271.226 |  |  |  | 2
10 |  | Shop | 473.8313 | 0 | 473.8313 | 0 | 947.663 |  |  |  | 2
11 |  | Shop | 473.8313 | 0 | 473.8313 | 0 | 947.663 |  |  |  | 2
12 |  | Shop | 473.8313 | 0 | 473.8313 | 0 | 947.663 |  |  |  | 2
13 |  | Shop | 414.6078 | 0 | 414.6078 | 0 | 829.216 |  |  |  | 2
14 |  | Shop | 453.8748 | 0 | 453.8748 | 0 | 907.75 |  |  |  | 2
2nd Floorn For Resturant
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Builder Saleable Area :
50%
Tower A | [7 empty] | 10.764
Ground Floor For Entrance Lobby, Drivers Room, Meter Room, Fire Control Room & Parking
1st to 4th Podium Floor For Parking
5th Podium Floor For Lobby & Part Terrace Area
1st, 5th, 7th, 9th, 11th, 15th, 17th & 19th Floor For Residential | [9 empty] | 5800
1 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 | 46.8125 |  | 5123343 | 883.335 | 1.67
2 |  | 1BHK | 374.8132 | 32.7979 | 407.6112 | 0 | 673.251 | 32.7125 |  | 3904855.8 | 673.251 | 1.6517
3 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.088 |  |  | 3683510.4 | 635.088 | 1.67
4 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.88 |  |  | 3688104 | 635.88 | 1.6721
5 |  | 1BHK | 388.4189 | 33.7451 | 422.1641 | 0 | 697.338 |  |  | 4044560.4 | 697.338 | 1.6518
6 |  | 2BHK | 536.3486 | 37.7547 | 574.1033 | 0 | 950.529 |  |  | 5513068.2 | 950.529 | 1.6557
2nd, 4th, 6th, 10th, 12th, 14th, 16th & 20th Floor | [9 empty] | 0
1 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  | 5513068.2 | 950.529 | 1.67
2 |  | 1BHK | 367.6229 | 0 | 367.6229 | 0 | 613.93 |  |  | 3560794 | 613.93 | 1.67
3 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  | 4032571.8 | 695.271 | 1.67
4 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  | 4032571.8 | 695.271 | 1.67
5 |  | 1BHK | 382.0467 | 0 | 382.0467 | 0 | 638.018 |  |  | 3700504.4 | 638.018 | 1.67
6 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  | 5123343 | 883.335 | 1.67
3rd & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  |  | 1.67
2 |  | 1BHK | 374.8132 | 32.7979 | 407.6112 | 0 | 673.251 |  |  |  | 1.6517
3 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.088 |  |  |  | 1.67
4 |  | Refuge Area
5 |  | 1BHK | 388.4189 | 33.7451 | 422.1641 | 0 | 697.338 |  |  |  | 1.6518
6 |  | 2BHK | 536.3486 | 37.7547 | 574.1033 | 0 | 950.529 |  |  |  | 1.6557
8th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  |  | 1.67
2 |  | 1BHK | 367.6229 | 0 | 367.6229 | 0 | 613.93 |  |  |  | 1.67
3 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  |  | 1.67
4 |  | Refuge Area
5 |  | 1BHK | 382.0467 | 0 | 382.0467 | 0 | 638.018 |  |  |  | 1.67
6 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  |  | 1.67
Tower B
Ground Floor For Entrance Lobby, Drivers Room, Meter Room, Fire Control Room & Parking
1st to 4th Podium Floor For Parking
5th Podium Floor For Lobby & Part Terrace Area
1st, 5th, 7th, 9th, 11th, 15th, 17th & 19th Floor For Residential
1 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  |  | 1.67
2 |  | 1BHK | 388.4189 | 29.1489 | 417.5679 | 0 | 697.338 |  |  |  | 1.67
3 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.088 |  |  |  | 1.67
4 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.088 |  |  |  | 1.67
5 |  | 2BHK | 576.8858 | 31.2156 | 608.1014 | 0 | 1015.529 | 50.2975 | 3.335 |  | 1.67
6 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 | 46.1825 |  |  | 1.67
2nd, 4th, 6th, 10th, 12th, 14th, 16th & 20th Floor
1 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  |  | 1.67
2 |  | 1BHK | 382.0467 | 0 | 382.0467 | 0 | 638.018 |  |  |  | 1.67
3 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  |  | 1.67
4 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  |  | 1.67
5 |  | 2BHK | 569.3725 | 0 | 569.3725 | 0 | 950.834 |  |  |  | 1.67
6 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  |  | 1.67
3rd & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  |  | 1.67
2 |  | 1BHK | 388.4189 | 29.1489 | 417.5679 | 0 | 697.338 |  |  |  | 1.67
3 |  | Refuge Area
4 |  | 1BHK | 380.2921 | 0 | 380.2921 | 0 | 635.088 |  |  |  | 1.67
5 |  | 2BHK | 576.8858 | 31.2156 | 608.1014 | 0 | 1015.529 |  |  |  | 1.67
6 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  |  | 1.67
8th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 528.943 | 0 | 528.943 | 0 | 883.335 |  |  |  | 1.67
2 |  | 1BHK | 382.0467 | 0 | 382.0467 | 0 | 638.018 |  |  |  | 1.67
3 |  | Refuge Area
4 |  | 1BHK | 387.4932 | 28.8368 | 416.33 | 0 | 695.271 |  |  |  | 1.67
5 |  | 2BHK | 569.3618 | 0 | 569.3618 | 0 | 950.834 |  |  |  | 1.67
6 |  | 2BHK | 536.3486 | 32.8302 | 569.1788 | 0 | 950.529 |  |  |  | 1.67
Tower C
Ground Floor For Entrance Lobby, Meter Room, Fire Control Room & Parking
1st to 4th Podium Floor For Parking
5th Podium Floor For Lobby & Part Terrace Area
1st Floor For Residential (Part Void Area)
1 |  | 1BHK | 402.9826 | 30.3545 | 433.3371 | 0 | 723.673 | 46.8125 |  |  | 1.67
2 |  | 2BHK | 580.2119 | 30.4621 | 610.674 | 0 | 1019.826 | 32.7125 |  |  | 1.67
3 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 654.861 |  |  |  | 1.67
4 |  | Void
5
6
2nd, 4th, 6th, 10th, 12th, 14th, 16th & 20th Floor
1 |  | 1BHK | 395.577 | 0 | 395.577 | 0 | 660.614 |  |  |  | 1.67
2 |  | 2BHK | 571.9236 | 0 | 571.9236 | 0 | 955.112 |  |  |  | 1.67
3 |  | 1BHK | 398.6555 | 31.2156 | 429.8711 | 0 | 717.885 |  |  |  | 1.67
4 |  | 1BHK | 403.7361 | 29.601 | 433.3371 | 0 | 723.673 |  |  |  | 1.67
5 |  | 2BHK | 580.0827 | 0 | 580.0827 | 0 | 968.738 |  |  |  | 1.67
6 |  | 2BHK | 575.508 | 0 | 575.508 | 0 | 961.098 |  |  |  | 1.67
3rd & 13th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | 2BHK | 580.2119 | 30.4621 | 610.674 | 0 | 1019.826 |  |  |  | 1.67
3 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 654.861 |  |  |  | 1.67
4 |  | 1BHK | 395.577 | 0 | 395.577 | 0 | 660.614 |  |  |  | 1.67
5 |  | 2BHK | 588.371 | 30.4621 | 618.8331 | 0 | 1033.451 |  |  |  | 1.67
6 |  | 2BHK | 583.9039 | 30.4621 | 614.3661 | 0 | 1025.991 |  |  |  | 1.67
5th, 7th, 9th, 11th, 15th, 17th & 19th Floor For Residential
1 |  | 1BHK | 402.9826 | 30.3545 | 433.3371 | 0 | 723.673 | 46.8125 |  |  | 1.67
2 |  | 2BHK | 580.2119 | 30.4621 | 610.674 | 0 | 1019.826 | 32.7125 |  |  | 1.67
3 |  | 1BHK | 392.1325 | 0 | 392.1325 | 0 | 654.861 |  |  |  | 1.67
4 |  | 1BHK | 395.577 | 0 | 395.577 | 0 | 660.614 |  |  |  | 1.67
5 |  | 2BHK | 588.371 | 30.4621 | 618.8331 | 0 | 1033.451 |  |  |  | 1.67
6 |  | 2BHK | 583.9039 | 30.4621 | 614.3661 | 0 | 1025.991 |  |  |  | 1.67
8th & 18th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | 2BHK | 571.9236 | 0 | 571.9236 | 0 | 955.112 |  |  |  | 1.67
3 |  | 1BHK | 398.6555 | 31.2156 | 429.8711 | 0 | 717.885 |  |  |  | 1.67
4 |  | 1BHK | 403.7361 | 29.601 | 433.3371 | 0 | 723.673 |  |  |  | 1.67
5 |  | 2BHK | 580.0827 | 0 | 580.0827 | 0 | 968.738 |  |  |  | 1.67
6 |  | 2BHK | 575.508 | 0 | 575.508 | 0 | 961.098 |  |  |  | 1.67
Remarks:
* | Tower A & C = Construction work is in the process at the time of visit. Commercial Building = Construction work is in process at the time of Visit Tower B = Construction work is same as last the visit dtd. 12/12/2024.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Sit out Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As per CC dated 22/05/2023 Tower A, B & C = Upto 21st Floor + Commercial Building = G + 2nd Floor (Built up area 25582.713). As per approved plans dated 22/05/2023 Tower A, B & C = Gr + 1st to 5th Podium + 1st to 20th Floor + Commercial Buildind = Gr + 1st & 2nd Floor (Builtup area 25582.713). Please provide revised approved C.C.
* | We have updated approved EC from State Environment Impact Assessment Authority Maharashtra on 23/01/2024.
* | Recommended Rates/Other Charges of the Property have been revised on 24/09/2024 & 09/10/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh patil |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mantram
Layout :
Google Map :
Formulas:
Khanavale = [Khanavale, row above]
Tower A
Tower A
Tower B
Tower C
Commercial
Wing A
Wing A
Wing B
Wing C
Wing C
Commercial
Wing A
Wing B
Wing C
Commercial
Wing A
Wing B
Wing C
Commercial
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D57: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC