## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-23
Name of the builder group |  |  |  | M/s.Nine Home Creators
Name of the builder company |  |  |  | M/s.Nine Home Creators
Name of the Project |  |  |  | Ninestar Prestige
Contact Details ( Name & Contact No.) |  |  |  | 9860281916
Name / No of the Building |  |  |  | Building No.1 (A Wing & B Wing) Building No.2 (A Wing & B Wing)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | Building No.1 - P99000030830 Building No.2 - P99000030824
Project location details |  | Ninestar Prestige, Gut No.199PT,Gut No.200 & Gut No.205, Gut No.206/PT, near Nine Star Landmark, Tembhikhodave Road, Mande, Saphale West, Palghar, Palghar.
Gut No |  | 199PT,Gut No.200 & Gut No.205, Gut No.206/PT
Road |  | Tembhikhodave Road |  | Locality/Village |  | Mande
City |  | Saphale West |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 40112
Nearby Landmark |  | Nine Star Landmark |  | Distance from city centre: |  | 2.2 KM from Saphale Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.5701 |  | Longitude |  | 72.8026
Location Link |  | https://goo.gl/maps/Kh9M9CXhmxB4CNZy7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5404.37
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.25472
Total FSI availaible for the project |  |  |  | 1.3547
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7321.42
Total number of Buildings |  |  |  | 02 Building (4 Wing)
Approval Detail : Plan approval
Layout Approval No |  | MHASUL/K-1/MJ1/B.S.P/S.R./C.R/55/20 |  |  | Dated | 2021-06-24
Approved Floor plan No. |  | MHASUL/K-1/MJ1/B.S.P/S.R./C.R/55/20 |  |  | Dated | 2021-06-24
Commencement Certificate No. |  | MHASUL/KS-1/T.1/NAP/S.R-55/20 |  |  | Dated | 2021-06-24
Valid Up to: Building No.1 = G + 1st to 7th Floor Building No.2 = G + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7321.42 | [5 empty] | s
Approved no of units |  |  | Building No.1 = A Wing = Flats - 43, Shops - 07 Building No.1 = B Wing = Flats - 43, Shops - 07 Building No.2 = A Wing = Flats - 42 Building No.2 = B Wing = Flats - 28 | [7 empty] | s
Approved no of Floors |  |  | Building No.1 = A & B Wing = G + 1st to 7th Floor Building No.2 = A & B Wing = G + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 - A & B Wing = G + 1st to 7th Floor
Building No.1 - B Wing = G + 1st to 7th Floor
Building No.2 - A & B Wing = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.1 - A Wing = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 85.71% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 - B Wing = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 85.71% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2 - A & B Wing = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 43.21% |  | 69.64% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 6 | 75% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 3 | 42.86% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2 - B Wing = G + 1st to 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 30% |  | 60% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3400
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7000/-
Development Charges |  |  |  |  | 2,00,000/-
Society Formation & Maintenance Charges |  |  |  |  | 60,000/-
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 2720
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1(A Wing) |  | 7 |  | 997.3922 |  | 1545.958
Building No.1(B Wing) |  | 7 |  | 997.3922 |  | 1545.958
Total |  | 14 |  | 1994.7845 |  | 3091.9159 |  |  | 107551.9159 | 73558.8617
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1(A Wing) Flats |  | 43 |  | 20781.9472 |  | 30460
Building No.1(B Wing) Flats |  | 43 |  | 18542.2279 |  | 27170
Building No.2(A Wing) Flats |  | 42 |  | 18281.6852 |  | 26495
Building No.2(B Wing) Flats |  | 28 |  | 13958.217 |  | 20335
Total |  | 156 |  | 71564.0773 |  | 104460
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.1 - Wing A
Ground Floor For Commercial
1 |  | Shop | 105.7025 | 0 | 163.8388 | Ground Floor For Commercial
2 |  | Shop | 132.7201 | 0 | 205.7162 | Ground Floor For Commercial
3 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
4 |  | Shop | 151.7724 | 0 | 235.2472 | Ground Floor For Commercial
5 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
6 |  | Shop | 125.4006 | 0 | 194.3709 | Ground Floor For Commercial
7 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
Building No.1 - Wing B
Ground Floor For Commercial
8 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
9 |  | Shop | 125.4006 | 0 | 194.3709 | Ground Floor For Commercial
10 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
11 |  | Shop | 151.7724 | 0 | 235.2472 | Ground Floor For Commercial
12 |  | Shop | 160.5989 | 0 | 248.9283 | Ground Floor For Commercial
13 |  | Shop | 132.7201 | 0 | 205.7162 | Ground Floor For Commercial
14 |  | Shop | 105.7025 | 0 | 163.8388 | Ground Floor For Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.1 Wing A
Ground Floor For Residential
1 |  | 1BHK | 392.1325 | 0 | 675 | Ground Floor For Residential |  | 3362.963 | 1.7214
1st Floor
101 |  | 1BHK | 464.6011 | 0 | 675 | 1st Floor |  | 34.9925 | 1.4529
102 |  | 1BHK | 412.7994 | 94.7232 | 675 | 1st Floor |  |  | 1.6352
103 |  | 2BHK | 526.3596 | 148.005 | 880 | 1st Floor |  | 3323.8636 | 1.6719
104 |  | 1BHK | 467.0769 | 0 | 675 | 1st Floor |  |  | 1.4452
105 |  | 1BHK | 464.6011 | 0 | 675 | 1st Floor |  |  | 1.4529
106 |  | 1BHK | 464.6011 | 0 | 675 | 1st Floor |  |  | 1.4529
2nd, 3rd, 4th, 5th, 6th & 7th Floor
201,..,701 |  | 1BHK | 464.6011 | 0 | 675 | 2nd, 3rd, 4th, 5th, 6th & 7th Floor | [5 empty] | 201,..,701 | 201 | 701
202,..,702 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 202,..,702 | 202 | 702
203,..,703 |  | 2BHK | 606.1477 | 0 | 880 | [6 empty] | 203,..,703 | 203 | 703
204,..,704 |  | 1BHK | 467.0769 | 0 | 675 | [6 empty] | 204,..,704 | 204 | 704
205,..,705 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 205,..,705 | 205 | 705
206,..,706 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 206,..,706 | 206 | 706
Building No.1 Wing B
Ground Floor For Residential
1 |  | 1BHK | 392.1325 | 0 | 675 | Ground Floor For Residential |  | 34.4225
1st Floor
101 |  | 1RK | 304.6212 | 0 | 440 | 1st Floor |  | 3456.8182
102 |  | 1RK | 304.6212 | 0 | 440 | 1st Floor
103 |  | 1BHK | 467.0769 | 0 | 675 | 1st Floor
104 |  | 2BHK | 526.3596 | 148.005 | 880 | 1st Floor
105 |  | 1BHK | 412.7994 | 94.7232 | 675 | 1st Floor
106 |  | 1BHK | 464.6011 | 0 | 675 | 1st Floor
2nd, 3rd, 4th, 5th, 6th & 7th Floor
201,..,701 |  | 1RK | 304.6212 | 0 | 440 | 2nd, 3rd, 4th, 5th, 6th & 7th Floor |  | 1.4444 |  |  |  | 201,..,701 | 201 | 701
202,..,702 |  | 1RK | 304.6212 | 0 | 440 | [6 empty] | 202,..,702 | 202 | 702
203,..,703 |  | 1BHK | 467.0769 | 0 | 675 | [6 empty] | 203,..,703 | 203 | 703
204,..,704 |  | 2BHK | 606.1477 | 0 | 880 | [6 empty] | 204,..,704 | 204 | 704
205,..,705 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 205,..,705 | 205 | 705
206,..,706 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 206,..,706 | 206 | 706
Building No.2 - Wing A
Ground Floor For Parking & Amenities
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor For Residential
101,..,701 |  | 1RK | 304.6212 | 0 | 440 | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor For Residential | [5 empty] | 101,..,701 | 101 | 701
102,..,702 |  | 1RK | 304.6212 | 0 | 440 | [6 empty] | 102,..,702 | 102 | 702
103,..,703 |  | 2BHK | 606.1477 | 0 | 880 | [6 empty] | 103,..,703 | 103 | 703
104,..,704 |  | 1BHK | 467.0769 | 0 | 675 |  |  | 4010.0466 |  |  |  | 104,..,704 | 104 | 704
105,..,705 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 105,..,705 | 105 | 705
106,..,706 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 106,..,706 | 106 | 706
Building No.2 - Wing B
Ground Floor For Parking & Amenities
1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor For Residential
101,..,701 |  | 1BHK | 464.6011 | 0 | 675 | 1st, 2nd, 3rd, 4th, 5th, 6th & 7th Floor For Residential | [5 empty] | 101,..,701 | 101 | 701
102,..,702 |  | 2BHK | 600.2275 | 0 | 880 | [6 empty] | 102,..,702 | 102 | 702
103,..,703 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 103,..,703 | 103 | 703
104,..,704 |  | 1BHK | 464.6011 | 0 | 675 | [6 empty] | 104,..,704 | 104 | 704
Remarks:
1 | Building No.1 (Wing A & B) - Construction work is in process at the time of visit. Building No.2 (Wing A & B) - Construction work is in process at the time of visit.
2 | We considered Saleable area as per Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + A.P Area +Terrace Area.
5 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr.Vrushabh (Site Supervisor) - 9028478363.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Harshad Pawade |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ninestar Prestige
Google Map :
Formulas:
Mande = [Mande, row above]
Building No.2 (Wing A)
Building No.1 (Wing A)
Building No.1 (Wing B)
Building No.2 (Wing B)
Building No.1 (Wing A)
Building No.1 (Wing B)
Building No.2 (Wing A)
Building No.2 (Wing B)
Building No.2
Building No.1
Building No.2

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted