## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 22/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-22
Name of the builder group |  |  |  | M/s. Macrotech Developers Limited
Name of the builder company |  |  |  | M/s. Macrotech Developers Limited
Name of the Project |  |  |  | Lodha Kandivali Project Tower (1, 2, 3, 4 & 5)
Contact Details ( Name & Contact No.) |  |  |  | Rajendra Giri - 9820248856
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Sandesh : 8097314102
Name / No of the Building |  |  |  | Tower 1 (Wing 1) Tower 2 (Wing 2) Tower 3 (Wing 3) Tower 4 (Wing 4) Tower 5 (Wing 5)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800045908 (Tower 1) P51800031351 (Tower 2) P51800031346 (Tower 3) P51800031532 (Tower 4) P51800032605 (Tower 5)
Project location details |  | Lodha Kandivali Project Tower (1, 2, 3, 4 & 5), Old CTS. No.174C & New CTS No. 174/C1, 174/C/2, 174/C/3 & 174/C/4, near White City, Akurli Road, Akurli, Kandivali, Borivali, Mumbai - 400101.
Old CTS. No |  | 174C & New CTS No. 174/C1, 174/C/2, 174/C/3 & 174/C/4
Road |  | Akurli Road |  | Locality/Village |  | Akurli
City |  | Kandivali |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400101
Nearby Landmark |  | White City |  | Distance from city centre: |  | 4.3 KM from Kandivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | White City Phase- I
North | NA | NA |  |  | White City
South | NA | NA |  |  | Akurli Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.2010111,72.8776277
Location Link |  | https://goo.gl/maps/Pkde9rMC5bdWgVLu5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 35680
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.22
Total FSI availaible for the project |  |  |  | 2.22
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 79209
Total number of Buildings |  |  |  | 5 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM)
Layout Approval No |  | CHE/A -4300/BP(WS) /AR |  |  | Dated | 2021-12-15
Approved Floor plan No. Tower No. 2 to 5 |  | CHE/A -4300/BP(WS) /AR |  |  | Dated | 2021-12-15
Approved Floor plan No. Tower No. 1 |  | CHE/A -4300/BP(WS) /AR |  |  | Dated | 2022-10-07
Commencement Certificate No. |  | CHE/A-4300/BP(WS)/AR/FCC/ 11/Amend |  |  | Dated | 2025-05-20
|  | This C.C. is re-endorsed for Wing 8 - comprising of Ground + 1st to 20th (Pt) floors along with staircase, lift lobby core up to 22nd Floor + LMR & OHT, Multi-level car parking (MLCP) Wing - comprising of 2level basements + Lower ground for parking + Upper ground for parking + 1st to 10th floors for parking + LMR & OHT, Fitness Centre - for entire work, Wing 1 - comprising of Ground + 1st to 33rd floors, Wing 6 comprising of Ground + 1st to 20th floors + LMR & OHT, Wing 3, 4, 5 & 7 - comprising of Ground + 1st to 22nd (Pt) floors + LMR & OHT and Wing 2 comprising of Ground + 1st to 38th upper floors + LMR & OHT as per approved amended plans dtd. 07.03.2025. |  |  | Valid Upto Date | 2025-12-19
Commencement Certificate No. |  | CHE/A-4300/BP(WS)/AR/FCC/9/Amend |  |  | Dated | 2024-07-01
|  | This C.C. is extended further for work of Wing 1 comprising of Ground + 1st to 33rd upper floors, Wing 6 comprising of Ground + 1st to 20th upper floors + LMR & OHT and re-endorsed for Wing 3, 4, 5 & 7 comprising of Ground + 1st to 22nd (Part) upper floors + LMR & OHT, Wing 2 comprising of Ground + 1st to 38th upper floors + LMR & OHT, Wing 8 up to plinth level and MLCP Wing up to plinth level and Fitness Centre for entire work as per approved amended plans dt. 19.06.2024 |  |  | Valid Upto Date | 2024-12-19
Part O. Certificate No.: |  | CHE/A-4300/BP(WS)/AR/OCC/1/New Approved upto : Wing -3 for 1st to 21st + 22nd (part) upper residential floor, and Wing- 4 for 1st to 21st upper residential floors. |  | Date of approval: | Dated | 2024-12-30
O. Certificate No.: |  | NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 79209
Approved no of units |  |  | Flats - 520
Approved no of Floors |  |  | Tower 1 (Wing 1) = Gr + 1st to 38th Floor Tower 2 (Wing 2) = Gr + 1st to 34th Floor Tower 3 (Wing 3) = Gr + 1st to 22nd Floor Tower 4 (Wing 4) = Gr + 1st to 22nd Floor Tower 5 (Wing 5) = Gr + 1st to 22nd Floor
Proposed no of Floors |  |  | Tower 1 (Wing 1) = Gr + 1st to 38th Floor
Tower 2 (Wing 2) = Gr + 1st to 38th Floor
Tower 3 (Wing 3) = Gr + 1st to 22nd Floor
Tower 4 (Wing 4) = Gr + 1st to 22nd Floor
Tower 5 (Wing 5) = Gr + 1st to 22nd Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 (Wing 1) = Gr + 1st to 38th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 30 Slab Completed, Brickwork upto 29 Floor Completed, Internal Plaster upto 24.65 Floor Completed, External Plaster upto 20.3 Floor Completed, Flooring upto 2 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 38
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 30 Slab Completed, Brickwork upto 29 Floor Completed, Internal Plaster upto 24.65 Floor Completed, External Plaster upto 20.3 Floor Completed, Flooring upto 2 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 57.23% |  | 78.07% |  | Excavation in process | 19 |  | Nov 24 slabs given as per Demand letter tower 1
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 30 | 76.92% |  |  |  |  | Footing in Process | 9.5
Brickwork | Brickwork & Internal Plaster | 29 | 76.32% |  |  |  |  | Footing Completed | 19 |  | 8.58
Internal Plaster | Brickwork & Internal Plaster | 24.65 | 64.87% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20.3 | 53.42% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 5.263% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 28.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Construction details: |  | Tower 2 (Wing 2) = Gr + 1st to 38th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 33 Floor Completed, Painting upto 30 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 38
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 33 Floor Completed, Painting upto 30 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 87.63% |  | 94.34% |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 39 | 100% |  |  |  |  | Footing in Process | 9.5
Brickwork | Brickwork & Internal Plaster | 38 | 100% |  |  |  |  | Footing Completed | 19
Internal Plaster | Brickwork & Internal Plaster | 38 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 38 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 33 | 86.84% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 30 | 78.95% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 28.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Construction details: |  | Tower 3 (Wing 3) = Gr + 1st to 22nd Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Progress % |  | 100% |  | Disbursement % |  | 100%
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 100% |  | 100% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Plinth in process | 16.5
Possession |  | 22 | 100% |  |  |  |  | Plinth completed | 22
Construction details: |  | Tower 4 (Wing 4) = Gr + 1st to 22nd Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | All work Completed. OC Received upto 21st Floor. | [5 empty] | All work Completed. OC Received upto 21st Floor.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 100% |  | 100% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Plinth in process | 16.5
Possession |  | 22 | 100% |  |  |  |  | Plinth completed | 22
Construction details: |  | Tower 5 (Wing 5) = Gr + 1st to 22nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 20 Floor Completed, Painting upto 18 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 20 Floor Completed, Painting upto 18 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 88.18% |  | 94.55% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 90.91% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 81.82% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Tower 4 (Wing 4) = Gr + 1st to 22nd Floor | [5 empty] | Excavation work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 11 | 50% | 0% |  | 10% |  | Excavation in process | 11
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Tower 5 (Wing 5) = Gr + 1st to 22nd Floor | [5 empty] | Excavation work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 11 | 50% | 0% |  | 10% |  | Excavation in process | 11
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 17500 |  |  | 16000 to 17500 + OC |  | Sanjay | Cost sheet | 2023-11-22
Floor Rise Rate Per Sq.ft
Development Charges
Utility, Infrastructure & Other Charges |  |  |  |  | 500000
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 14000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 (Wing 1) |  | 149 |  | 159343.4467 |  | 254949.5147
Tower 2 (Wing 2) |  | 134 |  | 141719.2546 |  | 226750.8073
Tower 3 (Wing 3) |  | 64 |  | 64075.1857 |  | 102520.2972
Tower 4 (Wing 4) |  | 87 |  | 66050.3797 |  | 105680.6076
Tower 5 (Wing 5) |  | 86 |  | 65291.1948 |  | 104465.9117
Total |  | 520 |  | 496479.4615 |  | 794367.1384
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Tower 1 (Wing 1)
Ground Floor for Residential & Parking
1 |  | 2BHK | 761.0148 | 0 | 1217.6237 | Ground Floor for Residential & Parking
2 |  | 3BHK | 842.9762 | 0 | 1348.7619
1st to 7th, 10th to 14th, 17th to 21st, 24th to 28th, 31st to 35th, 37th & 38th Floor
1 |  | 3BHK | 1016.649 | 0 | 1626.6385 | 1st to 7th, 10th to 14th, 17th to 21st, 24th to 28th, 31st to 35th, 37th & 38th Floor
2 |  | 3BHK | 1016.649 | 0 | 1626.6385
3 |  | 3BHK | 1133.4384 | 0 | 1813.5015
4 |  | 3BHK | 1133.4384 | 0 | 1813.5015
9th, 16th, 23rd & 30th Floor
1 |  | 3BHK | 1016.649 | 0 | 1626.6385 | 9th, 16th, 23rd & 30th Floor
2 |  | 3BHK | 1016.649 | 0 | 1626.6385
3 |  | 3BHK | 1133.4384 | 0 | 1813.5015
4 |  | 3BHK | 1133.4384 | 0 | 1813.5015
8th, 15th, 22nd & 29th Floor (Part Refuge Area)
1 |  | 3BHK | 1016.649 | 0 | 1626.6385 | 8th, 15th, 22nd & 29th Floor (Part Refuge Area)
2 |  | 3BHK | 1016.649 | 0 | 1626.6385
3 |  | 3BHK | 1133.4384 | 0 | 1813.5015
4 |  | Refuge Area
36th Floor (Part Refuge Area)
1 |  | 3BHK | 1016.649 | 0 | 1626.6385 | 36th Floor (Part Refuge Area)
2 |  | 3BHK | 1016.649 | 0 | 1626.6385
3 |  | 3BHK | 1133.4384 | 0 | 1813.5015
4 |  | Refuge Area
Tower 2 (Wing 2)
Ground Floor for Residential & Parking
1 |  | 3BHK | 1002.8819 | 0 | 1604.611 | Ground Floor for Residential & Parking
2 |  | 3BHK | 1002.8819 | 0 | 1604.611
1st to 7th, 9th to 14th, 16th to 21st, 23rd to 28th & 30th to 34th Floor
1 |  | 3BHK | 1002.8819 | 0 | 1604.611 | 1st to 7th, 9th to 14th, 16th to 21st, 23rd to 28th & 30th to 34th Floor
2 |  | 3BHK | 1002.8819 | 0 | 1604.611
3 |  | 3BHK | 1117.4108 | 0 | 1787.8573
4 |  | 3BHK | 1117.5185 | 0 | 1788.0296
8th, 15th, 22nd & 29th Floor (Part Area Refuge)
1 |  | 3BHK | 1002.8819 | 0 | 1604.611 | 8th, 15th, 22nd & 29th Floor (Part Area Refuge) |  | 15081.5368
2 |  | 3BHK | 1002.8819 | 0 | 1604.611 |  |  | 15081.5368
3 |  | 3BHK | 1117.4108 | 0 | 1787.8573 |  |  | 13535.7556
4 |  | Refuge Area
Tower 3 (Wing 3)
Ground Floor for Residential & Parking
1 |  | 4BHK | 1431.3967 | 0 | 2290.2348 | Ground Floor for Residential & Parking |  | 16548.5219
1st to 7th, 10th to 14th, 17th to 21st Floor
1 |  | 4BHK | 1431.3967 | 0 | 2290.2348 | 1st to 7th, 10th to 14th, 17th to 21st Floor
2 |  | 2BHK | 759.8308 | 0 | 1215.7292 |  |  | 16039.756
3 |  | 2BHK | 759.8308 | 0 | 1215.7292
8th & 15th Floor
1 |  | 4BHK | 1431.3967 | 0 | 2290.2348 | 8th & 15th Floor
2 |  | Refuge Area
3 |  | 2BHK | 759.8308 | 0 | 1215.7292
9th & 16th Floor
1 |  | 4BHK | 1431.3967 | 0 | 2290.2348 | 9th & 16th Floor
2 |  | 2BHK | 759.8308 | 0 | 1215.7292
3 |  | 2BHK | 759.8308 | 0 | 1215.7292
22nd Floor (Part Terrace)
1 |  | 4BHK | 1431.3967 | 0 | 2290.2348 | 22nd Floor (Part Terrace)
2 |  | Terrace Area
3 |  | 2BHK | 759.8308 | 0 | 1215.7292
Tower 4 (Wing 4)
Ground Floor for Residential & Parking
1 |  | 2BHK | 758.862 | 0 | 1214.1792 | Ground Floor for Residential & Parking
2 |  | 2BHK | 759.4002 | 0 | 1215.0403
1st to 7th, 10th to 14th, 17th to 21st Floor
1 |  | 2BHK | 758.862 | 0 | 1214.1792 | 1st to 7th, 10th to 14th, 17th to 21st Floor
2 |  | 2BHK | 759.4002 | 0 | 1215.0403
3 |  | 2BHK | 759.5078 | 0 | 1215.2125
4 |  | 2BHK | 759.0773 | 0 | 1214.5236
8th & 15th Floor (Part Refuge)
. |  | 2BHK | 758.862 | 0 | 1214.1792 | 8th & 15th Floor (Part Refuge)
2 |  | 2BHK | 759.4002 | 0 | 1215.0403
3 |  | Refuge Area
4 |  | 2BHK | 759.0773 | 0 | 1214.5236
9th & 16th Floor
1 |  | 2BHK | 758.862 | 0 | 1214.1792 | 9th & 16th Floor
2 |  | 2BHK | 759.4002 | 0 | 1215.0403
3 |  | 2BHK | 759.5078 | 0 | 1215.2125
4 |  | 2BHK | 759.0773 | 0 | 1214.5236
22nd Floor (Part Terrace)
1 |  | 2BHK | 758.862 | 0 | 1214.1792 | 22nd Floor (Part Terrace)
2 |  | 2BHK | 759.4002 | 0 | 1215.0403
3 |  | Terrace Area
4 |  | 2BHK | 759.0773 | 0 | 1214.5236
Tower 5 (Wing 5)
Ground Floor for Residential & Parking
3 |  | 2BHK | 759.0773 | 0 | 1214.5236 | Ground Floor for Residential & Parking
1st to 7th, 10th to 14th, 17th to 21st Floor
1 |  | 2BHK | 759.0773 | 0 | 1214.5236 | 1st to 7th, 10th to 14th, 17th to 21st Floor
2 |  | 2BHK | 759.5078 | 0 | 1215.2125
3 |  | 2BHK | 759.4002 | 0 | 1215.0403
4 |  | 2BHK | 758.862 | 0 | 1214.1792
8th & 15th Floor (Part Reffuge)
1 |  | 2BHK | 759.0773 | 0 | 1214.5236 | 8th & 15th Floor (Part Reffuge)
2 |  | Refuge Area
3 |  | 2BHK | 759.4002 | 0 | 1215.0403
4 |  | 2BHK | 758.862 | 0 | 1214.1792
9th & 16th Floor
1 |  | 2BHK | 759.0773 | 0 | 1214.5236 | 9th & 16th Floor
2 |  | 2BHK | 759.5078 | 0 | 1215.2125
3 |  | 2BHK | 759.4002 | 0 | 1215.0403
4 |  | 2BHK | 758.862 | 0 | 1214.1792
22nd Floor (Part Terrace)
1 |  | 2BHK | 759.0773 | 0 | 1214.5236 | 22nd Floor (Part Terrace)
2 |  | Terrace Area
3 |  | 2BHK | 759.4002 | 0 | 1215.0403
4 |  | 2BHK | 758.862 | 0 | 1214.1792
Remarks:
* | Tower 1 = Construction work is in process at the time of Visit. Internal photographs was not allowed. Tower 2 & 5 = Construction work is in process at the time of Visit. Tower 3 = All work completed. OC Received. Tower 4 = All work completed. OC Received upto 21st Floor.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved floor plan of Tower 5 (Wing 5) (on 04/04/2022).
* | We have updated approved floor plan of Tower 1 (Wing 1) (on 20/07/2023).
* | We have updated revised approved CC from MCGM site (on 29/12/2023).
* | We have updated latest CC from MCGM site (On 13/03/2024).
* | We have updated latest CC from MCGM site (On 12/08/2024).
* | Validity of CC is expired on 19/12/2024. Please provide latest CC for Tower 1 (Wing 1).
* | We have updated revised CC & OC from MCGM site (On 10/04/2025).
* | Please provide revised approved plan.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lodha Kandivali Project Tower (1, 2, 3, 4 & 5)
Layout :
Google Map :
3
T1
T5
T4
T3
T2
Tower 1
Tower 1
Tower 2
Tower 3
Tower 4
Tower 5
15th flr
22nd flr

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
2023-11-22 | Tower 1 - 1904 | Sanjay | 3.5cr (2P+)