## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-23 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Narang Propco Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Narang Propco Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Narang Vivenda | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Sandeep Gadge 7045015013
Site Person - Contact Details (Name & Contact No.) |  |  |  | Ms. Sneha : 7715983684
Name / No of the Building |  |  |  | Building No.1 (Wing D)
Name / No of the Existing Building |  |  |  | Ushma Nagar CHS Federation Ltd | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800055504 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Narang Vivenda, Plot No.1 to 7 & CTS No. 307/3, 307/4, 307/5 & 307/6 Redevelopement of "Ushma Nagar CHS Federation Ltd", near Sandesh CHS, Evershine Nagar Road, Ushma Nagar, Valnai, Malad West, Borivali, Mumbai - 400064. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 1 to 7 & CTS No. 307/3, 307/4, 307/5 & 307/6 Redevelopement of "Ushma Nagar CHS Federation Ltd" | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Ushma Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Evershine Nagar Road |  | Locality/Village |  | Valnai | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Malad West |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Borivali |  | Pin Code |  | 400064 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Sandesh CHS |  | Distance from city centre: |  | 2.6 KM from Malad Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Sandesh CHS
West | NA | Other Plot |  |  | Samir CHS
North | NA | Other Plot |  |  | Vishal Nagar CHS
South | NA | 13.40 M W Road |  |  | Evershine Nagar Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.1941039, 72.8324685
Location Link |  | https://maps.app.goo.gl/1wYfWPTJwKXiFd878
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 11090.2
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 0.84771
Total FSI availaible for the project |  |  |  | 4.8477
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 53762.074
Total number of Buildings |  |  |  | 01 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | P-15166/2023/(307/3 AND OTHER) P/N WARD/VALNAI/337/2/AMEND |  |  | Dated | 2024-02-12 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | P-15166/2023/(307/3 AND OTHER) P/N WARD/VALNAI/337/2/AMEND |  |  | Dated | 2024-02-12 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | P-15166/2023/(307/3 And Other)/P/N Ward/VALNAI/FCC/3/Amend |  |  | Dated | 2025-06-02 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is now granted for the work of remaining podium portion between Wing ‘A’ & ‘D’ of building No. 1 comprising of 02 levels basement + stilt (pt) + ground (pt)+ 1st to 4th level podium (Marked E-F-G-H in plan) as per approved amended plans dtd. 20.08.2024. |  |  | Valid Upto Date | 2025-12-26 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | P-15166/2023/(307/3 And Other)/P/N Ward/VALNAI- CFO/1/New |  |  | Dated | 2023-04-01 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Sale Wing ‘D’ is having common 02 level basements with Rehab Wing ‘A’, ‘B’ & ‘C’ i.e. Lower & Upper Basement + Ground floor + common 1st to 3rd podium floors + common 4th part podium & part podium for LOS + 5th to 39th upper residential floors (39th floor part) with a total height of 138.39 mtrs measured from general ground level to terrace level | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | Sale Wing ‘D’ is having common 02 level basements with Rehab Wing ‘A’, ‘B’ & ‘C’ i.e. Lower & Upper Basement + Ground floor + common 1st to 3rd podium floors + common 4th part podium & part podium for LOS + 5th to 39th upper residential floors (39th floor part) with a total height of 138.39 mtrs measured from general ground level to terrace level |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 53762.074
Approved no of units |  |  | Sale Flats - 255, Rehab Flats- 4, Rehab Shops -14
Approved no of Floors |  |  | Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 38th Floor
Proposed no of Floors |  |  | Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 39th Floor
Expected Completion |  |  | As per RERA - 31/12/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Center, Swimming Pool, Play Park, Multipurpose Lawn, Mini Theatre, Kids Play Area, Indoor games, Seating Area, Banquet Hall, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 39th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.25 Floor Completed | , RCC upto 10 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.25 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 39 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.25 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 22.52% |  | 54.04% |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 10 | 25% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 5 | 12.82% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 3.75 | 9.615% |  |  |  |  | Basement 1 | 29.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.25 | 8.333% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Construction details: |  | Part II = Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 39th Floor | [5 empty] | Excavation Completed, 1st Basement Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 39 | Excavation | , 1st Basement Completed
Stage of construction: |  | Excavation Completed, 1st Basement Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 19.5
Plinth |  | 29.25 | 75% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 29.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Average Progress % |  | 15.01% |  | Average Disbursement % |  | 46.39% |  | Plinth completed | 39
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 20000 |  |  |  | Rate 20K By Shailesh Verbal On 06/09/2024 | [7 empty] | 800000 | 150000 | 100000 | 100000
Other Charges |  |  |  |  | 600000 |  |  |  | 6 lacs other charges On 09/09/2024 | [7 empty] | 1300000 | 400000 | 350000 | 400000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 1000000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 16000 | [12 empty] | 1000000
Commercial Area Details : Shops
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Rehab |  | 14 |  | 3618.7045 |  | 5608.992
Total |  | 14 |  | 3618.7045 |  | 5608.992
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Rehab |  | 4 |  | 4565.3568 |  | 6848.0353
Sale |  | 255 |  | 285513.141 |  | 428269.7114
Total |  | 259 |  | 290078.4978 |  | 435117.7467 |  |  |  | 259
Grand Total |  | 273 |  | 293697.2023 |  | 440726.7387
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Building No.1 (Wing D)
1st & 2nd Basement For Parking
Ground Floor Commercial, Electrical Room & Parking
17 | Rehab | Shop | 187.7242 | 0 | 187.7242 | 0 | 290.9724
18 | Rehab | Shop | 198.7443 | 0 | 198.7443 | 0 | 308.0537
19 | Rehab | Shop | 258.871 | 0 | 258.871 | 0 | 401.25
20 | Rehab | Shop | 408.8517 | 0 | 408.8517 | 0 | 633.7201
21 | Rehab | Shop | 264.2185 | 0 | 264.2185 | 0 | 409.5387
22 | Rehab | Shop | 281.0636 | 0 | 281.0636 | 0 | 435.6487
23 | Rehab | Shop | 160.1414 | 0 | 160.1414 | 0 | 248.2192
24 | Rehab | Shop | 431.2893 | 0 | 431.2893 | 0 | 668.4984
25 | Rehab | Shop | 220.4177 | 0 | 220.4177 | 0 | 341.6474
26 | Rehab | Shop | 238.6863 | 0 | 238.6863 | 0 | 369.9638
27 | Rehab | Shop | 252.3819 | 0 | 252.3819 | 0 | 391.1919
28 | Rehab | Shop | 252.8948 | 0 | 252.8948 | 0 | 391.9869
29 | Rehab | Shop | 238.7455 | 0 | 238.7455 | 0 | 370.0556
30 | Rehab | Shop | 224.6743 | 0 | 224.6743 | 0 | 348.2451
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No.1 (Wing D)
1st, 2nd & 3rd Podium Floor For Parking
4th Podium Floor For Amenities | [8 empty] | 10.764
5th Floor For Residential
1 | Rehab | 2BHK | 1074.1396 | 67.1997 | 1141.3392 | 0 | 1712.0088 | 98.6164 | 5.735
2 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
3 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921 | 70.9056
4 | Rehab | 2BHK | 1074.1396 | 67.1997 | 1141.3392 | 0 | 1712.0088
5 | Rehab | 2BHK | 1074.1396 | 67.1997 | 1141.3392 | 0 | 1712.0088
6 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
7 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
8 | Rehab | 2BHK | 1074.1396 | 67.1997 | 1141.3392 | 0 | 1712.0088
6th, 8th to 13th, 15th to 20th, 22nd to 27th, 29th to 34th & 36th to 38th Floor For Residential | [9 empty] | 19000
1 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013 |  |  | 39858225.498
2 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921 |  |  | 23827750.128 |  |  | 34
3 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921 |  |  | 23827750.128
4 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013 | 120.8043 | 5.8 | 39858225.498
5 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013 |  |  | 39858225.498
6 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921 |  |  | 23827750.128
7 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921 |  |  | 23827750.128
8 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013 |  |  | 39858225.498
7th, 14th, 21st & 28th Floor (Part Refuge Area)
1 | Sale | 4BHK | 1592.7168 | 62.4312 | 1655.148 | 0 | 2482.722 | 138.1779 | 5.8
2 | - | Refuge Area
3 | - | [9 empty] | 259 |  | 28
4 | -
5 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013
6 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
7 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
8 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013
35th Floor (Part Refuge Area)
1 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013
2 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
3 | Sale | 1BHK | 620.7061 | 72.3341 | 693.0401 | 0 | 1039.5602 | 58.0694 | 6.72
4 | - | Refuge Area
5 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013
6 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
7 | Sale | 2BHK | 763.7273 | 72.3341 | 836.0614 | 0 | 1254.0921
8 | Sale | 3BHK | 1336.103 | 62.4312 | 1398.5342 | 0 | 2097.8013
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please check for Environment Clearance Certificate.
* | Recommended Rates / Other Charges of the Property have been revised on 06/09/2024 & 09/09/2024.
* | We have updated latest CC from MCGM site (On 13/06/2025).
* | Construction work goes beyond CC permission. Please provide latest CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Narang Vivenda
Layout :
Google Map :
N
N
Building No.1 Wing D (Sale)
Wing D
Wing D
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F108: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H149: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate