## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 22/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-22
Name of the builder group |  |  |  | Deep Laxmi Associates
Name of the builder company |  |  |  | Deep Laxmi Associates
Name of the Project |  |  |  | Shreeji Greens
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Deepak Warghade - 9970866890
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Bulding A, B & C
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700046293
Project location details |  | Shreeji Greens, Survey No.70, Hissa No. 6A & 6B, Survey No. 73, Hissa No. 2 & 5, Survey No. 73, Hissa No. 5, near Carmel Convent High School, Internal Road, , Belavali, Chikhloli, Ambernath, Thane - 421503.
Survey No |  | 70, Hissa No. 6A & 6B, Survey No. 73, Hissa No. 2 & 5, Survey No. 73, Hissa No. 5
Locality |  | NA
Road |  | Internal Road |  | Locality/Village |  | Belavali
City |  | Chikhloli |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Nearby Landmark |  | Carmel Convent High School |  | Distance from city centre: |  | 2 KM from Chikhloli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | School
West | NA | NA |  |  | Building
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.17969,73.217961
Location Link |  | https://goo.gl/maps/zsgAcQRf53XEjAXQ9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6640
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.8996
Total FSI availaible for the project |  |  |  | 2.9996
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19917.56
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgaon Badlapur Municipal Council
Layout Approval No |  | KBNP/NRV/BP/6936-92 |  |  | Dated | 2021-08-30
Approved Floor plan No. |  | KBNP/NRV/BP/6936-92 |  |  | Dated | 2021-08-30
Commencement-CC No Valid Up to: |  | K.B.N.P/B.P/2021-2022/6936 Uniqe No.92 |  |  | Dated | 2021-08-30
Building A = Gr + 1st to12th Floor Building B = Gr + 1st to 14th Floor Building C = Gr + 1st to 7th Floor
O. Certificate No.: Approved upto : |  | KBMC/TPD/2024-25/2564 Building A = Gr + 1st to12th Floor |  |  | Dated | 2024-12-12
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 19917.56
Approved no of units |  |  | Flats - 381, Shops - 2
Approved no of Floors |  |  | Building A = Gr + 1st to 12th Floor Building B = Gr + 1st to 14th Floor Building C = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building A = Gr + 1st to 12th Floor
Building B = Gr + 1st to 14th Floor
Building C = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/07/2026
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building A = Gr + 1st to 12th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 100% |  | 100% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 100% |  |  |  |  | Plinth in process | 9
Possession |  | 12 | 100% |  |  |  |  | Plinth completed | 12
Construction details: |  | Part 1 Building B = Gr + 1st to 14th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation | , Plinth work is process
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 7
Plinth |  | 10.5 | 75% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building B = Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 12 Floor, External Plaster upto 3 Floor Completed | , RCC upto 14 Slab, Brickwork upto 12 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 12 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 55.9% |  | 78.36% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 14 | 93.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 12 | 85.71% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 21.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building B Average Progress % |  | 31.7% |  | Building B Average Disbursement % |  | 58.55%
Construction details: |  | Building C = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor, Finishing upto 1 Floor Completed | , Painting upto 6 Floor, Finishing upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor, Finishing upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 90% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 14.29% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | Salable area of flat no. A203 is changed from 593 to 606 (they want rate as per 5000 rate) on 26/12/2024. by bhargav
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4900 |  |  |  | Rate 200+ Bhargav verbal On 19/11/2024
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges (For 1BHK) |  |  |  |  | 250000 |  |  | Added by Smith | 2023-05-30 | Cost sheet
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Development Charges (for 2BHK) |  |  |  |  | 400000 |  |  | Rushikesh | 2023-06-27 | Cost sheet
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 3920
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 2 |  | 495.6822 |  | 793.0915
Residential Area Details : | [7 empty] | `
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 168 |  | 74472.241 |  | 112002.4903
Wing B |  | 164 |  | 80014.9475 |  | 120022.4212
Wing C |  | 49 |  | 25685.9448 |  | 38528.9172 |  |  |  | 170
Total |  | 381 |  | 180173.1333 |  | 270553.8288 |  |  |  | 164
Building details Floor Wise | [9 empty] | 49
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Building A
Ground Floor for Commercial
1 |  | Shop | 249.8324 | 0 | 399.7319 | Ground Floor for Commercial |  | 22.8375
2 |  | Shop | 245.8498 | 0 | 393.3596 | Ground Floor for Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building A
1st Floor for Residential | [8 empty] | 10.764
101 |  | 1BHK | 393.3973 | 0 | 672.9787 | 1st Floor for Residential
102 |  | 1BHK | 393.3973 | 0 | 590.0959 | 1st Floor for Residential
103 |  | 1BHK | 395.4424 | 0 | 593.1637 | 1st Floor for Residential
104 |  | 2BHK | 571.676 | 82.8828 | 940.3969 | 1st Floor for Residential
105 |  | 2BHK | 571.676 | 0 | 857.5141 | 1st Floor for Residential
106 |  | 1BHK | 397.057 | 0 | 595.5856 | 1st Floor for Residential
107 |  | 1BHK | 395.0119 | 0 | 592.5178 | 1st Floor for Residential
108 |  | 1BHK | 395.0119 | 0 | 592.5178 | 1st Floor for Residential
109 |  | 1BHK | 395.0119 | 0 | 592.5178 | 1st Floor for Residential
110 |  | 1BHK | 393.3973 | 0 | 590.0959 | 1st Floor for Residential
111 |  | 2BHK | 571.676 | 0 | 857.5141 | 1st Floor for Residential
112 |  | 2BHK | 571.676 | 0 | 857.5141 | 1st Floor for Residential
113 |  | 1BHK | 393.3973 | 0 | 590.0959 | 1st Floor for Residential
114 |  | 1BHK | 393.3973 | 0 | 590.0959 | 1st Floor for Residential
2nd Floor
201,..1201 |  | 1BHK | 393.3973 | 0 | 590.0959 | 2nd Floor
202,..1202 |  | 1BHK | 393.3973 | 0 | 590.0959 | 2nd Floor
203,..1203 |  | 1BHK | 395.4424 | 0 | 606 | 2nd Floor |  | 2969400 | 2965000
204,..1204 |  | 2BHK | 571.676 | 0 | 857.5141 | 2nd Floor
205,..1205 |  | 2BHK | 571.676 | 0 | 857.5141 | 2nd Floor
206,..1206 |  | 1BHK | 397.057 | 0 | 595.5856 | 2nd Floor
207,..1207 |  | 1BHK | 395.0119 | 0 | 592.5178 | 2nd Floor
208,..1208 |  | 1BHK | 395.0119 | 0 | 592.5178 | 2nd Floor
209,..1209 |  | 1BHK | 395.0119 | 0 | 592.5178 | 2nd Floor
210,..1210 |  | 1BHK | 393.3973 | 0 | 590.0959 | 2nd Floor
211,..1211 |  | 2BHK | 571.676 | 0 | 857.5141 | 2nd Floor
212,..1212 |  | 2BHK | 571.676 | 0 | 857.5141 | 2nd Floor
213,..1213 |  | 1BHK | 393.3973 | 0 | 590.0959 | 2nd Floor
214,..1214 |  | 1BHK | 393.3973 | 0 | 590.0959 | 2nd Floor
3rd to 7th & 9th to 12th Floor
201,..1201 |  | 1BHK | 393.3973 | 0 | 590.0959 | 3rd to 7th & 9th to 12th Floor
202,..1202 |  | 1BHK | 393.3973 | 0 | 590.0959 | 3rd to 7th & 9th to 12th Floor
203,..1203 |  | 1BHK | 395.4424 | 0 | 593.1637 | 3rd to 7th & 9th to 12th Floor |  | 2906502.0075 | 2965000
204,..1204 |  | 2BHK | 571.676 | 0 | 857.5141 | 3rd to 7th & 9th to 12th Floor
205,..1205 |  | 2BHK | 571.676 | 0 | 857.5141 | 3rd to 7th & 9th to 12th Floor
206,..1206 |  | 1BHK | 397.057 | 0 | 595.5856 | 3rd to 7th & 9th to 12th Floor
207,..1207 |  | 1BHK | 395.0119 | 0 | 592.5178 | 3rd to 7th & 9th to 12th Floor
208,..1208 |  | 1BHK | 395.0119 | 0 | 592.5178 | 3rd to 7th & 9th to 12th Floor
209,..1209 |  | 1BHK | 395.0119 | 0 | 592.5178 | 3rd to 7th & 9th to 12th Floor
210,..1210 |  | 1BHK | 393.3973 | 0 | 590.0959 | 3rd to 7th & 9th to 12th Floor
211,..1211 |  | 2BHK | 571.676 | 0 | 857.5141 | 3rd to 7th & 9th to 12th Floor
212,..1212 |  | 2BHK | 571.676 | 0 | 857.5141 | 3rd to 7th & 9th to 12th Floor
213,..1213 |  | 1BHK | 393.3973 | 0 | 590.0959 | 3rd to 7th & 9th to 12th Floor
214,..1214 |  | 1BHK | 393.3973 | 0 | 590.0959 | 3rd to 7th & 9th to 12th Floor
8th Floor (Part Refuge Area) | [8 empty] | 10.764
801 |  | 1RK | 242.1631 | 0 | 363.2446 | 8th Floor (Part Refuge Area)
802 |  | 1RK | 242.1631 | 0 | 363.2446 | 8th Floor (Part Refuge Area)
803 |  | 1BHK | 395.4424 | 0 | 593.1637 | 8th Floor (Part Refuge Area)
804 |  | 2BHK | 571.676 | 0 | 857.5141 | 8th Floor (Part Refuge Area)
805 |  | 2BHK | 571.676 | 0 | 857.5141 | 8th Floor (Part Refuge Area)
806 |  | 1BHK | 397.057 | 0 | 595.5856 | 8th Floor (Part Refuge Area)
807 |  | 1BHK | 395.0119 | 0 | 592.5178 | 8th Floor (Part Refuge Area)
808 |  | 1BHK | 395.0119 | 0 | 592.5178 | 8th Floor (Part Refuge Area)
809 |  | 1BHK | 395.0119 | 0 | 592.5178 | 8th Floor (Part Refuge Area)
810 |  | 1BHK | 393.3973 | 0 | 590.0959 | 8th Floor (Part Refuge Area)
811 |  | 2BHK | 571.676 | 0 | 857.5141 | 8th Floor (Part Refuge Area)
812 |  | 2BHK | 571.676 | 0 | 857.5141 | 8th Floor (Part Refuge Area)
813 |  | 1BHK | 393.3973 | 0 | 590.0959 | 8th Floor (Part Refuge Area)
814 |  | 1BHK | 393.3973 | 0 | 590.0959 | 8th Floor (Part Refuge Area)
Building B
Ground Floor for Commercial
1st to 7th & 9th to 12th Floor for Residential
101,..,1201 |  | 1BHK | 522.5384 | 0 | 783.8076 | 1st to 7th & 9th to 12th Floor for Residential
102,..,1202 |  | 2BHK | 571.4608 | 0 | 857.1911 | 1st to 7th & 9th to 12th Floor for Residential
103,..,1203 |  | 1BHK | 501.7908 | 0 | 752.6862 | 1st to 7th & 9th to 12th Floor for Residential
104,..,1204 |  | 1BHK | 501.7908 | 0 | 752.6862 | 1st to 7th & 9th to 12th Floor for Residential
105,..,1205 |  | 2BHK | 571.3531 | 0 | 857.0297 | 1st to 7th & 9th to 12th Floor for Residential
106,..,1206 |  | 1BHK | 445.1452 | 0 | 667.7178 | 1st to 7th & 9th to 12th Floor for Residential
107,..,1207 |  | 1BHK | 388.1229 | 0 | 582.1844 | 1st to 7th & 9th to 12th Floor for Residential
108,..,1208 |  | 1BHK | 386.5083 | 0 | 579.7625 | 1st to 7th & 9th to 12th Floor for Residential
109,..,1209 |  | 2BHK | 572.4026 | 0 | 858.6039 | 1st to 7th & 9th to 12th Floor for Residential
110,..,1210 |  | 2BHK | 572.4026 | 0 | 858.6039 | 1st to 7th & 9th to 12th Floor for Residential
111,..,1211 |  | 1BHK | 386.5083 | 0 | 579.7625 | 1st to 7th & 9th to 12th Floor for Residential
112,..,1212 |  | 1BHK | 426.0122 | 0 | 639.0183 | 1st to 7th & 9th to 12th Floor for Residential
8th & 13th Floor (Part Refuge Area)
801 |  | 1BHK | 522.5384 | 0 | 783.8076 | 8th & 13th Floor (Part Refuge Area)
802 |  | 2BHK | 571.4608 | 0 | 857.1911 | 8th & 13th Floor (Part Refuge Area)
803 |  | Refuge Area |  |  |  | 8th & 13th Floor (Part Refuge Area)
804 |  | 2BHK | 661.2056 | 0 | 991.8084 | 8th & 13th Floor (Part Refuge Area)
805 |  | 2BHK | 571.3531 | 0 | 857.0297 | 8th & 13th Floor (Part Refuge Area)
806 |  | 1BHK | 445.1452 | 0 | 667.7178 | 8th & 13th Floor (Part Refuge Area)
807 |  | 1BHK | 388.1229 | 0 | 582.1844 | 8th & 13th Floor (Part Refuge Area)
808 |  | 1BHK | 386.5083 | 0 | 579.7625 | 8th & 13th Floor (Part Refuge Area)
809 |  | 2BHK | 572.4026 | 0 | 858.6039 | 8th & 13th Floor (Part Refuge Area)
810 |  | 2BHK | 572.4026 | 0 | 858.6039 | 8th & 13th Floor (Part Refuge Area)
811 |  | 1BHK | 386.5083 | 0 | 579.7625 | 8th & 13th Floor (Part Refuge Area)
812 |  | 1BHK | 426.0122 | 0 | 639.0183 | 8th & 13th Floor (Part Refuge Area)
14th Floor (Part Terrace Area)
1401 |  | 1BHK | 522.5384 | 0 | 783.8076 | 14th Floor (Part Terrace Area)
1402 |  | 2BHK | 571.4608 | 0 | 857.1911 | 14th Floor (Part Terrace Area)
1403 |  | 1BHK | 501.7908 | 0 | 752.6862 | 14th Floor (Part Terrace Area)
1404 |  | 1BHK | 501.7908 | 0 | 752.6862 | 14th Floor (Part Terrace Area)
1405 |  | 2BHK | 571.3531 | 0 | 857.0297 | 14th Floor (Part Terrace Area)
1406 |  | 1BHK | 445.1452 | 0 | 667.7178 | 14th Floor (Part Terrace Area)
1407 |  | 1BHK | 388.1229 | 0 | 582.1844 | 14th Floor (Part Terrace Area)
1408 |  | 1BHK | 386.5083 | 0 | 579.7625 | 14th Floor (Part Terrace Area)
1409 |  | 1BHK | 386.5083 | 0 | 579.7625 | 14th Floor (Part Terrace Area)
1410 |  | 1BHK | 426.0122 | 0 | 639.0183 | 14th Floor (Part Terrace Area)
Building C
Ground Floor for Commercial
1st to 7th Floor for Residential
101,..,701 |  | 1BHK | 434.8925 | 0 | 652.3388 | 1st to 7th Floor for Residential
102,..,702 |  | 2BHK | 588.4679 | 0 | 882.7018 | 1st to 7th Floor for Residential
103,..,703 |  | 2BHK | 588.4679 | 0 | 882.7018 | 1st to 7th Floor for Residential
104,..,704 |  | 1BHK | 388.0153 | 0 | 582.0229 | 1st to 7th Floor for Residential
105,..,705 |  | 2BHK | 503.9436 | 0 | 755.9154 | 1st to 7th Floor for Residential
106,..,706 |  | 2BHK | 582.8168 | 0 | 874.2252 | 1st to 7th Floor for Residential
107,..,707 |  | 2BHK | 582.8168 | 0 | 874.2252 | 1st to 7th Floor for Residential
Remarks:
* | Building A = All work completed. OC received. Building B = Construction work is in process at the time of visit. Internal photos was not allowed. Building C = Construction work is in process at the time of visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Since building B & C have received CC on 30/08/2021, but as of construction work is not started.
* | Recommended Rates of the Property have been revised on 19/11/2024.
* | We have updated OC for Building A on 26/12/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shreeji Greens
Layout :
Google Map :
Formulas:
Belavali = [Belavali, row above]
A Wing
B Wing
C Wing
Wing A
Building A
Building B
Building B
Building C
Building A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
201 | 1201 | 201,..,1201 | 201,..1201 | 101 | 701 | 101,..,701
202 | 1202 | 202,..,1202 | 202,..1202 | 102 | 702 | 102,..,702
203 | 1203 | 203,..,1203 | 203,..1203 | 103 | 703 | 103,..,703
204 | 1204 | 204,..,1204 | 204,..1204 | 104 | 704 | 104,..,704
205 | 1205 | 205,..,1205 | 205,..1205 | 105 | 705 | 105,..,705
206 | 1206 | 206,..,1206 | 206,..1206 | 106 | 706 | 106,..,706
207 | 1207 | 207,..,1207 | 207,..1207 | 107 | 707 | 107,..,707
208 | 1208 | 208,..,1208 | 208,..1208 | 108 | 708 | 108,..,708
209 | 1209 | 209,..,1209 | 209,..1209 | 109 | 709 | 109,..,709
210 | 1210 | 210,..,1210 | 210,..1210 | 110 | 710 | 110,..,710
211 | 1211 | 211,..,1211 | 211,..1211 | 111 | 711 | 111,..,711
212 | 1212 | 212,..,1212 | 212,..1212 | 112 | 712 | 112,..,712
213 | 1213 | 213,..,1213 | 213,..1213 | 113 | 713 | 113,..,713
214 | 1214 | 214,..,1214 | 214,..1214 | 114 | 714