## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-23
Name of the builder group |  |  |  | Terraferma Developers LLP
Name of the builder company |  |  |  | Terraferma Developers LLP
Name of the Project |  |  |  | Saujanya Rachanaa
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Manish Vakharia 9821073583
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms. Priya : 8433904500
Name / No of the Building |  |  |  | Wing (A, B & C) (Redevelopment Project)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51800046295
Project location details |  | Saujanya Rachanaa, CTS No.685, 685/1 to 3, near Vraj One , Bhardawadi Rd, Navneeth Colony, Ambivali, Andheri West, Andheri, Mumbai - 400058.
CTS No |  | 685, 685/1 to 3
Locality |  | Navneeth Colony
Road |  | Bhardawadi Rd |  | Locality/Village |  | Ambivali
City |  | Andheri West |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400058
Nearby Landmark |  | Vraj One |  | Distance from city centre: |  | 1.1KM from Andheri Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Vraj One
West | NA | NA |  |  | Panchsheel CHSL
North | NA | NA |  |  | Bhardawadi Rd/Bhardawadi Park
South | NA | NA |  |  | Palavi Co-operative Housing Society
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.1260383,72.8434363
Location Link |  | https://goo.gl/maps/nTW4piPpCtmKVEDXA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3156.39
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.2
Total FSI availaible for the project |  |  |  | 2.2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6944.06
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | MCGM
Layout Approval No |  | P-8426/2021/(685)/K/W WARD/AMBIVALI |  |  | Dated | 2022-12-23
Approved Floor plan No. |  | P-8426/2021/(685)/K/W WARD/AMBIVALI |  |  | Dated | 2022-12-23
Commencement-CC No Valid Up to: |  | P-8426/2021/(685)/K/W Ward/AMBIVALI/FCC/1/New |  |  | Dated | 2023-06-07
|  | Re-endorsement of earlier C.C. and further C.C. for building comprising of 3 Wings i.e. Full C.C. for ‘A’ Wing upto top of 12th (pt.) upper floor slab level + LMR and OHT (i.e. height up to 49.10 mt. AGL), Full C.C. for Wing ‘B’ upto top of 11th upper floor slab level (i.e. height up to 43.50mt. AGL) + LMR and OHT (i.e. height up to 49.10 mt. AGL) & further C.C. of Wing ‘C’ up to top of 10th upper floor slab level (i.e. height up to 40.50mt. AGL) as per approved amended plan dated 23/12/2022. |  |  | Valid Upto Date | 2024-06-06
Commencement-CC No Valid Up to: |  | P-8426/2021/(685)/K/W Ward/AMBIVALI/FCC/1/Amend |  |  | Dated | 2024-06-10
|  | Re-endorsement of C.C. of wing `A, B & C' and full C.C. for Wing `C' upto top of 11th floor (i.e. height up to 43.50mt. AGL) + LMR and OHT i.e. height up to 49.10 mt. AGL as per approved amended plan dated 17/05/2024 is approved. |  |  | Valid Upto Date | 2026-06-12
O. Certificate No.: |  | P-8426/2021/(685)/K/W WARD/AMBIVALI/OCC/1/NEW Approved upto : Wing A = Gr/St + 2P + 1st to 12th Floor Wing B & C = Gr/St + 2P + 1st to 11th Floor |  |  | Dated | 2025-08-29
Building wise Construction details | [7 empty] | STILT + P1 & P2 + 1ST TO TO 11TH (PT) UPPER FLOOR
Approved area of building (Sq.Mt) |  |  | 6944.06
Approved no of units |  |  | Rehab Flats - 55, Sale Flats - 65
Approved no of Floors |  |  | Wing A = Gr + 2P + 1st to 11th + 12th (Pt) Floor Wing B & C = Gr + 2P + 1st to 11th Floor
Proposed no of Floors |  |  | Wing A = Gr + 2P + 1st to 11th + 12th (Pt) Floor
Wing B = Gr + 2P + 1st to 11th Floor
Wing C = Gr + 2P + 1st to 11th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Wing A = Gr + 2P + 1st to 11th + 12th (Pt) Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 100% |  | 100% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 100% |  |  |  |  | Plinth in process | 9
Possession |  | 12 | 100% |  |  |  |  | Plinth completed | 12
Construction details: |  | Wing B & C = Gr + 2P + 1st to 11th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 11 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 100% |  | 100% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 100% |  |  |  |  | Plinth in process | 8.25
Possession |  | 11 | 100% |  |  |  |  | Plinth completed | 11
Construction details: |  | Wing C = Gr + 2P + 1st to 11th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 7 Floor Completed | , Flooring upto 7 Floor, Painting upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 11 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 84.55% |  | 93.18% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 2.75
Brickwork |  | 11 | 100% |  |  |  |  | Footing Completed | 5.5
Internal Plaster |  | 11 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 11 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting |  | 7 | 63.64% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 63.64% |  |  |  |  | Basement 4 | 0
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 21500
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 50000
Society Formation Charges |  |  |  |  | 200000
Advance Maintenance Charges |  |  |  |  | 200000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 17200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Sale | 26 |  | 23969.0599 |  | 37152.0429
| Rehab | 20 |  | 14146.587 |  | 21927.2098
Wing B | Sale | 14 |  | 12633.4915 |  | 19581.9119
| Rehab | 17 |  | 12877.619 |  | 19960.3095
Wing C | Sale | 25 |  | 19410.5059 |  | 30086.2842
| Rehab | 18 |  | 14034.6414 |  | 21753.6942
Total Sale |  | 65 |  | 56013.0574 |  | 86820.2389
Total Rehab |  | 55 |  | 41058.8474 |  | 63641.2135
Total Flats |  | 120 |  | 97071.9048 |  | 150461.4524
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | RehabFlat/ Sale Flats | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
A Wing
Ground Floor For Entrance Lobby & Parking
1st Podium Floor For Entrance Lobby & Parking
2nd Podium Floor For Entrance Lobby & Amenities
1st Floor For Residential
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 1st Floor For Residential |  | 57.3075 | 10.764 | 28230333.768
2 | Rehab | 2BHK | 670.059 | 0 | 1038.5914 | 1st Floor For Residential |  |  |  | 29080560.6
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 1st Floor For Residential |  |  |  | 49813014.888
4 | Rehab | 2BHK | 651.222 | 0 | 1009.3941 | 1st Floor For Residential |  |  |  | 28263034.8
2nd Floor
1 | Sale | 2BHK | 650.4685 | 0 | 1008.2262 | 2nd Floor
2 | Rehab | 2BHK | 670.059 | 0 | 1038.5914 | 2nd Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 2nd Floor
4 | Rehab | 2BHK | 651.222 | 0 | 1009.3941 | 2nd Floor
3rd Floor
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 3rd Floor
2 | Rehab | 2BHK | 670.059 | 0 | 1038.5914 | 3rd Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 3rd Floor
4 | Rehab | 2BHK | 651.222 | 0 | 1009.3941 | 3rd Floor
4th Floor
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 4th Floor
2 | Rehab | 2BHK | 766.1815 | 0 | 1187.5814 | 4th Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 4th Floor
4 | Rehab | 2BHK | 651.222 | 0 | 1009.3941 | 4th Floor
5th Floor
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 5th Floor
2 | Rehab | 2BHK | 766.1815 | 0 | 1187.5814 | 5th Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 5th Floor
4 | Sale | 2BHK | 651.222 | 0 | 1009.3941 | 5th Floor
6th Floor (Part Refuge Area)
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 6th Floor (Part Refuge Area)
2 | Sale | 2BHK | 766.1815 | 0 | 1187.5814 | 6th Floor (Part Refuge Area)
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 6th Floor (Part Refuge Area)
4 | Refuge Area |  |  |  |  | 6th Floor (Part Refuge Area)
7th Floor
1 | Rehab | 2BHK | 650.4685 | 0 | 1008.2262 | 7th Floor
2 | Rehab | 2BHK | 766.1815 | 0 | 1187.5814 | 7th Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 7th Floor
4 | Rehab | 2BHK | 651.222 | 0 | 1009.3941 | 7th Floor
8th Floor
1 | Rehab | 2BHK | 764.9975 | 0 | 1185.7461 | 8th Floor
2 | Rehab | 2BHK | 766.1815 | 0 | 1187.5814 | 8th Floor
3 | Rehab | 3BHK | 1147.7653 | 0 | 1779.0362 | 8th Floor
4 | Sale | 2BHK | 743.3618 | 0 | 1152.2109 | 8th Floor
9th Floor
1 | Sale | 2BHK | 764.9975 | 0 | 1185.7461 | 9th Floor
2 | Sale | 2BHK | 766.1815 | 0 | 1187.5814 | 9th Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 9th Floor
4 | Sale | 2BHK | 743.3618 | 0 | 1152.2109 | 9th Floor
10th & 11th Floor
1 | Sale | 2BHK | 764.9975 | 0 | 1185.7461 | 10th & 11th Floor
2 | Sale | 2BHK | 766.1815 | 0 | 1187.5814 | 10th & 11th Floor
3 | Sale | 3BHK | 1147.7653 | 0 | 1779.0362 | 10th & 11th Floor
4 | Sale | 2BHK | 743.3618 | 0 | 1152.2109 | 10th & 11th Floor
12th Floor (Part Terrace Area)
1 | Sale | 2BHK | 764.9975 | 0 | 1185.7461 | 12th Floor (Part Terrace Area)
2 | Sale | 2BHK | 766.1815 | 0 | 1187.5814 | 12th Floor (Part Terrace Area)
3 | Sale | 3BHK | 1325.3713 | 0 | 2054.3255 | 12th Floor (Part Terrace Area)
4 | - | Part Terrace Area |  |  |  | 12th Floor (Part Terrace Area)
B Wing
Ground Floor For Entrance Lobby, Machine Room & Parking
1st Podium Floor For Drive Way & Parking
2nd Podium Floor For Entrance Lobby Double Height
1st Floor For Residential
1 | - | Entrance Lobby Double Height |  |  |  | 1st Floor For Residential |  | 57.3075 | 10.764
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 1st Floor For Residential
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 1st Floor For Residential
2nd Floor
1 | Rehab | 2BHK | 657.0346 | 0 | 1018.4036 | 2nd Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 2nd Floor
3 | Rehab | 3BHK | 1093.0842 | 0 | 1694.2805 | 2nd Floor
3rd Floor
1 | Rehab | 2BHK | 657.0346 | 0 | 1018.4036 | 3rd Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 3rd Floor
3 | Rehab | 3BHK | 1093.0842 | 0 | 1694.2805 | 3rd Floor
4th Floor
1 | Rehab | 2BHK | 657.0346 | 0 | 1018.4036 | 4th Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 4th Floor
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 4th Floor
5th Floor
1 | Rehab | 2BHK | 657.0346 | 0 | 1018.4036 | 5th Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 5th Floor
3 | Rehab | 3BHK | 1093.0842 | 0 | 1694.2805 | 5th Floor
6th Floor (Part Refuge Area)
1 | Refuge Area |  |  |  |  | 6th Floor (Part Refuge Area)
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 6th Floor (Part Refuge Area)
3 | Rehab | 3BHK | 1093.0842 | 0 | 1694.2805 | 6th Floor (Part Refuge Area)
7th Floor
1 | Sale | 2BHK | 657.0346 | 0 | 1018.4036 | 7th Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 7th Floor
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 7th Floor
8th Floor
1 | Rehab | 2BHK | 657.0346 | 0 | 1018.4036 | 8th Floor
2 | Rehab | 2BHK | 652.5137 | 0 | 1011.3962 | 8th Floor
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 8th Floor
9th Floor
1 | Sale | 2BHK | 716.8824 | 0 | 1111.1677 | 9th Floor
2 | Sale | 2BHK | 724.7401 | 0 | 1123.3472 | 9th Floor
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 9th Floor
10th & 11th Floor
1 | Sale | 2BHK | 716.8824 | 0 | 1111.1677 | 10th & 11th Floor
2 | Sale | 2BHK | 724.7401 | 0 | 1123.3472 | 10th & 11th Floor
3 | Sale | 3BHK | 1093.0842 | 0 | 1694.2805 | 10th & 11th Floor
C Wing
Ground Floor For Entrance Lobby & Parking
1st Podium Floor For Drive Way & Parking
2nd Podium Floor For Society Office, Filtration Plant, Sub Station & Balancing Tank
1st Floor For Residential
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 1st Floor For Residential |  |  | 10.764
2 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 1st Floor For Residential
3 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 1st Floor For Residential
4 | Rehab | 2BHK | 650.7914 | 0 | 1008.7267 | 1st Floor For Residential
2nd Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 2nd Floor
2 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 2nd Floor
3 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 2nd Floor
4 | Rehab | 2BHK | 650.7914 | 0 | 1008.7267 | 2nd Floor
3rd Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 3rd Floor
2 | Sale | 2.5BHK | 816.557 | 0 | 1265.6634 | 3rd Floor
3 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 3rd Floor
4 | Rehab | 2BHK | 650.7914 | 0 | 1008.7267 | 3rd Floor
4th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 4th Floor
2 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 4th Floor
3 | Rehab | 2.5BHK | 816.557 | 0 | 1265.6634 | 4th Floor
4 | Sale | 2BHK | 650.7914 | 0 | 1008.7267 | 4th Floor
5th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 5th Floor
2 | Rehab | 2.5BHK | 851.4324 | 0 | 1319.7202 | 5th Floor
3 | Rehab | 2.5BHK | 851.4324 | 0 | 1319.7202 | 5th Floor
4 | Rehab | 2BHK | 650.7914 | 0 | 1008.7267 | 5th Floor
6th Floor (Part Refuge Area)
1 | Refuge Area |  |  |  |  | 6th Floor (Part Refuge Area)
2 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 6th Floor (Part Refuge Area)
3 | Rehab | 2.5BHK | 887.1689 | 0 | 1375.1118 | 6th Floor (Part Refuge Area)
4 | Rehab | 2BHK | 650.7914 | 0 | 1008.7267 | 6th Floor (Part Refuge Area)
7th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 7th Floor
2 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 7th Floor
3 | Rehab | 2.5BHK | 887.1689 | 0 | 1375.1118 | 7th Floor
4 | Sale | 2BHK | 700.4135 | 0 | 1085.6409 | 7th Floor
8th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 8th Floor
2 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 8th Floor
3 | Rehab | 2.5BHK | 887.1689 | 0 | 1375.1118 | 8th Floor
4 | Sale | 2BHK | 700.4135 | 0 | 1085.6409 | 8th Floor
9th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 9th Floor
2 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 9th Floor
3 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 9th Floor
4 | Rehab | 2BHK | 700.4135 | 0 | 1085.6409 | 9th Floor
10th & 11th Floor
1 | Sale | 2BHK | 715.6984 | 0 | 1109.3325 | 10th & 11th Floor
2 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 10th & 11th Floor
3 | Sale | 2.5BHK | 887.1689 | 0 | 1375.1118 | 10th & 11th Floor
4 | Sale | 2BHK | 700.4135 | 0 | 1085.6409 | 10th & 11th Floor
Remarks:
* | All work Completed. OC Received.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved floor plan & layout plan (on 17/01/2023).
* | We have updated latest CC from MCGM site (On 12/07/2024).
* | We have updated OC (On 23/09/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Saujanya Rachanaa
Layout :
Google Map :
C Wing
A Wing
B Wing
C Wing
Saujanya Rachanaa
A Wing
B Wing
C Wing
B Wing
C
C Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted