## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 28/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-26
Name of the builder group |  |  |  | M/s.Rustagi Estates Private Limited
Name of the builder company |  |  |  | M/s.Rustagi Estates Private Limited
Name of the Project |  |  |  | Rusttagi Aarambha Phase I, II & III
Contact Details ( Name & Contact No.) |  |  |  | Mr. Rocky Punjabi 8788898425 / 818149313156
Name / No.of the Building |  |  |  | Building No.1 Building No.2 Building No.3 (Wing A & B) Building No.4 Building No.5 (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plan, Cost Sheet |  |  |  |  | Phase II = Bldg 1, 2 & 4
RERA No. |  |  |  | Phase - I P51700034204 Phase - II P51700034078 Phase - III P51700033998 |  |  |  |  | Phase III = Bldg No.3 & 5
Project location details |  | Rusttagi Aarambha Phase I, II & III, Survey No.77/4/C/78/2C, 77/4/78/2/A….83/1/P, near Ganesh Vidyalay, Internal Road, Titwala, Titwala (East), Kalyan, Thane - 421605.
Survey No |  | 77/4/C/78/2C, 77/4/78/2/A….83/1/P
Road |  | Internal Road |  | Locality/Village |  | Titwala
City |  | Titwala (East) |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421605
Nearby Landmark |  | Ganesh Vidyalay |  | Distance from city centre: |  | 3.9 KM from Titwala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Adj S. No.66 |  |  | Chawl
West | NA | Adj S. No.81 |  |  | Anand Home
North | NA | 24.00 M. Wide D.P Road |  |  | Internal Road
South | NA | Adj S. No.82 & 83 |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.295792,73.230689
Location Link |  | https://maps.app.goo.gl/RpkaYK87EqUrYx9q6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 23756.38
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.62746
Total FSI availaible for the project |  |  |  | 1.6275
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 38662.5
Total number of Buildings |  |  |  | 08 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing & Area Development Authority (MHADA)
Layout Approval No. |  | EE/BP/PMAYA/A/MHADA/171/2024 |  |  | Dated | 2024-02-28
Approved Floor plan No. |  | EE/BP/PMAYA/A/MHADA/170/2024 |  |  | Dated | 2024-02-28
Commencement-CC No Valid Up to: Building No.1 |  | EE/BP/PMAY/A/MHADA/191/2024 |  |  | Dated | 2024-03-06
|  | This amended CC is issued for work upto plinth level only. |  |  | Valid Upto Date | 2025-03-05
Commencement-CC No Valid Up to: Building No.2, 4 & 5 |  | EE/BP/PMAY/A/MHADA/023/2023 |  |  | Dated | 2023-01-10
Building No.2 & 5 = Gr/St + 1st to 10th Floor Building No.4 = Gr/St + 1st to 11th Floor
Commencement-CC No Valid Up to: Building No.2, 4 & 5 |  | EE/BP/PMAY/A/MHADA/177/2024 |  |  | Dated | 2024-02-28
Building No.2 & 5 = 10th to 12th Floor Building No.4 = 11th to 13th Floor
Commencement-CC No Valid Up to: Building No.3 |  | EE/BP/PMAY/A/MHADA/340/2023 |  |  | Dated | 2023-04-25
Building No.3 = Gr/Stilt + 1st to 10th Floor
Commencement-CC No Valid Up to: Building No.1 |  | EE/BP/PMAY/A/MHADA/350/2024 |  |  | Dated | 2024-05-16
Building No.1 = Further CC for Only Ground Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 38662.5
Approved No.of units |  |  | Flats - 679, Shops - 39
Approved No.of Floors |  |  | Phase I - Building No.2 = Shops Only Phase II - Building No.1 = 1st to 3rd Floor Building No.2 = Gr/St + 1st to 12th Floor Building No.4 = Gr/St + 1st to 13th Floor Phase III - Building No.3 (Wing A & B) = Gr/St + 1st to 10th Floor Building No.5 (Wing A & B) = Gr/St + 1st to 10th Floor |  |  |  |  | (Ground Floor)
Proposed No.of Floors |  |  | Building No.1 = 1st to 3rd Floor
Building No.2 = Gr/St + 1st to 12th Floor
Building No.3 (Wing A & B) = Gr/St + 1st to 10th Floor
Building No.4 = Gr/St + 1st to 13th Floor
Building No.5 (Wing A) = Gr/St + 1st to 12th Floor
Building No.5 (Wing B) = Gr/St + 1st to 12th Floor
Expected Completion |  |  | As per RERA - Phase I = 31/03/2026 Phase II = 22/02/2026 Phase III = 22/02/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 = 1st to 3rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 1 Floor Completed, External Plaster upto 2 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 1 Floor Completed, External Plaster upto 2 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 66.67% |  | 85% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% |  |  |  |  | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 1 | 33.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 66.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 2.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Construction details: |  | Building No.2 = Gr/St + 1st to 12th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 92.5% |  | 95% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 50% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Building No.3 (Wing A & B) = Gr/St + 1st to 10th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 90% |  | 95% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 7.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 10
Construction details: |  | Building No.3 (Wing B) = Gr/St + 1st to 10th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 9 Floor Completed, Painting upto 8 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 9 Floor Completed, Painting upto 8 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 88% |  | 94.5% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 90% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 80% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 7.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 10
Construction details: |  | Building No.4 = Gr/St + 1st to 13th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 12 Floor Completed, Painting upto 12 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 12 Floor Completed, Painting upto 12 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 88.85% |  | 94.62% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 92.31% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 92.31% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | Building No.5 (Wing A & B) = Gr/St + 1st to 12th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring Completed, Painting upto 11 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring Completed, Painting upto 11 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 89.58% |  | 95% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 91.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Building No.5 (Wing B) = Gr/St + 1st to 12th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 11 Floor Completed, Painting upto 11 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 11 Floor Completed, Painting upto 11 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 88.75% |  | 94.58% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 91.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 91.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  | 3200 to 3500 & charges | 2023-06-27 | rushikesh | cost sheet
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 11200 |  |  | 6500 to 11200 | 2022-10-20 | Abhishek | Costsheet
Recommended rate of the Office Per Sq. Ft. | [9 empty] | Abhishek
Floor Rise Rate | [9 empty] | Abhishek
Development Charges (Only for 2BHK) |  |  |  |  | 300000 |  |  | Development Charges | 2022-10-04 | Abhishek | 125000 to 200000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000 |  |  | Loading taken as 40% to adjust extra Area on 14/06/2024
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase II (Building No.1) Wing A & B |  | 3 |  | 30144.582 |  | 46724.1021
Phase I (Building No.2) |  | 18 |  | 2422.5458 |  | 3754.9461
Phase III (Building No.3) Wing A |  | 6 |  | 991.5797 |  | 1536.9485
Phase III (Building No.5) Wing A & B |  | 12 |  | 1983.1594 |  | 3073.897
Total |  | 39 |  | 35541.8669 |  | 55089.8937
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase II (Building No.2) |  | 141 |  | 55897.7749 |  | 78453.5432 |  | 141
Phase II (Building No.4) |  | 153 |  | 61379.6648 |  | 85931.5308
Phase III (Building No.3) Wing A |  | 118 |  | 47296.5854 |  | 66215.2196
Phase III (Building No.3) Wing B |  | 79 |  | 31582.2218 |  | 44215.1106
Phase III (Building No.5) (Wing A) |  | 94 |  | 37710.3823 |  | 52794.5352
Phase III (Building No.5) (Wing B) |  | 94 |  | 37710.3823 |  | 52794.5352
Total |  | 679 |  | 271577.0117 |  | 380404.4746
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Phase I
Building No.2
Ground Floor for Commercial, Society Office, Meter Room, Pump Room & Double Heighted Lobby
1 |  | Shop | 134.55 | 0 | 208.5525 | Ground Floor for Commercial, Society Office, Meter Room, Pump Room & Double Heighted Lobby |  | 12.1
2 |  | Shop | 98.1677 | 0 | 152.1599 |  |  | 8.8766
3 |  | Shop | 171.04 | 0 | 265.1119
4 |  | Shop | 171.04 | 0 | 265.1119
5 |  | Shop | 98.1677 | 0 | 152.1599
6 |  | Shop | 134.55 | 0 | 208.5525
7 |  | Shop | 134.55 | 0 | 208.5525
8 |  | Shop | 98.1677 | 0 | 152.1599
9 |  | Shop | 171.04 | 0 | 265.1119
10 |  | Shop | 171.04 | 0 | 265.1119
11 |  | Shop | 98.1677 | 0 | 152.1599
12 |  | Shop | 134.55 | 0 | 208.5525
13 |  | Shop | 134.55 | 0 | 208.5525
14 |  | Shop | 98.1677 | 0 | 152.1599
15 |  | Shop | 171.04 | 0 | 265.1119
16 |  | Shop | 171.04 | 0 | 265.1119
17 |  | Shop | 98.1677 | 0 | 152.1599
18 |  | Shop | 134.55 | 0 | 208.5525
Phase II
Building No.1
Ground Floor for Meter Room, Entrance Lobby & Commercial
Ground Floor + 1st for Duplex Shop
1 |  | Duplex Shop | 18895.9867 | 0 | 29288.7794 | Ground Floor + 1st for Duplex Shop
2nd Floor for Commercial
1 |  | Shop | 10422.8888 | 0 | 16155.4777 | 2nd Floor for Commercial
3rd Floor for Commercial
1 |  | Shop | 825.7064 | 0 | 1279.845 | 3rd Floor for Commercial
Building No.2
Ground Floor for Commercial, Society Office, Meter Room, Pump Room, Double Heighted Lobby & Parking
1 |  | Shop | 134.55 | 0 | 208.5525 | Ground Floor for Commercial, Society Office, Meter Room, Pump Room, Double Heighted Lobby & Parking
2 |  | Shop | 98.1677 | 0 | 152.1599
3 |  | Shop | 171.04 | 0 | 265.1119
4 |  | Shop | 171.04 | 0 | 265.1119
5 |  | Shop | 98.1677 | 0 | 152.1599
6 |  | Shop | 134.55 | 0 | 208.5525
7 |  | Shop | 134.55 | 0 | 208.5525
8 |  | Shop | 98.1677 | 0 | 152.1599
9 |  | Shop | 171.04 | 0 | 265.1119
10 |  | Shop | 171.04 | 0 | 265.1119
11 |  | Shop | 98.1677 | 0 | 152.1599
12 |  | Shop | 134.55 | 0 | 208.5525
13 |  | Shop | 134.55 | 0 | 208.5525
14 |  | Shop | 98.1677 | 0 | 152.1599
15 |  | Shop | 171.04 | 0 | 265.1119
16 |  | Shop | 171.04 | 0 | 265.1119
17 |  | Shop | 98.1677 | 0 | 152.1599
18 |  | Shop | 134.55 | 0 | 208.5525
Phase III
Building No.3 (Wing A)
Ground Floor for Commercial, Society Office, Meter Room, Pump Room & Double Heighted Lobby
1 |  | Shop | 189.7693 | 0 | 294.1424 | Ground Floor for Commercial, Society Office, Meter Room, Pump Room & Double Heighted Lobby
2 |  | Shop | 145.2064 | 0 | 225.0699
3 |  | Shop | 186.5401 | 0 | 289.1372
4 |  | Shop | 138.2098 | 0 | 214.2251
5 |  | Shop | 145.314 | 0 | 225.2367
6 |  | Shop | 186.5401 | 0 | 289.1372
Building No.5
Wing A
Lower Stilt for Parking & Entrance Lobby
Upper Stilt for Parking, Society Office, Meter Room & Commercial
1 |  | Shop | 189.7693 | 0 | 294.1424 | Upper Stilt for Parking, Society Office, Meter Room & Commercial
2 |  | Shop | 145.2064 | 0 | 225.0699
3 |  | Shop | 186.5401 | 0 | 289.1372
4 |  | Shop | 138.2098 | 0 | 214.2251
5 |  | Shop | 145.2064 | 0 | 225.0699
6 |  | Shop | 186.5401 | 0 | 289.1372
Wing B
Lower Stilt for Parking & Entrance Lobby
Upper Stilt for Parking, Society Office, Meter Room & Commercial
1 |  | Shop | 189.7693 | 0 | 294.1424 | Upper Stilt for Parking, Society Office, Meter Room & Commercial
2 |  | Shop | 145.2064 | 0 | 225.0699
3 |  | Shop | 186.7554 | 0 | 289.4709
4 |  | Shop | 138.2098 | 0 | 214.2251
5 |  | Shop | 145.2064 | 0 | 225.0699
6 |  | Shop | 186.5401 | 0 | 289.1372
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
40%
Phase II | [7 empty] | 10.764
Building No.2
1st Floor For Residential & Part Double Height Entrance Lobby
1 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897 | 1st Floor For Residential & Part Double Height Entrance Lobby |  | 2667.6205
2 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897 |  |  | 27.1622
3 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897
4 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897
5 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897
6 | EWS | 1BHK | 396.4381 | 32.7764 | 587.7897 |  |  | Double Heighted Lobby
7 | EWS | 1BHK | 396.4381 | 0 | 555.0134
8 | EWS | 1BHK | 396.4381 | 0 | 555.0134
9 | EWS | 1BHK | 396.4381 | 0 | 555.0134
10 | EWS | Double Heighted Entrance Lobby
11 | EWS | 1BHK | 396.4381 | 0 | 555.0134
12 | EWS | 1BHK | 396.4381 | 0 | 555.0134
2nd to 7th, 9th to 12th Floor For Residential
1 | EWS | 1BHK | 396.4381 | 0 | 555.0134 | 2nd to 7th, 9th to 12th Floor For Residential
2 | EWS | 1BHK | 396.4381 | 0 | 555.0134
3 | EWS | 1BHK | 396.4381 | 0 | 555.0134
4 | EWS | 1BHK | 396.4381 | 0 | 555.0134
5 | EWS | 1BHK | 396.4381 | 0 | 555.0134
6 | EWS | 1BHK | 396.4381 | 0 | 555.0134
7 | EWS | 1BHK | 396.4381 | 0 | 555.0134
8 | EWS | 1BHK | 396.4381 | 0 | 555.0134
9 | EWS | 1BHK | 396.4381 | 0 | 555.0134
10 | EWS | 1BHK | 396.4381 | 0 | 555.0134
11 | EWS | 1BHK | 396.4381 | 0 | 555.0134
12 | EWS | 1BHK | 396.4381 | 0 | 555.0134
8th Floor (Part Refuge & Garden Area)
1 | EWS | 1BHK | 396.4381 | 0 | 555.0134 | 8th Floor (Part Refuge & Garden Area)
2 | EWS | 1BHK | 396.4381 | 0 | 555.0134
3 | EWS | 1BHK | 396.4381 | 0 | 555.0134
4 | EWS | 1BHK | 396.4381 | 0 | 555.0134
5 | EWS | 1BHK | 396.4381 | 0 | 555.0134
6 | EWS | 1BHK | 396.4381 | 0 | 555.0134
7 | EWS | 1BHK | 396.4381 | 0 | 555.0134
8 | EWS | 1BHK | 396.4381 | 0 | 555.0134
9 | EWS | Refuge Area
10 | EWS | Refuge with Garden Area
11 | EWS | 1BHK | 396.4381 | 0 | 555.0134
12 | EWS | 1BHK | 396.4381 | 0 | 555.0134
Building No.4
Lower Stilt for Parking & Entrance Lobby
Upper Stilt for Parking & Society Office
1st to 6th & 9th to 11th & 13th Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 1st to 6th & 9th to 11th & 13th Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | 1BHK | 401.1743 | 0 | 561.644
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
7th Floor (Part Refuge Area)
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 7th Floor (Part Refuge Area)
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | Refuge Area
11 | EWS | Garden
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
8th Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 8th Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | 1BHK | 401.1743 | 0 | 561.644
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
12th Floor (Part Refuge Area)
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 12th Floor (Part Refuge Area)
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | Refuge Area / Garden
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
Phase III
Building No.3
Wing A
1st Floor for Residential
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 1st Floor for Residential
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | 1BHK | 401.1743 | 0 | 561.644
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
2nd to 7th & 9th to 10th Floor for Residential
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 2nd to 7th & 9th to 10th Floor for Residential
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | 1BHK | 401.1743 | 0 | 561.644
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
8th Floor (Part Refuge Area)
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 8th Floor (Part Refuge Area)
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 |  | Refuge Area
5 |  | Garden
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
9 | EWS | 1BHK | 401.1743 | 0 | 561.644
10 | EWS | 1BHK | 401.1743 | 0 | 561.644
11 | EWS | 1BHK | 401.1743 | 0 | 561.644
12 | EWS | 1BHK | 401.1743 | 0 | 561.644
Wing B
Ground Floor for Society Office, Meter Room, Pump Room & Double Heighted Lobby
1st Floor for Residential
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 1st Floor for Residential
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 | EWS | 1BHK | 399.775 | 0 | 559.6849
5 | EWS | 1BHK | 399.775 | 0 | 559.6849
6 | EWS | 1BHK | 399.775 | 0 | 559.6849
7 | EWS | 1BHK | 399.775 | 0 | 559.6849
8 | EWS | 1BHK | 399.775 | 0 | 559.6849
2nd to 7th & 9th to 10th Floor for Residential
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 2nd to 7th & 9th to 10th Floor for Residential
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 | EWS | 1BHK | 399.775 | 0 | 559.6849
5 | EWS | 1BHK | 399.775 | 0 | 559.6849
6 | EWS | 1BHK | 399.775 | 0 | 559.6849
7 | EWS | 1BHK | 399.775 | 0 | 559.6849
8 | EWS | 1BHK | 399.775 | 0 | 559.6849
8th Floor (Part Refuge Area)
1 | EWS | 1BHK | 399.775 | 0 | 559.6849 | 8th Floor (Part Refuge Area)
2 | EWS | 1BHK | 399.775 | 0 | 559.6849
3 | EWS | 1BHK | 399.775 | 0 | 559.6849
4 |  | Refuge Area
5 | EWS | 1BHK | 399.775 | 0 | 559.6849
6 | EWS | 1BHK | 399.775 | 0 | 559.6849
7 | EWS | 1BHK | 399.775 | 0 | 559.6849
8 | EWS | 1BHK | 399.775 | 0 | 559.6849
Building No.5
Wing A
1st Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 1st Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
2nd to 6th & 8th to 11th Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 2nd to 6th & 8th to 11th Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
7th & 12th Floor (Part Refuge Area)
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 7th & 12th Floor (Part Refuge Area)
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 |  | Refuge Area / Garden
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
Wing B
1st Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 1st Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
2nd to 6th & 8th to 11th Floor for Residential
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 2nd to 6th & 8th to 11th Floor for Residential
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 | EWS | 1BHK | 401.1743 | 0 | 561.644
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
7th & 12th Floor (Part Refuge Area)
1 | EWS | 1BHK | 401.1743 | 0 | 561.644 | 7th & 12th Floor (Part Refuge Area)
2 | EWS | 1BHK | 401.1743 | 0 | 561.644
3 | EWS | 1BHK | 401.1743 | 0 | 561.644
4 | EWS | 1BHK | 401.1743 | 0 | 561.644
5 | EWS | 1BHK | 401.1743 | 0 | 561.644
6 | EWS | 1BHK | 401.1743 | 0 | 561.644
7 |  | Refuge Area / Garden
8 | EWS | 1BHK | 401.1743 | 0 | 561.644
Remarks:
* | Building No.1 to 5 = Construction work is in process at the time of visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Encl Balcony + Serv. Slab Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Rocky : 8788898425 & Variya : 9284560995.
* | We have updated Approved Plans & Latest CC (On 14/06/2024).
* | Building No. 1 plans are completely revised and structure is reduced to Gr. + 1st to 3rd Floor Commercial Building (Previous approved structure Gr. + 1st to 11th Floor).
* | We have updated approved floor plans of Phase I & Phase II (Building No.2) On 23/12/2024.
* | Construction work of Building No. 2 & 5 goes beyond approved no. of floor. Please Provide revised Approved Plans.
* | As per RERA, completion period of project Rustaagi Aarambha Phase I is expired on 21/02/2025 but still project is under construction.
* | We have updated revised CC for Building no.1 (On 28/09/2025). Construction work of Building No.1 goes beyond CC permission. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have No.direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Rusttagi Aarambha Phase I, II & III
Layout :
Google Map :
Formulas:
Titwala = [Titwala, row above]
4
2
3A
3B
4
5B
5B
3A
1st Flr
13th Flr
BUILDING 1 ADDED IN PHASE II
SO PHASE II LAND AREA = 7346.52 SQM
BLUILDING NO. 1 REMOVED FROM PHASE 1
SO PHASE 1 LAND AREA = 2290 SQM
BUILDING 6 ADDED IN PHASE III
SO PHASE III LAND AREA = 11348 SQM
1
4
3A
6
2
5B
5A
3B
Bldg 1
Bldg 5
B Wing
A Wing
Bldg 1
Bldg 4

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted