## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 26/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-26
Name of the builder group |  |  |  | Millennium Group
Name of the builder company |  |  |  | Millennium Group
Name of the Project |  |  |  | Millennium Urbania
Contact Details ( Name & Contact No.) |  |  |  | 9322917679
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000045626
Project location details |  | Millennium Urbania, Plot No.17C, Sector - 16E, near Verona CHS Apartment, Roadpali Road, Kalamboli, Kalamboli, Kalamboli, Panvel, Raigad - 410218.
Plot No |  | 17C, Sector - 16E
Locality |  | Kalamboli
Road |  | Roadpali Road |  | Village |  | Kalamboli
City |  | Kalamboli |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410218
Nearby Landmark |  | Verona CHS Apartment |  | Distance from city centre: |  | 5.4 KM from Mansarovar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Cake road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Roadpali Road
South | NA | NA |  |  | Verona CHS Apartment
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.0439 |  | Longitude |  | 73.1011
Location Link |  | https://goo.gl/maps/nnwcUrqeLeorfEkd9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2022.58 |  |  |  |  | 1.5
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.729
Total FSI availaible for the project |  |  |  | 3.229
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6530.843 |  |  |  |  | 3.229
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/16279/JK-923/2023 |  |  | Dated | 2023-03-31
Approved Floor plan No. |  | PMP/NRV/16279/JK-923/2023 |  |  | Dated | 2023-03-31
Commencement-CC No Valid Up to: |  | PMC/TP/Kalamboli/16E/17C/21-23/16279/923/2023 |  |  | Dated | 2023-03-31
Gr/Stilt + 1st to 4th Floor (Podium) + 5th to 17th Floor (For Flats = 91 & Commercial Unit = 21)
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 6530.843
Approved no of units |  |  | Flats - 91, Shops - 21
Approved no of Floors |  |  | Gr/Stilt + 1st to 4th Floor (Podium) + 5th to 17th Floor
Proposed no of Floors |  |  | Gr/Stilt + 1st to 4th Floor (Podium) + 5th to 17th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/Stilt + 1st to 4th Floor (Podium) + 5th to 17th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 15 Floor, External Plaster upto 10 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed | , RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 15 Floor, External Plaster upto 10 Floor, Flooring upto 3 Floor, Painting upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 17 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 15 Floor, External Plaster upto 10 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.25
Excavation |  | 17 | 100% | 69.69% |  | 86.27% |  | Excavation in process | 8.5
Plinth |  | 17 | 100% |  |  |  |  | Excavation Completed | 17
RCC (Including podiums) |  | 17 | 94.44% |  |  |  |  | Footing in Process | 4.25
Brickwork | Brickwork & Internal Plaster | 16 | 94.12% |  |  |  |  | Footing Completed | 8.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 88.24% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 58.82% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 17.65% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 11.76% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 17
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 8500 |  |  | 8200 to 8400 & OC Charges |  | smith | 2024-03-11
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 17000 |  |  | 8400 to 8500 & FR + CAR PARK 5L BY smith on 24/07/2024
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate (From 6th Floor) (Only For 2BHK) |  |  |  |  | 40 |  |  | FR n 1406 area changed by Smith on 24/07/2024
Development Charges |  |  |  |  | 150000 |  |  | 234500 | #DIV/0!
Club Membership |  |  |  |  | 100000
Infrastructure Charges (Only For 2BHK) |  |  |  |  | 200000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000 |  |  | 67000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 500000
Distressed valuation of the Property |  |  |  |  | 6800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | rate sheet
Shops |  | 21 |  | 6742.6557 |  | 10451.1164 |  |  | cost sheet | visitor | Market
Residential Area Details : | [7 empty] | flat | 9000 | 6250 | 8800
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | shop | 20000
Flats |  | 91 |  | 48437.1604 |  | 73503.9169
Grand Total |  | 112 |  | 55179.8161 |  | 83955.0333
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
[5 empty] | 55% |  |  |  | 10.764
Ground Floor for Commercial & Parking
1 |  | Shop | 393.2197 | 0 | 609.4905 | Ground Floor for Commercial & Parking |  | 36.5317
2 |  | Shop | 403.4993 | 0 | 625.4239
3 |  | Shop | 421.755 | 0 | 653.7203
4 |  | Shop | 411.949 | 0 | 638.521
5 |  | Shop | 433.8861 | 0 | 672.5234
6 |  | Shop | 441.9483 | 0 | 685.0199
7 |  | Shop | 454.7037 | 0 | 704.7907
8 |  | Shop | 464.9833 | 0 | 720.7241
9 |  | Shop | 473.7559 | 0 | 734.3217
10 |  | Shop | 334.1899 | 0 | 517.9944
11 |  | Shop | 346.4393 | 0 | 536.981
12 |  | Shop | 286.5592 | 0 | 444.1668
13 |  | Shop | 283.3515 | 0 | 439.1949
14 |  | Shop | 275.1601 | 0 | 426.4982
15 |  | Shop | 241.964 | 0 | 375.0441
16 |  | Shop | 220.9526 | 0 | 342.4766
17 |  | Shop | 181.9439 | 0 | 282.013
18 |  | Shop | 87.2207 | 0 | 135.1921
19 |  | Shop | 80.8807 | 0 | 125.3651
20 |  | Shop | 260.1336 | 0 | 403.2071
21 |  | Shop | 244.1598 | 0 | 378.4477
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
1st to 3rd Floor for Parking
4th Floor for Garden & Club House
5th to 13th Floor for Residential (Part Refuge Area at Midlanding @ 7th & 12th Floor)
1 |  | 1 | 446.8782 | 0 | 670.3173 | 5th to 13th Floor for Residential (Part Refuge Area at Midlanding @ 7th & 12th Floor) |  | 39.6645 | 8503.4352
2 |  | 1 | 423.8164 | 0 | 635.7245 |  |  | 8966.1476 | 99A | 8808.8468 | dewello
3 |  | 1 | 423.8164 | 0 | 635.7245
4 |  | 2 | 661.211 | 0 | 991.8165 |  |  | 8650.7939 | 8650.7939 | 99A
5 |  | 2 | 678.3365 | 0 | 1017.5048
6 |  | 3 | 857.0189 | 0 | 1285.5284 |  |  | 9023.527 | 9023.527 | 99A
7 |  | 1 | 455.7854 | 0 | 683.6782
14th Floor
1 |  | 1 | 446.8782 | 0 | 670.3173 | 14th Floor |  | 39.6645 | 8503.4352
2 |  | 1 | 423.8164 | 0 | 635.7245 |  |  | 8966.1476 | 99A | 8808.8468 | dewello
3 |  | 1 | 423.8164 | 0 | 635.7245
4 |  | 2 | 661.211 | 0 | 991.8165 |  |  | 8650.7939 | 8650.7939 | 99A
5 |  | 2 | 678.3365 | 0 | 1017.5048
6 |  | 3 | 857.0189 | 0 | 1327 |  |  | FR n 1406 area changed by Smith on 24/07/2024
7 |  | 1 | 455.7854 | 0 | 683.6782
15th Floor | [8 empty] | 10.764 |  | 614.5337
1501 |  | 1 | 446.8782 | 0 | 670.3173 | 15th Floor |  |  |  | 50% | 45%
1502 |  | 1 | 423.8164 | 0 | 635.7245 |  |  |  |  | 5212941.1542 | 5039176.4491
1503 |  | 1 | 423.8164 | 0 | 635.7245 |  |  |  |  | 5659941.1542 | 5486176.4491
1504 |  | 2 | 661.211 | 0 | 991.8165
1505 |  | 2 | 678.3365 | 0 | 1017.5048
1506 |  | 2 | 696.6784 | 147.3592 | 1118.6971
1507 |  | 1 | 455.7854 | 0 | 683.6782
16th Floor
1601 |  | 1 | 446.8782 | 0 | 670.3173 | 16th Floor
1602 |  | 1 | 423.8164 | 0 | 635.7245
1603 |  | 1 | 423.8164 | 0 | 635.7245
1604 |  | 1 | 456.033 | 182.5574 | 775.3282
1605 |  | 1 | 512.0381 | 144.8834 | 840.4989
1606 |  | 1 | 505.2945 | 155.0016 | 835.4425
1607 |  | 1 | 455.7854 | 0 | 683.6782
17th Floor (Part Refuge Area at Midlanding)
1701 |  | 0 | 284.0404 | 149.6196 | 500.8704 | 17th Floor (Part Refuge Area at Midlanding)
1702 |  | 0 | 268.7017 | 139.1247 | 472.6149
1703 |  | 0 | 268.7017 | 149.6196 | 477.8624
1704 |  | 0 | 262.3456 | 144.4529 | 465.7448
1705 |  | 0 | 279.1374 | 196.6583 | 517.0353
1706 |  | 0 | 317.312 | 135.3035 | 543.6197
1707 |  | 0 | 278.1095 | 151.7724 | 493.0504
Remarks: | [11 empty] | Construction work is the same as last visit (dtd.11/11/2024), but work is in process at the time of the visit. (Slow Speed)
* | Construction work is in process at the time of visit (Labour found). | [6 empty] | Construction work has incresed as compare to last visited date 17/08/2024 but at the time of visit no labour or no active work found on site.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Truck Terminal is adjacent to the project.
* | The Hindu crematorium is on West side of project @90m.
* | We have updated Approved layout plan, floor plan & CC (on 26/12/2023).
* | Recommended Rates/Other Charges of the Property have been revised on 26/12/2023, 11/03/2024 & 24/07/2024.
* | On site we met Ambekar : 7400377747.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Millennium Urbania
Google Map :
Formulas:
Kalamboli = [Kalamboli, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
FR n 1406 area changed by Smith on 24/07/2024