## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 26/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-26
Name of the builder group |  |  |  | M/s. Patidar Developers
Name of the builder company |  |  |  | M/s. Patidar Developers
Name of the Project |  |  |  | Umiya Residency
Contect Details ( Name & Contect No.) |  |  |  | 9323390390
Name / No of the Building |  |  |  | Building No. 1, 2 & 3
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51700007983
Project location details |  | Umiya Residency, Survey No.73 & Hissa No. 50 & 55, Internal Road, Baliyani, Titwala, Kalyan, Thane.
Survey No |  | 73 & Hissa No. 50 & 55
Road |  | Internal Road |  | Locality/Village |  | Baliyani
City |  | Titwala |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421605
Near by Landmark |  | Chistiya Sunni Masjid |  | Distance from city centre: |  | 2.2Km from Titwala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Building
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.278937,73.1995901
Location Link |  | https://goo.gl/maps/io7QsuvE7g24aPfV6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2844
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.82438
Total FSI availaible for the project |  |  |  | 1.9244
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5472.95
Total number of Buildings |  |  |  | 3 Buildings
Approval Detail : Plan approval
Layout Approval No |  | KDMC/TPD/BP/KD/2017-18/06/227 |  |  | Dated | 2023-10-17
Approved Floor plan No. Building No. 2 & 3 |  | KDMC/TPD/BP/KD/2017-18/06/387 |  |  | Dated | 2021-12-09
Approved Floor plan No. Building No. 1 |  | KDMC/TPD/BP/KD/2017-18/06/227 |  |  | Dated | 2023-10-17
Commencement Certificate No. Valid Up to: |  | KDMP/NRV/BP/KV/2017-18/06 |  |  | Dated | 2017-04-19
Building No. 2 = G/St + 1st to 4th Floor
Commencement Certificate No. Valid Up to: |  | KDMC/TPD/BP/KD/2017-18/06/387 |  |  | Dated | 2021-12-09
Building No. 3 = G/St + 1st to 7th Floor
Commencement Certificate No. Valid Up to: |  | KDMC/TPD/BP/KD/2017-18/06/227 |  |  | Dated | 2023-10-17
Building No. 1 = G/St + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5472.95
Approved no of units |  |  | Flats - 141
Approved no of Floors |  |  | Building No. 1 = G/St + 1st to 7th Floor Building No. 2 = G/St + 1st to 4th Floor Building No. 3 = G/St + 1st to 7th Floor
Proposed no of Floors |  |  | Building No. 1 & 3 = G/St + 1st to 7th Floor Building No. 2 = G/St + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.2 = Gr + 4th Floor Building No.3 = Gr + 7th Floor | [5 empty] | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Construction details: |  | Building No.1 = Gr + 7th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 6 Floor Completed, Painting upto 6 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 6 Floor Completed, Painting upto 6 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 87.86% |  | 94.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3900 |  |  | 3500 to 3700 | Rushikesh | 2023-02-28
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 200000 |  |  | 3700 to 3900 | sanket | 2023-04-19
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | 10000
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges (For 2years) |  |  |  |  | 25000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3120
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No. 1 |  | 54 | 23534.9101 |  | 34125.6197
Building No. 2 |  | 55 | 15389.829 |  | 22315.252
Building No. 3 |  | 32 | 10228.8139 |  | 15539.6208
Total |  | 141 | 49153.553 |  | 71980.4926
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Building No. 1
Ground Floor for Residential & Parking
1 |  | 1BHK | 411.9706 | 0 | 597.3573 | Ground Floor |  | 1.45
2 |  | 1BHK | 359.27 | 0 | 520.9415
3 |  | 1RK | 273.2872 | 0 | 396.2664
4 |  | 1.5BHK | 446.5876 | 0 | 647.552
5 |  | 1BHK | 360.1096 | 0 | 522.1589
1st to 7th Floor for Residential
1 |  | 1BHK | 477.5772 | 0 | 692.4869 | 1st to 7th Floor for Residential
2 |  | 1BHK | 449.9567 | 0 | 652.4373
3 |  | 1RK | 322.5863 | 0 | 467.7502
4 |  | 1.5BHK | 556.1113 | 0 | 806.3614
5 |  | 1BHK | 413.0416 | 0 | 598.9103
6 |  | 1BHK | 452.5724 | 0 | 656.23
7 |  | 1BHK | 425.8238 | 0 | 617.4446
Building No. 2
Ground Floor for Residential
1 |  | 1RK | 250.9088 | 0 | 363.8178 | Ground Floor for Residential |  | 272.0332
2 |  | 1RK | 273.1903 | 0 | 396.126
3 |  | 1RK | 273.1903 | 0 | 396.126
4 |  | 1BHK | 283.6314 | 0 | 411.2655
5 |  | 1RK | 248.6484 | 0 | 360.5402
6 |  | 1BHK | 271.2528 | 0 | 393.3166
7 |  | 1BHK | 273.1903 | 0 | 396.126
8 |  | 1RK | 246.8185 | 0 | 357.8869
9 |  | 1RK | 245.8498 | 0 | 356.4822 |  |  | 22.8538
10 |  | 1RK | 239.499 | 0 | 347.2736 |  |  | 4319.3615
11 |  | 1BHK | 272.2216 | 0 | 394.7213
1st to 4th Floor for Residential
1 |  | 1RK | 273.1096 | 0 | 396.0089 | 1st to 4th Floor for Residential
2 |  | 1RK | 295.3911 | 0 | 428.3171
3 |  | 1RK | 295.3911 | 0 | 428.3171
4 |  | 1BHK | 305.8322 | 0 | 443.4566
5 |  | 1RK | 270.8492 | 0 | 392.7313
6 |  | 1BHK | 288.6097 | 0 | 418.4841
7 |  | 1BHK | 290.5473 | 0 | 421.2935
8 |  | 1RK | 269.0193 | 0 | 390.0779
9 |  | 1RK | 268.0505 | 0 | 388.6732
10 |  | 1RK | 256.856 | 0 | 372.4411
11 |  | 1BHK | 314.2012 | 0 | 455.5917
Building No. 3
Ground Floor for Residential
1 |  | 1BHK | 367.1331 | 0 | 532.343 | Ground Floor for Residential |  | 307.323
2 |  | 1RK | 233.0406 | 0 | 337.9089
3 |  | 1RK | 233.7941 | 0 | 339.0014
4 |  | 1BHK | 367.1331 | 0 | 532.343
1st & 3rd Floor for Residential
1 |  | 1BHK | 367.0524 | 46.8234 | 579.0494 | 1st & 3rd Floor for Residential
2 |  | 1RK | 259.6815 | 41.6567 | 418.1949
3 |  | 1RK | 260.435 | 41.6567 | 419.2874
4 |  | 1BHK | 369.6358 | 46.8234 | 582.7953
2nd & 4th Floor
1 |  | 1BHK | 389.3339 | 0 | 564.5341 | 2nd & 4th Floor
2 |  | 1RK | 277.0385 | 0 | 401.7058
3 |  | 1RK | 277.7919 | 0 | 402.7983
4 |  | 1BHK | 389.3339 | 0 | 564.5341
5th & 7th Floor
1 |  | 1BHK | 367.0524 | 46.8234 | 579.0494 | 5th & 7th Floor
2 |  | 1RK | 259.6815 | 41.6567 | 418.1949
3 |  | 1RK | 260.435 | 41.6567 | 419.2874
4 |  | 1BHK | 369.6358 | 46.8234 | 582.7953
6th Floor
1 |  | 1BHK | 389.3339 | 0 | 564.5341 | 6th Floor
2 |  | 1RK | 277.0385 | 0 | 401.7058
3 |  | 1RK | 277.7919 | 0 | 402.7983
4 |  | 1BHK | 389.3339 | 0 | 564.5341
Remarks:
1. Building No. 1 = Construction work is in process at the time of Visit. Building No. 2 & 3 = All work completed. Provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised approved floor plan & C.C. (on 19/04/2022). 8. We have updated revised approved floor plan & C.C of Wing A. (on 17/04/2024). 9. As checked on RERA portal on date 26/09/2025, we have observed that above project "Umiya Residency" is kept under abeyance. Please check from your end. 9. On Site, we meet Sales person 9323390390. 7. On Site, we meet Mr.Nagesh (Supervisor) - 9920477956.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Umiya Residency
Google Map :
Bldg No. 1
Bldg No. 1

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Suraj Palette - 500m | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick | Mangrish Apartment sea side - 1.1KM | 4BHK | 2274 | 3638.4 | 32981.5303 | 120000000
Magic Brick | Suraj Palette - 500m | 3BHK | 1466 | 2345.6 | 32528.9905 | 76300000
Magic Brick | Mangrish Apartment sea side - 1.1KM | 4BHK | 2275 | 3640 | 32554.9451 | 118500000
Magic Brick | Suvidha Emerald - 1.1KM | 4BHK | 2700 | 4320 | 32175.9259 | 139000000
99 Acres | Suraj Palette - 500m | 3BHK | 1466 | 2345.6 | 32997.9536 | 77400000
99 Acres | Kings Krest - 350m | 4BHK | 1725 | 2760 | 31268.1159 | 86300000
Average |  |  |  |  | 32291.4302
Valuation Adopted |  |  |  |  | 32000