## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-25
Branch Name/ID |  | Mahindra Rural Housing Finance - Thane |  |  | Date & Time of Site Visit | 26/09/2025 at 04:37PM
Name of the person met at site & Contact No |  | Ms Vaidehi 7020283967 |  |  | Date of Report Release | 29/09/2025
Project Details
Name of the project |  | L M Tower
Address |  | L M Tower, CTS No.110/8/B/2 & 110/12/1, near Landmark residency, Bhiwandi Murbad Road, Temghar, Bhiwandi, Bhiwandi, Thane - 421302. | [10 empty] | Thane | Palghar | Mumbai | Raigad | Pune
CTS No |  | 110/8/B/2 & 110/12/1 | [10 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Temghar | [10 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Bhiwandi Murbad Road | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Bhiwandi | [10 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Bhiwandi | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421302 | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700027947 | [13 empty] | Mahad | Daund
Landmark |  | Landmark residency | [13 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.282225,73.074556 | [10 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/APduhNwhfDkwra2R7 | [13 empty] | Poladpur | Purandhar
Name of the builder / developer |  | L M Realty | [13 empty] | Mahasala | Bhor
Office address (agreement) |  | Room No 9, 1st Floor, H No 865/B/101, Parol Road, K P Compound, Shelar, Near Asma Hotel, Shelar, Bhiwandi, Thane, 421302 | [13 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [13 empty] | Murud | Velhe
Builder Bank Details |  | Bank Name = AXIS BANK IFSC Code = UTIB0000591
Contact No. |  | 7020283967
Location of the project Municipal Limit : |  | Bhiwandi Nizampur Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartments + Shops
No of Wings / Buildings |  | Building No. A |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 112 Shops = 07 Offices = 14 |  |  | Exposure Limit (Proposed) | 17 |  | 16.8
Approved No. of Floor |  | Building No. A = Gr + 1st to 15th Floor
Proposed No. of Floor |  | Building No. A = Gr + 1st to 15th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | 18.00 M. Wide Road | Other Plot | Other Plot | Other Plot
|  | Physical on site |  | Bhadwad Road | Landmark residency | Open Plot | Building
Verification of survey No. (Title document) |  | Survey No. 110/8B/Plot No/2, 110/8/B/Plot No/1, 110/12/1 & 110/8/A/2
Plot area mentioned in the sale deed (As per 7/12) |  | 2761.69 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 2657.01
Approach road |  | Yes, Approx 18M
Connectivity |  | 1. 0.55km from The Learning High School 2. 0.90km from Glory English High School 3. 0.08km from Shree Saish Hospital 4. 0.60km from Heal Life Hospital 5. 0.50km from Local Market 6. 2.9km from The Miracle Mall 7. 0.70km from Sidhivinayak Shiv Temple 8. 1.1km from Sai Baba Temple 9. 1.10km from Saibaba Mandir Bus stop 10. 6.30km from Bhiwandi Road Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 2657.01
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.1356
|  | Total FSI availaible for the project |  |  |  | 3.2356
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 8597.025
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8597.025
Building plan approvals - Approval No : |  | BNMC/RB/2024/APL/00021 |  |  |  | Date | 2025-01-17
Building height / No. of Floors |  | Gr + 1st to 15th Floor (Height 48.60 Mtrs)
Construction/Building Permission Valid Upto |  | BNMC/RB/2024/APL/00021 Building A = Gr + 1st to 15th Floor |  |  |  | Date | 2025-01-17
Fire NOC Valid Upto |  | BNSMNP/Agni/327/2024 Gr + 1st to 14th Floor (Height 45.40 Mtrs) |  |  |  | Date | 2024-06-12
NA / Land conversion |  | Name of the authority : |  | -
|  | Reference No : |  | - |  | Date | - |  | ``
|  | Validity & Area mentioned: |  | - |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions |  | -
Fire Noc No Valid Up to: | [5 empty] | Date
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2021-01-21 |  | Baseline finish date |  | 2025-12-31 |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 9 Floor, External Plaster upto 9 Floor Completed
Construction details:
Building No. A= Gr + 1st to 15th Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 15 | Piling Work in process | 3.75
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 9 Floor, External Plaster upto 9 Floor Completed | [5 empty] | Excavation in process | 7.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 15
Excavation |  | 0% |  | 15 | 100% | 71% |  | Footing in Process | 3.75
Plinth |  | 10% |  | 15 | 100% |  |  | Footing Completed | 7.5
RCC (Including podiums) |  | 40% |  | 16 | 100% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 15 | 100% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 9 | 60% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 9 | 60% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 11.25
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 15
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. A Shops |  | 7 |  | 2970.5411 |  | 4604.3387
Building No. A Offices |  | 14 |  | 7098.4382 |  | 11031.4772
Total |  | 21 |  | 10068.9793 |  | 15635.8159
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. A |  | 112 |  | 71426.8901 |  | 107140.3351
Grand Total |  | 133 |  | 81495.8694 |  | 122776.151
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | Attached Otla area+ Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
55%
Building No. A
Ground Floor For Commercial, Society Office, Drivers Room, Entrance Lobby & Parking | [9 empty] | Area in approved plans is not in scale Rera carpet taken as discuss with sachin sir
1 |  | Shop | 298.0552 | 38.7504 | 336.8056 | 0 | 522.0486 |  | 57.885
2 |  | Shop | 436.3726 | 38.7504 | 475.123 | 0 | 736.4406
3 |  | Shop | 452.9491 | 38.7504 | 491.6995 | 0 | 762.1343
4 |  | Shop | 452.9491 | 38.7504 | 491.6995 | 0 | 762.1343
5 |  | Shop | 452.9491 | 38.7504 | 491.6995 | 0 | 762.1343
6 |  | Shop | 302.6837 | 38.7504 | 341.4341 | 0 | 529.2228 |  | 64.076
7 |  | Shop | 303.3295 | 38.7504 | 342.0799 | 0 | 530.2239 |  | 50.22
1st Floor For Commercial & Residential
1 |  | Office | 311.8008 | 41.3338 | 353.1345 | 0 | 547.3585 |  | 57.885
2 |  | Office | 343.0487 | 38.7504 | 381.7991 | 0 | 591.7886
3+4+5 |  | Office | 1062.7297 | 116.2512 | 1178.9809 | 0 | 1827.4204
6 |  | Office | 298.5934 | 41.3338 | 339.9271 | 0 | 526.887
7 |  | Office | 303.3295 | 62.1298 | 365.4593 | 0 | 566.462
2nd Floor For Commercial & Residential
1 |  | Office | 311.8331 | 41.3338 | 353.1668 | 0 | 547.4086 |  | 57.885
2 |  | Office | 343.0487 | 38.7504 | 381.7991 | 0 | 591.7886
3 |  | Office | 342.8334 | 38.7504 | 381.5838 | 0 | 591.4549
4 |  | Office | 343.1563 | 38.7504 | 381.9067 | 0 | 591.9554
5 |  | Office | 343.0487 | 38.7504 | 381.7991 | 0 | 591.7886
6 |  | Office | 298.5934 | 41.3338 | 339.9271 | 0 | 526.887
7 |  | Office | 303.3295 | 62.1298 | 365.4593 | 0 | 566.462
3rd Floor For Commercial & Residential
1 |  | Office | 478.2445 | 0 | 478.2445 | 0 | 741.279 |  | 57.885
2 |  | Office | 1415.2507 | 0 | 1415.2507 | 28.898 | 2222.5366
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | AP Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Building No. A
Ground Floor For Commercial, Society Office, Drivers Room, Entrance Lobby & Parking
1st Floor For Residential (Part Commercial Area) | [7 empty] | 1 |  | 10.764
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
6 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
7 |  | Commercial
8
2nd Floor For Residential (Part Commercial Area) | [7 empty] | 1 |  |  |  | 5800
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  |  | 4500000 | 5527.7033 | 4721671.656
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92 |  |  | 4721671.656
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81 | 6800000 | 6137.5247 | 6426043.416
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  |  |  |  | 6426043.416
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472 |  |  |  |  | 4741337.484
6 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472 |  |  |  |  | 4741337.484
7 |  | Commercial
8
3rd Floor For Residential (Part Commercial Area) | [7 empty] | 1
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  |  | 3200000 | 5896.2169
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
6 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
7 |  | Commercial
8
4th Floor For Residential (Part Commercial Area) | [7 empty] | 1
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  |  | 3799000 | 4666.61
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
6 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
7 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
8 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
5th to 7th, 9th to 12th, 14th & 15th Floor For Residential | [7 empty] | 9
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  |  | 3800000 | 4667.8383
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92 |  | 0
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81 | 5700000 | 5144.6898
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  |  |  | 0
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472 |  |  |  | 0
6 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472 |  |  |  | 0
7 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  |  |  | 0
8 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  |  |  | 0
8th & 13th Floor (Part Refuge Area) | [7 empty] | 2 |  |  | #DIV/0!
1 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  |  |  | 0
2 |  | 1BHK | 434.2198 | 108.5011 | 542.7209 | 0 | 814.0813 |  | 44.92 |  | 0
3 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385 |  | 54.81
4 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
5 |  | 1BHK | 436.4802 | 108.5011 | 544.9813 | 0 | 817.472
6 |  | Refuge Area
7 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
8 |  | 1.5BHK | 615.2702 | 123.3554 | 738.6257 | 0 | 1107.9385
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5500
Recommended of Parking ( If Available) |  |  |  |  | 3,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + AP Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Ms Vaidehi 7020283967
11 | We have referred Survey nos from approved floor plan. More survey nos are mentioned in CC (Survey No.110/8/A/2, 110/8/B/1). Please check for Legal Report.
Photographs Of Property : |  | L M Tower
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Mangesh Laxman Bapardekar |  | Authorized Signatory Name & Seal of the agency
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C61: RERA Start date
Note on H79: if multiple buildings are in project and are connected internally
Note on C81: AAC Block or Brick
Note on H83: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3