## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 29/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-27
Name of the builder |  |  |  | M/s. Balkrishna Kashinath Bhoir
Name of the builder company |  |  |  | M/s. Balkrishna Kashinath Bhoir
Name of the Project |  |  |  | Shree Ashta Vinayak Vastu Prakalpa
Contact Details ( Name & Contact No.) |  |  |  | Kavita 8169308125
Name / No of the Building |  |  |  | Building 1 to 11
Docouments Provided |  |  |  | Refer Data, Part OC
RERA No. |  |  |  | Building 1 to 6 = Not Registered on RERA Building 7 to 9 = P51700007934 Building 10 & 11 = P51700007934
Project location details |  | Shree Ashta Vinayak Vastu Prakalpa, S No.56/1(Pt) & 57, near Carmel High School, Amnbernath- Badlapur road, Belavali, Badlapur East, Ambernath, Thane.
S No |  | 56/1(Pt) & 57
Road |  | Amnbernath- Badlapur road |  | Locality/Village |  | Belavali |  | Ashta Vinayak Vastu Prakalpa Phase 2 Katrap Road Opp Sun N Shade Hotel Near Carmel High School, Badlapur East, Maharashtra 421503
City |  | Badlapur East |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Nearby Landmark |  | Carmel High School |  | Distance from city centre: |  | 2.6km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | NA
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Amnbernath- Badlapur road
West | NA | NA |  |  | Road
North | NA | NA |  |  | Jay-Vijay Enterprises
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1787 |  | Longitude |  | 73.2217
Location Link |  | https://maps.app.goo.gl/fU14FK8bvZFkM54g6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 14712
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14712
Total number of Buildings |  |  |  | 11 Buildings
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  | Dated | NA
Approved Floor plan No. |  | NA |  |  | Dated | NA
Commencement Certificate No. Building No 4 to 11 |  | KBNP/NRV/BP/1760-184/2016-17 Unique No.184 |  |  | Dated | 2017-03-01
Valid Up to: Gr + 1st to 7th Floor
O. Certificate No.: Approved upto : |  | KBNP/NRV/7726/2018-2019 Building No.7, 8 & 9 = Stilt + 1st to 7th Floor (For Residential) |  | Date of approval: | Dated | 2018-10-19
Part O. Certificate No.: Approved upto : |  | KBNP/NRV/5114/2020-2021 Building No.3 to 9 = Ground Floor (For Commercial) |  | Date of approval: | Dated | 2020-07-21
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 14712
Approved no of units |  |  | NA
Approved no of Floors |  |  | Building No.1 to 11 = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 to 11 = Gr + 1st to 7th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes |  |  | All work completed. Please provide OC.
Construction details: |  | Building No.7, 8 & 9 = Gr + 1st to 7th Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | All work Completed. OC Received.
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Piling Work in process | 1.75
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 3.5
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation Completed | 7
Plinth |  | 7 | 100% |  |  |  |  | Footing in Process | 1.75
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing Completed | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth completed | 7
Possession |  | 7 | 100% |  |  |  |  | All work completed. Please provide OC.
Construction details: |  | Building No.3 to 6 = Gr + 1st to 7th Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | All work Completed. Part OC Received.
Stage of construction: |  | All work Completed. Part OC Received. | [5 empty] | Piling Work in process | 1.75
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 3.5
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation Completed | 7
Plinth |  | 7 | 100% |  |  |  |  | Footing in Process | 1.75
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing Completed | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth completed | 7
Possession |  | 7 | 100%
Construction details: |  | Building No.1, 2, 10 & 11 = Gr + 1st to 7th Floor | [5 empty] | Excavation work Completed. 0, RCC upto 7 Slab Completed, Brickwork upto 7 Floor Completed, Internal Plaster upto 7 Floor Completed, External Plaster upto 7 Floor Completed, Flooring upto 7 Floor Completed, Painting upto 7 Floor Completed, Finishing upto 7 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | All work Completed. Provide OC | [5 empty] | All work Completed. Provide OC
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 0
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 0
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 0
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 0
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8800
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 250000
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor |  |  |  | 301,..,1501 | 301 | 1501
5 |  |  |  | 0 | 0 | Ground Floor |  |  |  | 302,..,1502 | 302 | 1502
6 |  |  |  | 0 | 0 | Ground Floor |  |  |  | 303,..,1503 | 303 | 1503
7 |  |  |  | 0 | 0 | Ground Floor |  |  |  | 304,..,1504 | 304 | 1504
[10 empty] | 305,..,1505 | 305 | 1505
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor |  |  |  | 306,..,1506 | 306 | 1506
50%
2nd Floor | [9 empty] | 201 to 501 | 201 | 501
201 |  |  |  | 0 | 0 | 2nd Floor |  |  |  | 202 to 502 | 202 | 502
202 |  |  |  | 0 | 0 | 2nd Floor |  |  |  | 203 to 503 | 203 | 503
203 |  |  |  | 0 | 0 | 2nd Floor |  |  |  | 204 to 504 | 204 | 504
204 |  |  |  | 0 | 0 | 2nd Floor |  |  |  | 205 to 505 | 205 | 505
205 |  |  |  | 0 | 0 | 2nd Floor |  |  |  | 206 to 506 | 206 | 506
206 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor | [9 empty] | 201 & 501 | 201 | 501
301,..,1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 202 & 502 | 202 | 502
302,..,1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 203 & 503 | 203 | 503
303,..,1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 204 & 504 | 204 | 504
304,..,1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 205 & 505 | 205 | 505
305,..,1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 206 & 506 | 206 | 506
306,..,1506 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
206 to 506 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
206 & 506 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
1. Bldg No.3 to 6 = All work completed. OC Received upto Ground Floor, Provide Full OC. Bldg No.1, 2, 10 & 11 = All work completed. Provide OC. Bldg No 7, 8 & 9 = All work completed. OC Received. 2. We have considered rate by verifying it from market inquire. 3. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 4. Car parking is subjected to authentic documentation. 5. We have updated OC from Rera for Bldg No. 7, 8 & 9 (On 28/10/2023). 6. We have updated Part OC for Building No.3 to 9 on 29/09/2025 5. On Site, we meet Miss. Kavita Shrivastava - 8169308125
1 | Construction work is in process at the time of Visit (labour found). All work completed. OC received.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr........(........).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shree Ashta Vinayak Vastu Prakalpa
Google Map :

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted