## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 27/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-27
Name of the builder group |  |  |  | Kum Kum Enterprises
Name of the builder company |  |  |  | Kum Kum Enterprises
Name of the Project |  |  |  | Kumkum Corner
Provided Contact Details (Name & Contact No.) |  |  |  | 9619830004
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Shailesh : 9619830004
Name / No of the Building |  |  |  | Building 1
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P52000050669
Project location details |  | Kumkum Corner, Survey No..111, Plot No. 9 - 10, near Sai Disha Apartment, Internal Road, Hajare Nagar, Dhamote, Neral, Karjat, Raigad - 410101.
Survey No. |  | 111, Plot No. 9 - 10
Locality |  | Hajare Nagar
Road |  | Internal Road |  | Locality/Village |  | Dhamote
City |  | Neral |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410101
Nearby Landmark |  | Sai Disha Apartment |  | Distance from city centre: |  | 2.5 KM from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Sai Disha Apartment
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Siddhivinayak Samarth
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.031775, 73.328122
Location Link |  | https://goo.gl/maps/bGJf8kJbAMJkgM61A
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 870
Permissible FSI |  |  |  | 1.6
Permissible TDR/Paid FSI |  |  |  | 0.64
Total FSI availaible for the project |  |  |  | 2.24
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 1948.8
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Raigad Zilha Parishad
Layout Approval No |  | J.K. RJP BP/NSVP/561/2022 |  |  | Dated | 2022-12-19
Approved Floor plan No. |  | J.K. RJP BP/NSVP/561/2022 |  |  | Dated | 2022-12-19
Commencement-CC No Valid Up to: |  | J.K. RJP BP/NSVP/561/2022 |  |  | Dated | 2022-12-19
Gr + 1st to 7th Floor
O. Certificate No.: |  | J.K.59 Approved upto : Gr/St + 1st to 7th Floor Total Built Up Area = 1946.34 Sq.Mt. |  |  | Dated | 2025-03-26
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 1948.8
Approved no of units |  |  | Flats - 46
Approved no of Floors |  |  | Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Gr + 1st to 7th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Main door with decorative laminate finish. Glazed tiles in Bath & WC
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Gr + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 20 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  |  | By Rushikesh Sir | 2024-06-12
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Housing | Inspection Sheet
Flats |  | 46 |  | 17247.0657 |  | 25212.9335 |  | 2722.271 | 3453.6919
Building details Floor Wise | [7 empty] | 3058.7315
Details of Flats in Building | [7 empty] | 2890.5013
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Ground Floor for Parking & Society Office & Driver Room
1st to 6th Floor for Residential
1 |  | 1BHK | 383.3007 | 0 | 555.786 | 1st to 6th Floor for Residential |  |  |  | 1778515.0531
2 |  | 1BHK | 379.4041 | 0 | 550.1359 | 1st to 6th Floor for Residential |  |  | 10.764 | 1760434.9776
3 |  | 1BHK | 372.5313 | 0 | 540.1704 | 1st to 6th Floor for Residential |  |  |  | 1728545.1206
4 |  | 1BHK | 383.3007 | 0 | 555.786 | 1st to 6th Floor for Residential |  |  |  | 1778515.0531
5 |  | 1BHK | 383.3007 | 0 | 555.786 | 1st to 6th Floor for Residential |  | 29.3775 | 2.475 | 1778515.0531
6 |  | 1BHK | 393.8279 | 0 | 571.0504 | 1st to 6th Floor for Residential |  |  |  | 1827361.224
7 |  | 1BHK | 383.3007 | 0 | 555.786 | 1st to 6th Floor for Residential |  | 27.8115 | 2.475 | 1778515.0531
7th Floor (Part Natural Floor) | [9 empty] | 0
1 |  | 1RK | 228.3152 | 121.4394 | 391.7768 | 7th Floor (Part Natural Floor) |  |  |  | 1253685.6634
2 |  | 1RK | 288.8842 | 74.0025 | 492.8846 | 7th Floor (Part Natural Floor) |  |  |  | 1577230.8365
3 |  | 1RK | 272.7705 | 69.966 | 465.4833 | 7th Floor (Part Natural Floor) |  |  |  | 1489546.4314
4 |  | 1BHK | 383.3007 | 0 | 555.786 | 7th Floor (Part Natural Floor) |  |  |  | 1778515.0531
Remarks:
* | All work Completed. OC Received.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Chajja Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 12/06/2024.
* | We have updated OC (On 28/04/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kumkum Corner
Layout :
Google Map :
Formulas:
Dhamote = [Dhamote, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted