## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 29/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-27
Name of the builder group |  |  |  | Macrotech Developers Limited
Name of the builder company |  |  |  | Macrotech Developers Limited
Name of the Project |  |  |  | Lodha Bellevue
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing 1
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51900046567
Project location details |  | Lodha Bellevue, CTS No.1913, near Dagdi Chawl, Maulana Azad Road, Agripada, Byculla, Byculla West, Byculla, Mumbai - 400011.
CTS No |  | 1913
Locality |  | Agripada
Road |  | Maulana Azad Road |  | Locality/Village |  | Byculla
City |  | Byculla West |  | District |  | Mumbai
Taluka |  | Byculla |  | Pin Code |  | 400011
Nearby Landmark |  | Dagdi Chawl |  | Distance from city centre: |  | 0.7KM from Byculla Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Bapurao Jagtap Marg
West | NA | NA |  |  | Rangwala compund
North | NA | NA |  |  | Dagdi Chawl
South | NA | NA |  |  | Chawl
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 18.977829,72.828098
Location Link |  | https://goo.gl/maps/y5N5XKcY6tZWok4k6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 24858.97
Permissible FSI |  |  |  | 1.33
Permissible TDR/Paid FSI |  |  |  | 4.058
Total FSI availaible for the project |  |  |  | 5.388
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 133939.9
Total number of Buildings |  |  |  | 1 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-11910/2022/(1913)/E Ward/BYCULLA/337/3/Amend |  |  | Dated | 2024-05-09
Approved Floor plan No. |  | P-11910/2022/(1913)/E Ward/BYCULLA/337/3/Amend |  |  | Dated | 2024-05-09
Commencement-CC No Valid Up to: |  | P-11910/2022/(1913)/E Ward/BYCULLA/CC/2/Amend |  |  | Dated | 2024-07-09
|  | This CC is endorsed for Wing 1 & Wing 3 i.e. full CC of wing 1 & wing 3 including OHT & LMR and plinth & core upto ground level of Wing 2 and Plinth & core for MLCP-2 for part portion marked A-B-C-D-E-F (excluding plinth area below the existing structure) as per Phase I of approved Phase Programme dated 25.06.2024 and amended approved plan 09.05.2024. |  |  | Valid Upto Date | 2025-07-08
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 47451.25
Approved no of units |  |  | Flats - 391 |  |  |  |  | Flats - 269, Shops - 9
Approved no of Floors |  |  | Wing 1 = Gr/Stilt + Service Floor + 1st to 58th Floor Wing 2 = G + 1st Floor Wing 3 = G + 7P + 8A + 9th Floor Wing 4 = G + 7P + 8A + 9th Floor Wing 5 = 4B + Gr Floor
Proposed no of Floors |  |  | Wing 1 = Gr/Stilt + Service Floor + 1st to 58th Floor Wing 2 = G + 1st Floor Wing 3 = G + 7P + 8A + 9th Floor Wing 4 = G + 7P + 8A + 9th Floor Wing 5 = 4B + Gr Floor
Wing 2 = G + 1st to 56th Floor
Wing 3 & 4 = G + 7P + 8A + 56th Floor
Wing 5 = 4B + Gr + 20th Floor
Expected Completion |  |  | As per RERA - 30/09/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing 1 = Gr/Stilt + Service Floor + 1st to 58th Floor Wing 2 = G + 1st Floor Wing 3 = G + 7P + 8A + 9th Floor Wing 4 = G + 7P + 8A + 9th Floor Wing 5 = 4B + Gr Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 53 Slab, Brickwork upto 52 Floor, Internal Plaster upto 39 Floor, External Plaster upto 36.4 Floor, Flooring upto 16 Floor Completed | , RCC upto 53 Slab, Brickwork upto 52 Floor, Internal Plaster upto 39 Floor, External Plaster upto 36.4 Floor, Flooring upto 16 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 58 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 53 Slab, Brickwork upto 52 Floor, Internal Plaster upto 39 Floor, External Plaster upto 36.4 Floor, Flooring upto 16 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14.5
Excavation |  | 58 | 100% | 66.73% |  | 84.31% |  | Excavation in process | 29
Plinth |  | 58 | 100% |  |  |  |  | Excavation Completed | 58
RCC (Including podiums) |  | 53 | 89.83% |  |  |  |  | Footing in Process | 14.5
Brickwork | Brickwork & Internal Plaster | 52 | 89.66% |  |  |  |  | Footing Completed | 29
Internal Plaster | Brickwork & Internal Plaster | 39 | 67.24% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 36.4 | 62.76% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 16 | 27.59% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 43.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 58
Construction details: |  | Wing 2 = G + 1st to 56th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 56 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 28
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 56
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 14
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 28
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 42
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 56
Construction details: |  | Wing 3 & 4 = G + 7P + 8A + 56th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 56 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 28
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 56
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 14
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 28
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 42
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 56
Construction details: |  | Wing 5 = 4B + Gr + 20th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 10
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 35000 |  |  | 30000 TO 35000 | SMITH | 2025-09-29 | CASE 18TH FLOOR A1
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 42000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Infrastructure Charges |  |  |  |  | 855000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 28000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing 5 |  | 9 |  | 3145.9997 |  | 5033.5995
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing 1 |  | 391 |  | 442662.4873 |  | 663993.7309
Wing 2 |  | 7 |  | 7660.1575 |  | 11490.2363
Wing 3 |  | 3 |  | 5094.908 |  | 7642.362
Wing 4 |  | 3 |  | 5094.908 |  | 7642.362
Total |  | 404 |  | 460512.4607 |  | 690768.6911
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing 5 (Commercial Wing)
1st to 4th Basement Floor For Parking
Ground Floor For Commercial | [8 empty] | 10.764
1 |  | Shop | 350.9333 | 0 | 561.4933 | Ground Floor For Commercial
2 |  | Shop | 399.775 | 0 | 639.6399 | Ground Floor For Commercial
3 |  | Shop | 399.775 | 0 | 639.6399 | Ground Floor For Commercial
4 |  | Shop | 399.775 | 0 | 639.6399 | Ground Floor For Commercial
5 |  | Shop | 399.775 | 0 | 639.6399 | Ground Floor For Commercial
6 |  | Shop | 298.9916 | 0 | 478.3866 | Ground Floor For Commercial
7 |  | Shop | 298.9916 | 0 | 478.3866 | Ground Floor For Commercial
8 |  | Shop | 298.9916 | 0 | 478.3866 | Ground Floor For Commercial
9 |  | Shop | 298.9916 | 0 | 478.3866 | Ground Floor For Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing 1
Ground Floor For Meter Room, Society Office, B.M.S.Room, Fire Control Room & Parking
1A Service Floor
1st to 6th Floor, 8th to 12th Floor 13th Floor (14th Floor As per Builder), 15th to 20th Floor (16th to 21st Floor As per Builder), 22nd to 27th Floor (23rd to 28th Floor As per Builder), 29th to 34th Floor (30th to 35th Floor As per Builder), 36th to 41st Floor(37th to 42nd Floor As per Builder), 43rd to 48th Floor (44th to 49th Floor As per Builder), 50th to 55th Floor (51st to 56th Floor As per Builder), 57th & 58th Floor (58th & 59th Floor As per Builder)
1 | C1 | 2 | 877.8849 | 0 | 1316.8274 | 1st to 6th Floor, 8th to 12th Floor 13th Floor (14th Floor As per Builder), 15th to 20th Floor (16th to 21st Floor As per Builder), 22nd to 27th Floor (23rd to 28th Floor As per Builder), 29th to 34th Floor (30th to 35th Floor As per Builder), 36th to 41st Floor(37th to 42nd Floor As per Builder), 43rd to 48th Floor (44th to 49th Floor As per Builder), 50th to 55th Floor (51st to 56th Floor As per Builder), 57th & 58th Floor (58th & 59th Floor As per Builder)
2 | C2 | 2 | 877.8849 | 0 | 1316.8274 |  |  |  | 73.3269
3 | A1 | 3 | 1104.973 | 0 | 1657.4596 |  |  | 29925.3154
4 | A2 | 4 | 1531.4212 | 0 | 2297.1318 |  |  | 30472.7837
5 | B1 | 2.5 | 899.8435 | 0 | 1349.7652 |  |  | 29338.4353
6 | B2 | 4 | 1531.4212 | 0 | 2297.1318
7 | B3 | 3 | 1109.7953 | 0 | 1664.693
7th Floor, 14th Floor (15th Floor As per Builder), 21st Floor (22nd Floor As per Builder), 28th Floor (29th Floor As per Builder), 35th Floor (36th Floor As per Builder), 42nd Floor (43rd Floor As per Builder), 49th Floor (50th Floor As per Builder (Part Refuge Area)
1 | C1 | 2 | 877.8849 | 0 | 1316.8274 | 7th Floor, 14th Floor (15th Floor As per Builder), 21st Floor (22nd Floor As per Builder), 28th Floor (29th Floor As per Builder), 35th Floor (36th Floor As per Builder), 42nd Floor (43rd Floor As per Builder), 49th Floor (50th Floor As per Builder (Part Refuge Area)
2 | C2 | 2 | 877.8849 | 0 | 1316.8274 |  |  |  | 73.3269
3 | A1 | 3 | 1104.973 | 0 | 1657.4596
4 | A2 | Refuge Area
5 | B1
6 | B2 | 4.5 | 1664.0337 | 0 | 2496.0505
7 | B3 | 3 | 1109.7953 | 0 | 1664.693
56th Floor (57th Floor As per Builder) (Part Refuge Area)
1 | C1 | 2 | 877.8849 | 0 | 1316.8274 | 56th Floor (57th Floor As per Builder) (Part Refuge Area)
2 | C2 | 2 | 877.8849 | 0 | 1316.8274
3 | A1 | 3 | 1104.973 | 0 | 1657.4596
4 | A2 | Refuge Area
5 | B1 | 3.5 | 1057.3208 | 0 | 1585.9812
6 | B2 | 4 | 1531.4212 | 0 | 2297.1318
7 | B3 | 3 | 1109.7953 | 0 | 1664.693
27A Floor for Service Floor (Between 27th & 28th Floor)
36th Floor (37th Floor As per builder) (Part Refuge Area)
1 |  | 2 | 854.1772 | 0 | 1281.2658 | 36th Floor (37th Floor As per builder) (Part Refuge Area)
2 |  | 2 | 857.4064 | 0 | 1286.1096 |  |  |  | 73.3269
3 |  | 3 | 1044.2695 | 0 | 1566.4042
4 |  | Refuge Area
5
6 |  | 4 | 1492.1326 | 0 | 2238.1989
7 |  | 3 | 1044.2695 | 0 | 1566.4042
Wing 2
Ground Floor For Parking
1st Floor For Residential
1 |  | 2 | 854.1772 | 0 | 1281.2658 | 1st Floor For Residential
2 |  | 2 | 857.4064 | 0 | 1286.1096 | 1st Floor For Residential
3 |  | 3 | 1044.2695 | 0 | 1566.4042 | 1st Floor For Residential
4 |  | 4 | 1492.1326 | 0 | 2238.1989 | 1st Floor For Residential
5 |  | 3 | 875.7698 | 0 | 1313.6547 | 1st Floor For Residential
6 |  | 4 | 1492.1326 | 0 | 2238.1989 | 1st Floor For Residential
7 |  | 3 | 1044.2695 | 0 | 1566.4042 | 1st Floor For Residential
Wing 3
Ground Floor For Parking
1st To 7th Podium Floor For Parking
8th Podium Floor For Amenities
9th Floor For Residential
1 |  | 4 | 1804.5254 | 0 | 2706.7881 | 9th Floor For Residential |  | 29555.3243
2 |  | 3 | 1485.8572 | 0 | 2228.7858 | 9th Floor For Residential
3 |  | 4 | 1804.5254 | 0 | 2706.7881 | 9th Floor For Residential
Wing 4
Ground Floor For Parking
1st To 7th Podium Floor For Parking
8th Podium Floor For Amenities
9th Floor For Residential
1 |  | 4 | 1804.5254 | 0 | 2706.7881 | 9th Floor For Residential
2 |  | 3 | 1485.8572 | 0 | 2228.7858 | 9th Floor For Residential
3 |  | 4 | 1804.5254 | 0 | 2706.7881 | 9th Floor For Residential
Ground Floor
1 |  | 1 |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
1 | Wing 1 = Construction work is in process at the time of Visit. (Internal photographs was not allowed.) Wing 2 to 5 = Work not yet Started.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Deck Area.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Wing 1 belongs to Lodha Bellevue, so we are giving the construction stage only for Wing 1.
11 | Wing 2 belongs to different projects & Wing 3 belongs to lodha Solitaire.
12 | We have updated latest approved floor plans & CC (dtd.18/05/2024).
13 | We have updated latest CC from MCGM site (On 31/10/2024).
14 | We have updated Sale Flat Numbering provided to us on mail by the Bank Officials. Please find the attachment Below. (On 09/01/2025)
15 | We have updated latest CC from MCGM site (On 28/09/2025).
16 | Validity of CC is expired on 08/07/2025. Please provide latest CC.
17 | Recommended Rates / Other charges of the Property have been revised on 29/09/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lodha Bellevue
Remark 15 (Flat Bifurcation as per Sale plan) :
Layout :
Google Map :
Formulas:
Byculla = [Byculla, row above]
WING 1
WING 3
WING 4
WING 2
WING 5
WING 1
Wing 1

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted