## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 30/09/2025
CPC Name: |  |  |  |  | Axis Sanpada.
Date Of Property Visit |  |  |  |  | 2025-09-29
Name of the builder group |  |  |  |  | M/s.Sai Swarg Enterprises
Name of the builder company |  |  |  |  | M/s.Sai Swarg Enterprises
Name of the Project |  |  |  |  | Panvelkar Utsav Phase II
Contact Details ( Name & Contact No.) |  |  |  |  | 2512600034
Name / No of the Building |  |  |  |  | B & C Wing
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P51700022593
Project Location Details |  | Panvelkar Utsav Phase II, GUT No.1 & 2, Hissa No.1, 2, 3, 4, Barvi Dam Road, Valivali, Badlapur East, Ambarnath, Thane.
GUT No |  | 1 & 2 |  |  | Hissa No |  | 1, 2, 3, 4
Road |  | Barvi Dam Road |  |  | Village |  | Valivali
City |  | Badlapur East |  |  | District |  | Thane
Taluka |  | Ambarnath |  |  | Pin Code |  | 421503
Near by Landmark |  | Sadguru Residency |  |  | Distance from city centre: |  | About 2.4 Km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Sadguru Residency |  | Open Plot |  | Mandir |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.183791, 73.239318
Location Link |  | https://goo.gl/maps/23AN8DPMf5jgR4Ti9
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 6809.24
Permissible FSI |  |  |  |  | 0.85
Permissible TDR/Paid FSI |  |  |  |  | 1.0285
Total FSI availaible for the project |  |  |  |  | 1.8785
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 12790.85
Total number of Buildings |  |  |  |  | 02 wings
Approval Detail : Plan approval
Layout Approval No |  | KBNP/NRV/BP/4677-30 |  |  |  | Dated | 31/05/2019.
Approved Floor plan No. |  | KBNP/NRV/BP/4677-30 |  |  |  | Dated | 31/05/2019.
Commencement Certificate No. |  | KBNP/NRV/BP/4677/2019-2020/30 Valid Up to: B & C Wing = G + 1st to 12th Floor |  |  |  | Dated | 31/05/2019. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 31/05/2019. |  | Expected Completion |  | Completed
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 7405.63 |  | Approved no of units |  | Flats = 202 & shop = 14
Approved no of Floors |  | B & C Wing - G + 1st to 12th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years
Material laying at Site: Nothing
Construction details:
Construction details: |  | B Wing - G + 1st to 12th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 13 Slab completed, Brickwork upto 12 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed, Flooring upto 12 Floor completed, Painting upto 12 Floor completed, Finishing upto 12 Floor completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 3
Excavation |  | 12 | 100% |  | 100% |  | 100% |  | Excavation in process |  | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed |  | 12
RCC (Including podiums) |  | 13 | 100% | [5 empty] | Footing in Process |  | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Footing Completed |  | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Basement 2 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% | [5 empty] | Basement 3 |  | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% | [5 empty] | Basement 4 |  | 0
Painting & Wooden |  | 12 | 100% | [5 empty] | Basement 5 |  | 0
Building Common Amenities | Building Common Amenities | 12 | 100% | [5 empty] | Plinth in process/1st basement proces |  | 9
Possession |  | 12 | 100% | [5 empty] | Plinth completed |  | 12
Construction details: |  | C Wing - G + 1st to 12th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 13 Slab completed, Brickwork upto 12 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed, Flooring upto 12 Floor completed, Painting upto 12 Floor completed, Finishing upto 12 Floor completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 3
Excavation |  | 12 | 100% |  | 100% |  | 100% |  | Excavation in process |  | 6
Plinth |  | 12 | 100% | [5 empty] | Excavation Completed |  | 12
RCC (Including podiums) |  | 13 | 100% | [5 empty] | Footing in Process |  | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Footing Completed |  | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Basement 2 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% | [5 empty] | Basement 3 |  | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% | [5 empty] | Basement 4 |  | 0
Painting & Wooden |  | 12 | 100% | [5 empty] | Basement 5 |  | 0
Building Common Amenities | Building Common Amenities | 12 | 100% | [5 empty] | Plinth in process/1st basement proces |  | 9
Possession |  | 12 | 100% | [5 empty] | Plinth completed |  | 12
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 8500/-
Other Charges | [5 empty] | 200000/-
Any Other amenities | [5 empty] | NA
Maintenance | [5 empty] | 39960/-
Other charges | [5 empty] | 10,000/-
Maintance Charges For 2 Years | [5 empty] | 50,000/-
Development charges | [5 empty] | 2,00,000/-
Recommended rate of Parking | [5 empty] | 2,00,000/-
Distressed valuation of the Property | [5 empty] | 3600
Commercial Area Details :
Building & Wing |  | No. of Shops | Total Carpet Area |  |  | Total Saleable Area
B |  | 14 | 2163.0258 |  |  | 3460.8413
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
B |  | 107 | 44037.4346 |  |  | 66405.7128
C |  | 95 | 31650.7347 |  |  | 47476.1021
Total |  | 202 | 75688.1693 |  |  | 113881.8149
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
B Wing
Ground Floor is for Parking & Commercial
1 |  | Shop | 174.8074 |  | 0 | 279.6918 | N | Ground Floor
2 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
3 |  | Shop | 139.7167 |  | 0 | 223.5468 | N
4 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
5 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
6 |  | Shop | 126.7999 |  | 0 | 202.8799 | N
7 |  | Shop | 139.2862 |  | 0 | 222.8579 | N
8 |  | Shop | 139.2862 |  | 0 | 222.8579 | N
9 |  | Shop | 126.7999 |  | 0 | 202.8799 | N
10 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
11 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
12 |  | Shop | 174.8074 |  | 0 | 279.6918 | N
13 |  | Shop | 126.7999 |  | 0 | 202.8799 | N
14 |  | Shop | 140.6855 |  | 0 | 225.0968 | N
1st Floor
1 |  | 1 BHK | 380.615 |  | 0 | 570.9226 | N | 1st Floor |  |  |  | 48528.4176
2 |  | 1 BHK | 380.615 |  | 0 | 570.9226 | N |  |  |  |  | 48528.4176
3 |  | 1 BHK | 396.7341 |  | 0 | 595.1012 | N |  |  |  |  | 50583.6016
4 |  | 2 BHK | 495.144 |  | 220.7696 | 853.1008 | N |  |  |  |  | 72513.5697
5 |  | 1 BHK | 363.285 |  | 103.442 | 596.6485 | N |  |  |  |  | 50715.1242
6 |  | 1 BHK | 363.285 |  | 103.442 | 596.6485 | N |  |  |  |  | 50715.1242
7 |  | 1 BHK | 363.285 |  | 407.2021 | 680.6615 | N |  |  |  |  | 57856.2309
8 |  | 1 BHK | 398.4564 |  | 0 | 597.6846 | N |  |  |  |  | 50803.1872
9 |  | 1 BHK | 398.2411 |  | 0 | 597.3616 | N |  |  |  |  | 50775.739
2nd to 7th & 9th to 12th Floors | [11 empty] | 0
1 |  | 1 BHK | 380.615 |  | 0 | 570.9226 | N | 2nd to 7th & 9th to 12th Floors |  |  |  | 48528.4176
2 |  | 1 BHK | 380.615 |  | 0 | 570.9226 | N |  |  |  |  | 48528.4176
3 |  | 1 BHK | 396.7341 |  | 0 | 595.1012 | N |  |  |  |  | 50583.6016
4 |  | 2 BHK | 557.1446 |  | 0 | 835.717 | N |  |  | 3870536 | 3793582.928 | 71035.9416
5 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
6 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
7 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
8 |  | 1 BHK | 398.4564 |  | 0 | 597.6846 | N |  |  |  |  | 50803.1872
9 |  | 1 BHK | 398.2411 |  | 0 | 597.3616 | N |  |  |  |  | 50775.739
8th Floor (Part Refuge) | [11 empty] | 0
1 |  | 1 BHK | 380.615 |  | 0 | 570.9226 | N | 8th Floor |  |  |  | 48528.4176
2 |  | 1 BHK | 396.7341 |  | 0 | 595.1012 | N |  |  |  |  | 50583.6016
3 |  | 2 BHK | 557.1446 |  | 0 | 835.717 | N |  |  |  |  | 71035.9416
4 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
5 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
6 |  | 1 BHK | 401.4703 |  | 0 | 602.2054 | N |  |  |  |  | 51187.462
7 |  | 1 BHK | 398.4564 |  | 0 | 597.6846 | N |  |  |  |  | 50803.1872
8 |  | 1 BHK | 398.2411 |  | 0 | 597.3616 | N |  |  |  |  | 50775.739
C Wing | [11 empty] | 0
Ground Floor is for Parking | [11 empty] | 0
1st to 7th & 9th to 12 Floors | [11 empty] | 0
1 |  | 1 RK | 275.9351 |  | 0 | 413.9027 | N | 1st to 7th & 9th to 12 Floors |  | 4457.5693 |  | 35181.7303
2 |  | 1 RK | 272.3292 |  | 0 | 408.4938 | N |  |  |  |  | 34721.973
3 |  | 1 RK | 272.3292 |  | 0 | 408.4938 | N |  |  |  |  | 34721.973
4 |  | 1 RK | 265.7093 |  | 0 | 398.564 | N |  |  |  |  | 33877.9408
5 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
6 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
7 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
8 |  | 1 BHK | 384.1672 |  | 0 | 576.2507 | N |  |  |  |  | 48981.3129
8th Floor (Part Refuge) | [11 empty] | 0
1 |  | 1 RK | 275.9351 |  | 0 | 413.9027 | N | 8th Floor |  |  |  | 35181.7303
2 |  | 1 RK | 272.3292 |  | 0 | 408.4938 | N |  |  |  |  | 34721.973
3 |  | 1 RK | 272.3292 |  | 0 | 408.4938 | N |  |  |  |  | 34721.973
4 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
5 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
6 |  | 1 BHK | 396.4112 |  | 0 | 594.6168 | N |  |  |  |  | 50542.4293
7 |  | 1 BHK | 384.1672 |  | 0 | 576.2507 | N |  |  |  |  | 48981.3129
Remarks:
1. Wing B & C = All work Completed. Please provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + E.P Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Since the project has received first CC on 31/05/2019, but still project is under construction. 7. On site, we meet Mr. Kiran (Sales) - 8530953111.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Sudhir Bhosale |  | Report Prepared By : |  |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Panvelkar Utsav Phase II
Google Map :
Wing B
Wing C

## Note
06/05/2021. | Asmi | Akash

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99acers | Panvelkar Utsav | 1BHK | 230 | 345 | 4927.5362 | 1700000
Magic Brick | Panvelkar Utsav |  | 236.808 | 355.212 | 4785.8744 | 1700000
Average |  |  |  |  | 4856.7053
Valuation Adopted |  |  |  |  | 4800

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 12
Particulars | total floor | 12
plinth | 10 | 7 | 70%
slab | 13 | 0 | 0% |  | Parking |  | Rate
Bricks | 12 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 12 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 12 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 12 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 12 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 8
Particulars | total floor | 8
plinth | 10 | 10 | 100%
slab | 9 | 1 | 11.11% |  | Parking |  | Rate
Bricks | 8 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 8 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 8 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 8 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 8 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 4.4444 | 0 | 0 | 0 | 0 | 0
RCC | 4.4444 | 3.3333 |  | Recommended |  | 30 | 3.3333 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 14.44% | 33.33% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.35 | 9.2125 | CB | 2.75 | 1 | 2.75 |  |  | 0
|  | 1.2 | 1.5 | 1.8 | FB | 2.2 | 1.2 | 2.64 |  |  | 0
|  | 0.9 | 1.35 | 1.215 |  |  |  | 0 |  |  | 0
| kitch | 2.2 | 2 | 4.4 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 178.9784 | 16.6275 |  |  | 58.018 | 5.39 |  | 0 | 0
|  |  | 236.9964 | 22.0175