## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-09-29 |  |  | 2025-07-04
Project Name |  | Prestige Ocean Towers - North & South |  | Date & Time of Site Visit |  | 01/10/2025 at 02:52PM |  |  | 2025-10-01
Name of the person met at site & Contact No. |  | Ms. Manisha 8904004107 |  | Date of Report Release |  | 03/10/2025 |  |  | 89
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. Prestige Projects Private Limited |  | Developer Name |  | M/s. Prestige Projects Private Limited
Developer Office Address |  | 1005, 10th Floor, Godrej BKC, Plot C-68, G-Block, Bandra Kurla Complex, Village Kolekalyan, Tal. Andheri, Mumbai 400051.
Project Address | As per ARF | Prestige Ocean Towers - North & South, Plot No 2193, Charni Road, Girgaon, Mumbai South, Maharashtra, 400004.
| As per Legal Documents | Proposed Development On Plot Bearing C.S. No.2193 (Pt) Of Bhuleshwar Division 'C' Ward, Situated at the Junction of Babasaheb Jaykar Marg & Maharshi Karve Road, Mumbai.
| As per Actual at site | Prestige Ocean Towers - North & South, Maharshi Karve Rd, Hemraj Wadi, Thakurdwar, Girgaon, Mumbai, Maharashtra 400002.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, Airport NOC, CRZ NOC, EC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. |  | North Tower - (Wing 1/ Tower 1) | P51900053993 | RERA Registration Validity |  | North Tower = 30/06/2030 South Tower = 31/12/2030
|  | South Tower (Wing 2/ Tower 2) | P51900066470
Project Launch Date | : | North Tower = 18/12/2023 South Tower = 11/06/2024 |  | Construction Start Date | : | North Tower = Oct-24 South Tower = Aug-24
Proposed Date of Completion (As per RERA) | : | North Tower = 30/06/2030 South Tower = 31/12/2030 |  | Developer Bank Name (As per RERA) | : | ICICI Bank Limited
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 9309.93
FSI/FAR Permissible | : | 1.33 |  | Net Plot Area (In Sq.Mt) | : | 8571.33
Permissible Built up Area (In Sq.Mt) | : | 44125 |  | Proposed Built up Area (In Sq.Mt) | : | 44125
Total Number of Units Approved | : | Sale Flats = 126 AH/RR MP Rooms = 170 Sale MP Rooms = 2 |  | Total Number of Units Planned | : | As per RERA Site Flats = Flat - 126 AH/RR MP Rooms = 170
Latitude, Longitude | : | 18.9504333,72.8212283 |  | Landmark | : | S.K. Patil Garden
Location Link | : | https://maps.app.goo.gl/VDqWpHFyMroYq5E86
Extra Amenities available | : | Kids Play Area, Multipurpose court, Amphitheater, Club House, Indoor Games, Landscape Garden, Senior Citizen Area, Banquet Hall, Gym, Swimming Pool etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 12m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.35 KM from Charni Road Railway Station Bus Stop
Distance from the nearest School (Km) | : | About 0.65 KM from St. Sebastian Goan High School |  | Distance from Hospital (Km) | : | About 0.80 KM from Conwest & Manjula S Badani Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.75 KM from Vegetable Market. 2. Approx. 2.00 KM from Crawford Market. |  | Distance from Railway Station (Km) | : | 0.35 KM from Charni Road Railway Station 0.50 KM from Marine Lines Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | Yes
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East |  | West
East |  | Other Plot |  |  | Slum
West |  | 27.44 M.W. Maharshi Karve Road |  |  | Maharshi Karve Road
North |  | 18.30 Mt. Wide Dr. Babasaheb Jaykar Marg |  |  | Dr. Babasaheb Jaykar Marg
South |  | 12.20 M.W. S.K.Patil |  |  | Bhai Jivanji Ln
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
North Tower Wing 1 (Tower 1) |  | Sale | 2B + G + 1st to 55th Floor |  |  | 2B + G + 1st to 51st Floor
South Tower Wing 2 (Tower 2) |  | Sale | 2B + G + 1st to 55th Floor |  |  | 2B + G + 1st to 52nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | EB/1525/C/A/337/9/Amend |  |  |  | Date: | 2024-10-29
Approved Plan Details | : | EB/1525/C/A/337/9/Amend |  |  |  | Date: | 2024-10-29
CC Details Valid Up to: |  | EB/1525/C/A/FCC/1/New |  |  |  | Date: | 2023-09-20
|  | This C.C. is endorsed up to plinth i.e. up to the top slab of 3rd Podium Floor as per approved plan dated 12.9.2023. |  |  |  | Valid Upto Date | 2026-02-16
Environmental Clearance Details Valid Up to: | : | SEIAA-EC-0000002180 CS No. 2193 Proposed Builtup Area =193926.87 sq.m |  |  |  | Date: | 2020-03-13 | 16.02.2025.
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details Valid Up to: |  | SNCR/WEST/B/102122/713099 |  |  |  | Date: | 2022-11-11 | [5 empty] | 7 RCC 3Brick 2 plaster
|  | Site Elevation (AMSL) = 4.65 Mtrs Permissible Top Elevation (AMSL) = 275.37 Mtrs |  |  |  | Date: | 2030-11-10 | 270.72 |  |  |  |  | 7 RCC 3Brick 2 plaster
Fire NOC Valid Up to: |  | EB/1525/C/A-CFO |  |  |  | Date: | 2023-08-25
Wing 1 (Tower 1) = 2B + Gr/Stilt + P1 to P6 + 7th Floor + 8th to 51st Floor (Height = 205.90M) Wing 2 (Tower 2) = 2B + Gr/Stilt + P1 to P6 + 7th Floor + 8th to 55th Floor (Height = 221.50M)
CRZ NOC: |  | CRZ 2014 /CR 157/TC 4 |  |  |  | Date: | 2015-01-23
Construction Status
North Tower Wing 1 (Tower 1)= 2B + G + 1st to 55th Floor. |  |  | Basement | Ground |  | Podium | Floors
|  |  | 2 | 1 |  | 0 | 55
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation work in process
Excavation |  | 27.5 | 50% | 5% |  | Excavation work in process |  | All work Completed. OC Received.
Plinth |  | 0 | 0% |  |  |  |  | Piling Work in process | 13.75
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Excavation in process | 27.5
Brickwork |  | 0 | 0% |  |  |  |  | Excavation Completed | 55
Internal Plaster |  | 0 | 0% |  |  |  |  | Footing in Process | 13.75
External Plaster |  | 0 | 0% |  |  |  |  | Footing Completed | 27.5
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 1 | 41.25
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 2 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Construction Status
South Tower Wing 2 (Tower 2)= 2B + G + 1st to 55th Floor. |  |  | Basement | Ground |  | Podium | Floors
|  |  | 2 | 1 |  | 0 | 55
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation work Completed. 1st Basement Completed
Excavation |  | 55 | 100% | 21.25% |  | Excavation work Completed. 1st Basement Completed |  | All work Completed. OC Received.
Plinth |  | 41.25 | 75% |  |  |  |  | Piling Work in process | 13.75
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Excavation in process | 27.5
Brickwork |  | 0 | 0% |  |  |  |  | Excavation Completed | 55
Internal Plaster |  | 0 | 0% |  |  |  |  | Footing in Process | 13.75
External Plaster |  | 0 | 0% |  |  |  |  | Footing Completed | 27.5
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 1 | 41.25
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 2 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Project Completion % | [5 empty] | 13.12%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 93000 to 94000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1600000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 7623.56 |  | as per book
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 15630.8064
Distress Value (Rs. Per sqft) |  |  |  |  | : | 6098.848
Unit Details, Nomenclature and Area Details (Flat)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Tower 1 |  | Sale |  | 76 |  | 184536.9073 |  | OK | Diff of 3 Sq Ft
Tower 2 |  | Sale |  | 50 |  | 123531.3238 |  | OK | Diff of 3 Sq Ft
Total |  | - |  | 126 |  | 308068.2311
Unit Details, Nomenclature and Area Details (MP Room)
Building & Wing |  | Sale /AH/RR |  | No. of Unit |  | Total Gross Carpet Area
Tower 2 |  | AH/RR |  | 170 |  | 52991.3421 |  | OK
|  | Sale |  | 2 |  | 598.3492 |  | OK
Total |  | - |  | 172 |  | 53589.6913
Grand Total |  | - |  | 298 |  | 361657.9224
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / AH/RR | Description | Carpet area | Deck Area | Attached Terrace area | Gross Carpet area | 10.764
Wing 1 / Tower 1 (North Tower)
2nd & 1st Basement Floor for Parking
Ground Floor for Entrance Lobby & Control Room
1st Floor for Podium Parking, Meter Room & Panel Room
2nd & 3rd Floor for Podium Parking & Society Office
4th & 5th Floor For Podium Parking
6th Podium Floor for Garden, Meeting Room, Kids Play Area (Part Refuge Area)
7th Floor For Fitness Center
8th Floor For Service Floor
9th to 13th & 15th to 20th & 24th Floor for Residential | [7 empty] | 12
1 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
2 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
14th Floor For Residential (Part Refuge Area) | [7 empty] | 1
- |  | Sale | Refuge Area | [11 empty] | 101,..,1401 | 101 | 1401
1 |  | Sale | 5BHK | 3207.0262 | 174.2799 | 0 | 3381.3061 | OK | [6 empty] | 102,..,1402 | 102 | 1402
21st Floor For Residential (Part Refuge Area) | [7 empty] | 1
- |  | - | Refuge Area | [11 empty] | 2101,..,2101 | 2101 | 2101
1 |  | Sale | 5BHK | 3028.0208 | 0 | 0 | 3028.0208 | OK | [6 empty] | 2102,..,2102 | 2102 | 2102
22nd Floor as Service Floor | [7 empty] | 1
23rd Floor For Residential | [7 empty] | 1
1 |  | Sale | 4BHK | 2270.8811 | 0 | 0 | 2270.8811 | OK
2 |  | Sale | 4BHK | 2270.8811 | 0 | 0 | 2270.8811 | OK
25th to 28th, 30th to 35th, 37th to 42nd, 46th & 47th Floor | [7 empty] | 18
1 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | 91461.0399
2 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
29th & 36th Floor For Residential (Part Refuge Area) | [7 empty] | 2
- |  | - | Refuge Area | [11 empty] | 2901,..,3601 | 2901 | 3601
1 |  | Sale | 5BHK | 3206.9185 | 175.4101 | 0 | 3382.3287 | [7 empty] | 2902,..,3602 | 2902 | 3602
43rd Floor For Residential (Part Refuge Area) | [7 empty] | 1
- |  | - | Refuge Area | [11 empty] | 401,..,4301 | 401 | 4301
1 |  | Sale | 5BHK | 3206.9185 | 0 | 0 | 3206.9185 | OK | [6 empty] | 402,..,4302 | 402 | 4302
44th Floor as Service Floor | [7 empty] | 215512000
45th Floor For Residential | [7 empty] | 1
1 |  | Sale | 4BHK | 2270.8811 | 0 | 0 | 2270.8811 | 107843.604
2 |  | Sale | 4BHK | 2270.8811 | 0 | 0 | 2270.8811 | 94902.3715
48th to 50th Floor | [7 empty] | 3 | 92475.1198
1 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | 90776.924
2 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
51st Floor For Residential (Part Terrace Area Treated as Refuge) | [7 empty] | 1
- |  | - | Terrace Area
1 |  | Sale | 5BHK | 3379.5731 | 175.4101 | 0 | 3554.9832 | OK
Wing 2 / Tower 2 (South Tower)
2nd & 1st Basement Floor for Parking
Ground Floor for Entrance Lobby & Control Room
1st Floor for Podium Parking, Meter Room & Panel Room
2nd & 3rd Floor for Podium Parking & Society Office
4th & 5th Floor For Podium Parking
6th Podium Floor for Garden, Meeting Room, Kids Play Area (Part Refuge Area)
7th Floor for Fitness Center
8th Floor As Service Floor
9th to 13th & 15th to 20th & 22nd Floor for Residential | [7 empty] | 12
1 |  | AH/RR | MP Room | 296.2942 | 0 | 0 | 296.2942 | OK
2 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
3 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
4 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
5 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
6 |  | AH/RR | MP Room | 296.2942 | 0 | 0 | 296.2942 | OK
7 |  | AH/RR | MP Room | 296.8248 | 0 | 0 | 296.8248 | OK
8 |  | AH/RR | MP Room | 296.1876 | 0 | 0 | 296.1876 | OK
9 |  | AH/RR | MP Room | 299.1746 | 0 | 0 | 299.1746 | OK
10 |  | AH/RR | MP Room | 299.1746 | 0 | 0 | 299.1746 | OK
11 |  | AH/RR | MP Room | 296.1876 | 0 | 0 | 296.1876 | OK
12 |  | AH/RR | MP Room | 296.8248 | 0 | 0 | 296.8248 | OK
14th & 21st Floor For Residential (Part Refuge Area) | [7 empty] | 2
1 |  | - | Refuge Area
2 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
3 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
4 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
5 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
6 |  | AH/RR | MP Room | 296.2942 | 0 | 0 | 296.2942 | OK
7 |  | AH/RR | MP Room | 296.8248 | 0 | 0 | 296.8248 | OK
8 |  | AH/RR | MP Room | 296.1876 | 0 | 0 | 296.1876 | OK
9 |  | AH/RR | MP Room | 299.1746 | 0 | 0 | 299.1746 | OK
10 |  | Refuge Area
11
12
23rd Floor For Residential | [7 empty] | 1
1 |  | AH/RR | MP Room | 296.2942 | 0 | 0 | 296.2942 | OK
2 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
3 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
4 |  | AH/RR | MP Room | 296.1478 | 83.4102 | 0 | 379.558 | OK
5 |  | AH/RR | MP Room | 297.5159 | 0 | 0 | 297.5159 | OK
6 |  | AH/RR | MP Room | 296.2942 | 0 | 0 | 296.2942 | OK
7 |  | AH/RR | MP Room | 296.8248 | 0 | 0 | 296.8248 | OK
8 |  | AH/RR | MP Room | 296.1876 | 0 | 0 | 296.1876 | OK
9 |  | Sale | MP Room | 299.1746 | 0 | 0 | 299.1746 | OK
10 |  | Sale | MP Room | 299.1746 | 0 | 0 | 299.1746 | OK
11 |  | AH/RR | MP Room | 296.1876 | 0 | 0 | 296.1876 | OK
12 |  | AH/RR | MP Room | 296.8248 | 0 | 0 | 296.8248 | OK
24th Floor as Service Floor | [7 empty] | 1
25th to 28th, 30th to 35th, 37th to 42nd, 46th & 47th Floor | [7 empty] | 18
1 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
2 |  | Sale | 4BHK | 2270.8811 | 85.4446 | 0 | 2356.3257 | OK
29th & 36th Floor For Residential (Part Refuge Area) | [7 empty] | 2
- |  | - | Refuge Area
1 |  | Sale | 5BHK | 3322.3086 | 175.4101 | 0 | 3497.7187 | OK
43rd Floor For Residential (Part Refuge Area) | [7 empty] | 1
- |  | - | Refuge Area
1 |  | Sale | 5BHK | 3153.852 | 0 | 0 | 3153.852
44th Floor as Service Floor | [7 empty] | 1
45th Floor For Residential | [7 empty] | 1 |  | 93000
1 |  | Sale | 4BHK | 2261.7317 | 0 | 0 | 2261.7317 | 94573.5526 |  | 210341046.24
2 |  | Sale | 4BHK | 2261.7317 | 0 | 0 | 2261.7317 | OK |  | 210341046.24
48th to 50th & 52nd Floor | [7 empty] | 4 |  | 93000
1 |  | Sale | 4BHK | 2473.4596 | 85.4446 | 0 | 2558.9042 | 83590.4684 |  | 237978089.856
2 |  | Sale | 4BHK | 2473.4596 | 85.4446 | 0 | 2558.9042 | OK |  | 237978089.856
51st Floor For Residential (Part Refuge Area) | [7 empty] | 1
- |  | - | Refuge Area
1 |  | Sale | 5BHK | 3384.2016 | 175.4101 | 0 | 3559.6117 | 79896.354
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Wing 2 (Tower 2) ground floor shop numbering is not mentioned in the approved floor plan. Therefore we are unable to draft the commercial area for Wing 2 (Tower 2).
* | We have referred Fire Noc from MCGM site on 05/07/2025
* | As per approved floor plan flat type AH/RR to be handed over to MCGM
* | We have given Valuation for Sale Flats only.
* | Validity Date of CC is expired on 16/02/2025. Provide revised approved CC.
Site & Building/Tower Photographs
Name of the Project |  |  | Prestige Ocean Towers - North & South
Project Site Address |  |  | Prestige Ocean Towers - North & South, Plot No 2193, Charni Road, Girgaon, Mumbai South, Maharashtra, 400004.
Site Visit Date & Time |  |  | 01/10/2025 at 02:52PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Karan Misal |  | Authorized Signatory Name & Signature
Wing 2
Wing 1
Tower 1
Tower 2
Tower 1
Tower 2
Tower 2
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C18: Maybe same as RERA Registration Validity or different
Note on G18: From Rera
Note on C21: From RERA
Note on G21: From RERA
Note on G22: From RERA
Note on G28: SACHIN: Road size should be in metre
Note on G100: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0