## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-09-29
Project Name |  | Narang Vivenda |  | Date & Time of Site Visit |  | 30/09/2025 @ 01:49PM |  |  |  | 2025-07-08 |  | 84
Name of the person met at site & Contact No. |  | Ms. Sneha |  | Date of Report Release |  | 03/10/2025 |  |  |  | 2025-09-30
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Narang Propco Private Limited |  | Developer Name |  | Narang Propco Private Limited (Narang Realty)
Developer Office Address |  | Windsor, 1st floor, C.S.T. Road,, Kalina, Santacruz (East),, Mumbai, Maharashtra 400098
Project Address | As per ARF | Narang Vivenda, CTS No. 307/3 ,307/4 ,307/5 ,307/6, Evershine Nagar Rd, Malad, Malad West, Mumbai, Maharashtra 400064
| As per Legal Documents | Proposed Redevelopment of Residential Building on Plot No. 1 to 7 Bearing CTS No. 307/3, 307/4, 307/5 and 307/6 of Village Valnai at Malad (West), Mumbai
| As per Actual at site | Narang Vivenda, Plot No.1 to 7 & CTS No. 307/3, 307/4, 307/5 & 307/6 Redevelopement of "Ushma Nagar CHS Federation Ltd", near Sandesh CHS, Evershine Nagar Road, Ushma Nagar, Valnai, Malad West, Borivali, Mumbai - 400064.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800055504 |  | RERA Registration Validity | : | 2029-12-31
Project Launch Date | : | 2024-04-02 |  | Construction Start Date | : | 2024-04-01
Proposed Date of Completion (As per RERA) | : | 2029-12-31 |  | Developer Bank Name (As per RERA) | : | ICICI BANK LIMITED IFSC Code - ICIC0007710
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 11731
FSI/FAR Permissible | : | 4 |  | Net Plot Area (In Sq.Mt) | : | 11090.2
Permissible Built up Area (In Sq.Mt) | : | 44360.8 |  | Proposed Built up Area (In Sq.Mt) | : | 53754.271
Total Number of Units Approved | : | Sale Flats = 254 Rehab Flats = 04 Shop = 14 |  | Total Number of Units Planned | : | As per RERA Site Flats & Shop = Not provided
Latitude, Longitude | : | 19.1941039,72.8324685 |  | Landmark | : | Abrol Vastu Park
Location Link | : | https://maps.app.goo.gl/SGoqJcusRRqZ4LRz7
Extra Amenities available | : | Fitness Center, Swimming Pool, Play Park, Multipurpose Lawn, Mini Theatre, Kids Play Area, Indoor games, Seating Area, Banquet Hall, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Concrete |  | Width of the Road | : | 13.40M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.550 KM from Evershine Nagar (Malad-W) Bus Stop
Distance from the nearest School (Km) | : | About 0.350 KM from Ryan International School, Malad |  | Distance from Hospital (Km) | : | About 0.700 KM form Zenith Hospital
Distance from the Main C (Km) | : | 1. Approx. 1.20 KM from 20th Century Super Market. 2. Approx. 1.20 KM from Reliance SMART Superstore. |  | Distance from Railway Station (Km) | : | 3.30 KM from Malad Railway Station 3.40 KM from Kandivli Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East |  | West
East |  | Other Plot |  |  | Sandesh CHS
West |  | Other Plot |  |  | Samir CHS
North |  | Other Plot |  |  | Vishal Nagar CHS
South |  | 13.40 M W Road |  |  | Evershine Nagar Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 1 (Wing D) |  | Sale | Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 39th Floor |  |  | Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 38th Floor
Tower 2 |  | Sale
Tower 3 |  | Sale
Tower 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | P-15166/2023/(307/3 AND OTHER) P/N WARD/ VALNAI/337/2/AMEND |  |  |  | Date: | 2024-08-20
Approved Plan Details | : | P-15166/2023/(307/3 AND OTHER) P/N WARD/ VALNAI/337/2/AMEND |  |  |  | Date: | 2024-08-20
CC Details Valid Up to: |  | P-15166/2023/(307/3 And Other)/P/N Ward/VALNAI/ FCC/2/Amend |  |  |  | Date: | 2024-10-25
|  | This Further C.C. is now granted for the work above the remaining portion of plinth of sale Wing ‘D’ of building No. 1 (i.e. entire Wing ‘D’) comprising of 02 levels basement + stilt (pt) + ground (pt) + 1st to 4th level podium + 5th to 36th upper floors as per approved amended plans dated 20.08.2024. |  |  |  | Valid Upto Date | 2025-10-24
CC Details Valid Up to: |  | P-15166/2023/(307/3 And Other)/P/N Ward/VALNAI/ FCC/3/Amend |  |  |  | Date: | 2025-06-02
|  | This C.C. is now granted for the work of remaining podium portion between Wing ‘A’ & ‘D’ of building No. 1 comprising of 02 levels basement + stilt (pt) + ground (pt)+ 1st to 4th level podium (Marked E-F-G-H in plan) as per approved amended plans dtd. 20.08.2024. |  |  |  | Valid Upto Date | 2025-12-26
Environmental Clearance Details | : | SIA/MH/INFRA2/422706/2023 Valid Up to: CTS No. 307/3, 307/4, 307/5 & 307/6 Proposed Builtup Area = 99419.94 Sq.m |  |  |  | Date: | 2023-07-21
Fire NOC Details | : | P-15155/2023/(307/3 And Other)/P/N Ward/Valnai-CFO/ 1/New Wing D = 2B + Gr. + 1P to 4P + 5th to 39th Floor (Total height = 138.39 mtrs) |  |  |  | Date: | 2024-07-01
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date: | [5 empty] | 7 RCC 3Brick 2 plaster
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Building No. 1 (Wing D) = Building No.1 (Wing D) = 2B + G + P1 to P4 + 5th to 39th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed
|  |  | 2 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 32.37% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 10 | 25% |  |  |  |  | Footing in Process | 9.75
Brickwork |  | 5 | 12.82% |  |  |  |  | Footing Completed | 19.5
Internal Plaster |  | 3.75 | 9.615% |  |  |  |  | Basement 1 | 29.25
External Plaster |  | 3.75 | 9.615% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 2 = . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 2 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 0.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 1.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 3 = . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 3 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 1.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 2.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 32.37%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 31000 to 32000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1000000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 7079.1527
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 16398.1791
Distress Value (Rs. Per sqft) |  |  |  |  | : | 5663.3222
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing D (Shop) |  | Rehab |  | 14 |  | 3646.4487
Rehab
Total |  | - |  | 14 |  | 3646.4487
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing D |  | Rehab |  | 4 |  | 4561.8693
|  | Sale |  | 254 |  | 287841.4803
Total |  | - |  | 258 |  | 292403.3496
Grand Total |  | - |  | 272 |  | 296049.7983
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Building No.1 (Wing D)
Lower & Upper Basement for Parking
Ground Floor For Commercial, Electrical Panel Room, Meter Room & Parking | [8 empty] | 10.764
17 |  | Rehab | Shop | 192.3258 | 0 | 0 | 192.3258
18 |  | Rehab | Shop | 219.7341 | 0 | 0 | 219.7341
19 |  | Rehab | Shop | 258.871 | 0 | 0 | 258.871
20 |  | Rehab | Shop | 411.0045 | 0 | 0 | 411.0045
21 |  | Rehab | Shop | 264.2185 | 0 | 0 | 264.2185
22 |  | Rehab | Shop | 281.0636 | 0 | 0 | 281.0636
23 |  | Rehab | Shop | 160.1414 | 0 | 0 | 160.1414
24 |  | Rehab | Shop | 431.2893 | 0 | 0 | 431.2893
25 |  | Rehab | Shop | 220.4177 | 0 | 0 | 220.4177
26 |  | Rehab | Shop | 238.6863 | 0 | 0 | 238.6863
27 |  | Rehab | Shop | 252.3819 | 0 | 0 | 252.3819
28 |  | Rehab | Shop | 252.8948 | 0 | 0 | 252.8948
29 |  | Rehab | Shop | 238.7455 | 0 | 0 | 238.7455
30 |  | Rehab | Shop | 224.6743 | 0 | 0 | 224.6743
1st to 3rd Podium Floor For Parking
4th Podium Floor For Amenity
5th Floor For Residential
1 |  | Rehab | 2BHK | 1073.2677 | 67.1997 | 0 | 1140.4673 | 99.0576
2 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
3 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393 |  | 33535.7509
4 |  | Rehab | 2BHK | 1073.2677 | 67.1997 | 0 | 1140.4673
5 |  | Rehab | 2BHK | 1073.2677 | 67.1997 | 0 | 1140.4673
6 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
7 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
8 |  | Rehab | 2BHK | 1073.2677 | 67.1997 | 0 | 1140.4673
6th, 8th to 13th, 15th to 19th, 22nd to 27th, 29th to 34th & 36th to 38th Floor For Residential
1 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
2 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
3 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
4 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
5 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
6 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
7 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
8 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
7th, 14th, 21st & 28th Floor (Part Refuge Area)
1 |  | Sale | 4BHK | 1591.8449 | 67.1997 | 0 | 1659.0446 |  | 33573.5407
2 |  | - | Refuge Area
3 |  | -
4 |  | -
5 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739 |  | 34011.3293 | 28663.636
6 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
7 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
8 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
20th Floor
1 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
2 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
3 |  | Sale | 3BHK | 2158.0421 | 158.8766 | 0 | 2316.9187
5 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
6 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
7 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
8 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
35th Floor (Part Refuge Area)
1 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
2 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
3 |  | Sale | 1BHK | 620.7061 | 86.112 | 0 | 706.8181
4 |  | - | Refuge Area
5 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
6 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
7 |  | Sale | 2BHK | 763.7273 | 86.112 | 0 | 849.8393
8 |  | Sale | 3BHK | 1335.2742 | 67.1997 | 0 | 1402.4739
1st Floor
101 | [6 empty] | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [6 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [6 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [6 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [6 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [6 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [6 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [6 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [6 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [6 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [6 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [6 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [6 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [6 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [6 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit. Internal visit was not allowed.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | In Wing D, flat no. 2003 & 2004 is merged as Single unit named as flat no.2003.
* | We have taken approved plans & CC from MCGM Site on 09/07/2025.
* | Please provide revised CC.
Site & Building/Tower Photographs
Name of the Project |  |  | Narang Vivenda
Project Site Address |  |  | Narang Vivenda, CTS No. 307/3 ,307/4 ,307/5 ,307/6, Evershine Nagar Rd, Malad, Malad West, Mumbai, Maharashtra 400064
Site Visit Date & Time |  |  | 30/09/2025 @ 01:49PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Sanket Salvi |  | Authorized Signatory Name & Signature
N
N
Building No.1 Wing D (Sale)
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G117: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0