## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 30/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-30
Name of the builder group |  |  |  | M/s. Godrej Properties Limited
Name of the builder company |  |  |  | M/s. Godrej Properties Limited
Name of the Project |  |  |  | Godrej Ascend Phase 1, 2, 3 & 4
Contact Details ( Name & Contact No.) |  |  |  | Mr. Norbert Mendez 9821422860
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Security
Name / No of the Building |  |  |  | Phase I = Tower 2 & 4 Phase II = Tower 3 (Panorama) Phase III = Tower 5 (Adora) Phase IV = Tower 1 (Arise)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Phase 1 (Tower 2 & 4) : P51700034608 Phase 2 (Tower 3) : P51700046541 Phase 3 (Tower 5) : P51700049514 Phase 4 (Tower 1) : P51700053668
Project location details |  | Godrej Ascend Phase 1, 2, 3 & 4, Survey No.234/1, 234/2, 235, 39, 40 & 41/1, near Kalpataru Starlight, Kolshet Road, , Balkum & Dhokali, Thane West, Thane, Thane - 400607.
Survey No |  | 234/1, 234/2, 235, 39, 40 & 41/1
Locality |  | NA
Road |  | Kolshet Road |  | Locality/Village |  | Balkum & Dhokali
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400607
Nearby Landmark |  | Kalpataru Starlight |  | Distance from city centre: |  | 5.6 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Other Plot/30 M. Wide Road |  |  | Kalpataru Sunrise Wing C
West | NA | Other Plot |  |  | Kalpataru Starlight
North | NA | 40 M Wide Road |  |  | Kolshet Road
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.228423,72.983823
Location Link |  | https://goo.gl/maps/SWJWgdtrybLChNHK9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 24332
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 4.7756
Total FSI availaible for the project |  |  |  | 5.8756
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 142964.49 |  |  |  | 131812.87 | 11151.62
Total number of Buildings |  |  |  | 5 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation
Layout Approval No. |  | S05/0194/19/TMC/TDD/0109/(P/C)/ 2024/AutoDCR |  |  | Dated | 2024-03-26
Approved Floor plan No. Tower 2, 3, 4 & 5 |  | S05/0194/19TMC/TDD/4351/23 |  |  | Dated | 2023-03-31
Approved Floor plan No. Tower 1 |  | S05/0194/19/TMC/TDD/0109/(P/C)/ 2024/AutoDCR |  |  | Dated | 2024-03-26
Commencement-CC No Valid Up to: |  | S05/0194/19TMCB/TDD/0109/[P/C]/ 2024AutoDCR |  |  | Dated | 2024-03-26
Tower 1, 2, 4, & 5 = Gr/Stilt + 1st to 42nd Floor Tower 3 = Gr/Stilt + 1st to 41st Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 142964.49
Approved no of units |  |  | Flats - 1570, Shops - 26
Approved no of Floors |  |  | Tower 1 = Gr + 1st to 46th Floor Tower 2 & 4 = Gr + 1st to 42nd Floor Tower 3 = Gr/Stilt + 1st to 37th Floor Tower 5 = Gr/Stilt + 1st to 41st Floor
Proposed no of Floors |  |  | Phase 1 : Tower 2 = Gr + 1st to 42nd Floor
Phase 1 : Tower 4 = Gr + 1st to 42nd Floor
Phase 2 : Tower 3 = Gr/Stilt + 1st to 42nd Floor
Phase 3 : Tower 5 = Gr/Stilt + 1st to 42nd Floor
Phase 4 : Tower 1 = Gr/Stilt + 1st to 46th Floor
Expected Completion |  |  | As per RERA - Phase 1 - 30/04/2028 Phase 2 - 31/12/2028 Phase 3 - 31/10/2029 Phase 4 - 31/12/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Basketball Pole, Jogging/Walking Trail, Swimming Pool, Spa, Fruit Orchard & Herbal Organic Garden, Retail Plaza, Kids Play Area, 22 Yard Cricket Pitch, Skating Rink, Chess Court, 2 Badminton Courts, Gym, Squash Court, Multi-Play Court, Yoga Deck
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Phase 4 : Tower 1 = Gr/Stilt + 1st to 46th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | , RCC upto 5 Slab, Brickwork upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 46 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 11.5
Excavation |  | 46 | 100% | 14.91% |  | 48.63% |  | Excavation in process | 23
Plinth |  | 46 | 100% |  |  |  |  | Excavation Completed | 46
RCC (Including podiums) |  | 5 | 10.64% |  |  |  |  | Footing in Process | 11.5
Brickwork | Brickwork & Internal Plaster | 4 | 8.696% |  |  |  |  | Footing Completed | 23
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 34.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 46
Construction details: |  | Phase 1 : Tower 2 = Gr + 1st to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 10.5 Floor, External Plaster upto 9.1 Floor Completed | , RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 10.5 Floor, External Plaster upto 9.1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 10.5 Floor, External Plaster upto 9.1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% | 30.5% |  | 59.47% |  | Excavation in process | 21
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42 | 0.86
RCC (Including podiums) |  | 15 | 34.88% |  |  |  |  | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 14 | 33.33% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 10.5 | 25% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9.1 | 21.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Construction details: |  | Phase 2 : Tower 3 = Gr/Stilt + 1st to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab Completed | , RCC upto 6 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% | 15.58% |  | 49.19% |  | Excavation in process | 21
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 6 | 13.95% |  |  |  |  | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Construction details: |  | Phase 1 : Tower 4 = Gr + 1st to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 22.1 Floor, External Plaster upto 20.8 Floor Completed | , RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 22.1 Floor, External Plaster upto 20.8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 22.1 Floor, External Plaster upto 20.8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% | 48.66% |  | 72.04% |  | Excavation in process | 21
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 27 | 62.79% |  |  |  |  | Footing in Process | 10.5 | 3.01
Brickwork | Brickwork & Internal Plaster | 26 | 61.9% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 22.1 | 52.62% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20.8 | 49.52% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Construction details: |  | Phase 3 : Tower 5 = Gr/Stilt + 1st to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 10 Floor, Internal Plaster upto 7.5 Floor, External Plaster upto 6.5 Floor Completed | , RCC upto 11 Slab, Brickwork upto 10 Floor, Internal Plaster upto 7.5 Floor, External Plaster upto 6.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 10 Floor, Internal Plaster upto 7.5 Floor, External Plaster upto 6.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% | 24.91% |  | 55.53% |  | Excavation in process | 21
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 11 | 25.58% |  |  |  |  | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 10 | 23.81% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 7.5 | 17.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6.5 | 15.48% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 13500 |  |  | 13000 to 13500 by sanket on 29/09/2023. do not change again
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 22000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 10800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 1 | Tower 2 | 12 |  | 8353.5098 |  | 13365.6157
Phase 4 | Tower 1 (Arise) | 14 |  | 9981.7801 |  | 15970.8482
Total |  | 26 |  | 18335.29 |  | 29336.4639
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 1 | Tower 2 | 241 |  | 189796.7817 |  | 303674.8506
| Tower 4 | 413 |  | 203931.6224 |  | 326290.5959
Phase 2 | Tower 3 (Panorama) | 179 |  | 140923.2568 |  | 225477.2108
Phase 3 | Tower 5 (Adora) | 485 |  | 218956.5478 |  | 350330.4765
Phase 4 | Tower 1 (Arise) | 252 |  | 202391.4017 |  | 323826.2427
Total |  | 1570 |  | 955999.6103 |  | 1529599.3765
Grand Total |  | 1596 |  | 974334.9003 |  | 1558935.8405
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Phase 1
Tower 2
Ground Floor For Commercial & Entrance
101 |  | Shop | 671.3507 | 0 | 1074.1611 | Ground Floor For Commercial & Entrance
102 |  | Shop | 654.9894 | 0 | 1047.983
103 |  | Shop | 654.2359 | 0 | 1046.7775
104 |  | Shop | 507.1997 | 0 | 811.5195
105 |  | Shop | 1252.822 | 0 | 2004.5151
106 |  | Shop | 912.7872 | 0 | 1460.4595
1st Floor For Commercial & Residential
201 |  | Shop | 528.2971 | 0 | 845.2754 | 1st Floor For Commercial & Residential
202 |  | Shop | 486.8557 | 0 | 778.9692
203 |  | Shop | 486.8557 | 0 | 778.9692
204 |  | Shop | 364.2538 | 0 | 582.806
205 |  | Shop | 1085.98 | 0 | 1737.5679
206 |  | Shop | 747.8827 | 0 | 1196.6124
Phase 4
Tower 1 (Arise)
Ground Floor For Commercial, Entrance Lobby, Society Office, Meter Room & Parking
107 |  | Shop | 798.9041 | 0 | 1278.2465 | Ground Floor For Commercial, Entrance Lobby, Society Office, Meter Room & Parking
108 |  | Shop | 1187.0539 | 0 | 1899.2863
109 |  | Shop | 373.1879 | 0 | 597.1006
110 |  | Shop | 694.278 | 0 | 1110.8448
111 |  | Shop | 718.7123 | 0 | 1149.9396
112 |  | Shop | 366.4066 | 0 | 586.2505
113 |  | Shop | 1397.4901 | 0 | 2235.9842
1st Floor For Part Commercial
207 |  | Shop | 657.1422 | 0 | 1051.4275 | 1st Floor For Part Commercial
208 |  | Shop | 1022.7953 | 0 | 1636.4724
209 |  | Shop | 271.6834 | 0 | 434.6934
210 |  | Shop | 508.4914 | 0 | 813.5862
211 |  | Shop | 533.2486 | 0 | 853.1977
212 |  | Shop | 264.902 | 0 | 423.8433
213 |  | Shop | 1187.4845 | 0 | 1899.9752
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Phase 1
Tower 2
1st Floor For Commercial & Residential
5 |  | 3BHK | 752.3027 | 0 | 1203.6843 | 1st Floor For Commercial & Residential
6 |  | 3BHK | 752.3027 | 0 | 1203.6843
2nd to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor
1 |  | 3BHK | 863.0575 | 0 | 1380.892 | 2nd to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor
2 |  | 3BHK | 746.0528 | 0 | 1193.6845
3 |  | 3BHK | 746.0528 | 0 | 1193.6845
4 |  | 3BHK | 863.0575 | 0 | 1380.892 |  |  | 12672.9676
5 |  | 3BHK | 746.0528 | 0 | 1193.6845
6 |  | 3BHK | 746.0528 | 0 | 1193.6845
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 3BHK | 863.0575 | 0 | 1380.892 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
2 |  | 3BHK | 746.0528 | 0 | 1193.6845
3 |  | Refuge Area
4 |  | 3BHK | 863.0575 | 0 | 1380.892
5 |  | 3BHK | 746.0528 | 0 | 1193.6845
6 |  | 3BHK | 746.0528 | 0 | 1193.6845
31st, 32nd, 34th to 37th, 39th to 42nd Floor
1 |  | 3BHK | 863.0575 | 0 | 1380.892 | 31st, 32nd, 34th to 37th, 39th to 42nd Floor
2 |  | 3BHK | 754.5564 | 0 | 1207.2902
3 |  | 3BHK | 754.5564 | 0 | 1207.2902
4 |  | 3BHK | 863.0575 | 0 | 1380.892
5 |  | 3BHK | 754.5564 | 0 | 1207.2902
6 |  | 3BHK | 754.5564 | 0 | 1207.2902
33rd & 38th Floor (Part Refuge Area)
1 |  | 3BHK | 863.0575 | 0 | 1380.892 | 33rd & 38th Floor (Part Refuge Area)
2 |  | 3BHK | 754.5564 | 0 | 1207.2902
3 |  | Refuge Area
4 |  | 3BHK | 863.0575 | 0 | 1380.892
5 |  | 3BHK | 754.5564 | 0 | 1207.2902
6 |  | 3BHK | 754.5564 | 0 | 1207.2902
Tower 4
Ground Floor For Parking
1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th to 42nd Floor
1 |  | 2BHK | 583.0859 | 0 | 932.9374 | 1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th to 42nd Floor
2 |  | 1BHK | 383.629 | 0 | 613.8063
3 |  | 1BHK | 383.629 | 0 | 613.8063
4 |  | 1BHK | 383.629 | 0 | 613.8063
5 |  | 1BHK | 383.629 | 0 | 613.8063 |  |  | 11796.2811
6 |  | 2BHK | 524.5297 | 0 | 839.2476
7 |  | 2BHK | 524.5297 | 0 | 839.2476
8 |  | 2BHK | 581.1484 | 0 | 929.8374 |  |  | 54.3758
9 |  | 2BHK | 573.0754 | 0 | 916.9206
10 |  | 2BHK | 622.0516 | 0 | 995.2825
8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
1 |  | 2BHK | 583.0859 | 0 | 932.9374 | 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
2 |  | 1BHK | 383.629 | 0 | 613.8063
3 |  | 1BHK | 383.629 | 0 | 613.8063
4 |  | 1BHK | 383.629 | 0 | 613.8063
5 |  | 1BHK | 383.629 | 0 | 613.8063
6 |  | Refuge Area
7 |  | 2BHK | 524.5297 | 0 | 839.2476
8 |  | 2BHK | 581.1484 | 0 | 929.8374
9 |  | 2BHK | 573.0754 | 0 | 916.9206
10 |  | 2BHK | 622.0516 | 0 | 995.2825
Phase 2
Tower 3 (Panorama)
Ground Floor For Parking & Meter Room
1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th Floor
1 |  | 2BHK | 598.0478 | 0 | 956.8765 | 1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th Floor |  | 59.2844 | 10.764
2 |  | 3BHK | 872.6375 | 0 | 1396.22
3 |  | 2BHK | 637.4441 | 0 | 1019.9105
4 |  | 3BHK | 898.794 | 0 | 1438.0704
5 |  | 3BHK | 898.794 | 0 | 1438.0704
8th, 13th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th, 13th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
2 |  | 3BHK | 872.6375 | 0 | 1396.22
3 |  | 2BHK | 637.4441 | 0 | 1019.9105
4 |  | 3BHK | 898.794 | 0 | 1438.0704
5 |  | 3BHK | 898.794 | 0 | 1438.0704
Phase 3
Tower 5 (Adora)
Ground Floor For Parking & Meter Room
1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th & 39th to 41st Floor For Residential
1 |  | 2BHK | 440.9822 | 0 | 705.5716 | 1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th & 39th to 41st Floor For Residential |  | 59.2844 | 10.764
2 |  | 1BHK | 388.8562 | 0 | 622.17
3 |  | 1BHK | 413.748 | 0 | 661.9968
4 |  | 1BHK | 388.8562 | 0 | 622.17
5 |  | 1BHK | 388.8562 | 0 | 622.17
6 |  | 2BHK | 452.8886 | 0 | 724.6217
7 |  | 2BHK | 452.8886 | 0 | 724.6217
8 |  | 2BHK | 601.1398 | 0 | 961.8237
9 |  | 2BHK | 438.4648 | 0 | 701.5437
10 |  | 2BHK | 438.4648 | 0 | 701.5437
11 |  | 2BHK | 570.6158 | 0 | 912.9853
12 |  | 2BHK | 439.5022 | 0 | 703.2035
8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
1 |  | 2BHK | 440.9822 | 0 | 705.5716 | 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  | 59.2844 | 10.764
2 |  | 1BHK | 388.8562 | 0 | 622.17
3 |  | 1BHK | 413.748 | 0 | 661.9968
4 |  | 1BHK | 388.8562 | 0 | 622.17
5 |  | 1BHK | 388.8562 | 0 | 622.17
6 |  | 2BHK | 452.8886 | 0 | 724.6217
7 |  | 2BHK | 452.8886 | 0 | 724.6217
8 |  | 2BHK | 601.1398 | 0 | 961.8237
9 |  | 2BHK | 438.4648 | 0 | 701.5437
10 |  | Refuge Area
11 |  | 2BHK | 570.6158 | 0 | 912.9853
12 |  | 2BHK | 439.5022 | 0 | 703.2035
Phase 4
Tower 1 (Arise) | [7 empty] | Utility Area + Balcony INCLUDED
1st floor For Part Residential | [7 empty] | 1
5 |  | 3BHK | 803.7479 | 0 | 1285.9966 | 1st floor For Part Residential |  |  | 10.764
6 |  | 3BHK | 803.7479 | 0 | 1285.9966
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th to 32nd, 34th to 37th, 39th to 42nd & 44th Floor For Residential | [7 empty] | 35
1 |  | 3BHK | 909.9886 | 0 | 1455.9817 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th to 32nd, 34th to 37th, 39th to 42nd & 44th Floor For Residential |  |  | 10.764
2 |  | 2BHK | 669.9514 | 0 | 1071.9222
3 |  | 2BHK | 696.7537 | 0 | 1114.806
4 |  | 3BHK | 914.8324 | 0 | 1463.7318
5 |  | 3BHK | 803.7479 | 0 | 1285.9966
6 |  | 3BHK | 803.7479 | 0 | 1285.9966
8th, 13th, 18th, 23rd, 28th, 33rd, 38th & 43rd Floor (Part Refuge Area) | [7 empty] | 8
1 |  | 3BHK | 909.9886 | 0 | 1455.9817 | 8th, 13th, 18th, 23rd, 28th, 33rd, 38th & 43rd Floor (Part Refuge Area) |  |  | 10.764 | 59.2844
2 |  | 2BHK | 669.9514 | 0 | 1071.9222
3 |  | Refuge Area
4 |  | 3BHK | 914.8324 | 0 | 1463.7318
5 |  | 3BHK | 803.7479 | 0 | 1285.9966
6 |  | 3BHK | 803.7479 | 0 | 1285.9966
45th Floor For Recreational Area | [7 empty] | 1
46th Floor For Amenity & Part Terrace Area | [7 empty] | 1
Remarks:
* | Tower 1 to 5 = Construction work is in process at the time of Visit. Internal visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Deck Area + Utility Area + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr........(........).
* | We have updated approved floor plans of Phase 2 (Tower 3) (On 18/10/2022).
* | We have updated approved floor plans of Phase 3 (Tower 5) (On 22/04/2023).
* | We have updated approved floor plans of Phase 4 (Tower 1) (On 27/11/2023).
* | We have updated revised approved CC of (Tower 1, 2, 3, 5) (On 06/05/2024).
* | We have updated revised approved plans of Phase 4 (Tower 1) (On 10/02/2025).
* | Construction stage of Tower 1 is reduced due to revision in proposed structure of project.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Godrej Ascend Phase 1, 2, 3 & 4
Layout Plan :
Google Map :
Tower 1
Tower 2
Tower 3
Tower 4
Tower 5
Tower 1
Tower 2
Tower 3
Tower 4

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted
440.9822 |  | 848.6136
388.8562 |  | 633.0308
413.748 |  | 659.7256
388.8562 |  | 818.6466
388.8562 |  | 752.3027
452.8886 |  | 752.3027
452.8886 |  | 1207.5055
601.1398
438.4648
438.4648
570.6158
439.5022