## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 03/10/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Truhome Finance Limited | Sammaan Capital Limited | Jio Finance Limited
Bank Name: |  |  |  | Jio Finance Limited | [5 empty] | Branch | Axis Goregaon | PNB Thane | Truhome Vasai | SCL Kalyan | JFL Koparkhairane
CPC Name: |  |  |  | JFL Koparkhairane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-10-01 | [6 empty] | Axis Sanpada | PNB Panvel |  | SCL Vashi
Name of the builder group |  |  |  | M/s. Sumit Woods Limited | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | M/s. Sumit Woods Limited | [9 empty] | SCL Thane
Name of the Project (As per RERA) |  |  |  | Sumit KMR Param | [9 empty] | SCL Andheri
Name of the Project (As per Builder) |  |  |  | Sky World | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Kishore 9820248101 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Suresh 9819054278 | [9 empty] | SCL Virar
Name / No of the Building |  |  |  | Building No.1
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | RERA Certificate | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800076840 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Sky World, CTS No.282, 283, 284 & 293, near Sri Sri Ravishankar Vidya Mandir, Baburao Paranjape Marg, Ashok Nagar, Borivali, Borivali West, Borivali, Mumbai - 400092. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 282, 283, 284 & 293 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Ashok Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Baburao Paranjape Marg |  | Locality/Village |  | Borivali | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Borivali West |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Borivali |  | Pin Code |  | 400092 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Sri Sri Ravishankar Vidya Mandir |  | Distance from city centre: |  | 1.7KM from Borivali Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 13.40 M.Wide Proposed D.P. Road |  |  | Internal Road
West | NA | Other Plot |  |  | Sri Sri Ravishankar Vidya Mandir
North | NA | 18.30 M.Wide Existing D.P. Road |  |  | Internal Road
South | NA | Internal Road |  |  | C.K.P. Colony Lane
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.232578,72.845430
Location Link |  | https://maps.app.goo.gl/1oLWQZHM2nHMxGXx6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2580.8
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 6.0762
Total FSI availaible for the project |  |  |  | 7.0762
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 18262.18
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | P-12775/2022/(282 And Other)/R/C Ward/BORIVALI-R/C/337/2/Amend |  |  | Dated | 2025-02-14 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | P-12775/2022/(282 And Other)/R/C Ward/BORIVALI-R/C/337/2/Amend |  |  | Dated | 2025-02-14 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Municipal Corporation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | P-12775/2022/(282 And Other)/R/C Ward/BORIVALI-R/C/FCC/1/Amend |  |  | Dated | 2025-03-18 |  | NO REMARK | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[5 empty] | Valid Upto Date | 2026-03-04 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
This C.C. is granted and further extended for proposed residential building No. 1 comprises of Basement + (pt.) Ground floor + (pt.) Stilt floor + 1st to + 8th podiums + 9th to 33rd & 34th (pt) upper floors by (restricting CC of Flat No. 2 of 34th (pt) as per approved amended plans dated 14.02.2025.
Fire Noc No Valid Up to: |  | P-12775/2022/(282 And Other)/R/C Ward/BORIVALI-R/C-CFO/1/New. |  |  | Dated | 2023-07-01 |  |  |  | 2021-03-18 | NO REMARK | [5 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Residential Building No.1 = 1B + Gr/Stilt + P1 to P7 + 8th Amenity Floor + 9th to 37th Floor(Total Height = 119.65 mtrs.) | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  |  |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up for: |  | JUHU/WEST/B/102822/723727 |  |  | Dated | 2022-11-29 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
[5 empty] | Valid upto Dated | 2030-11-28 | [11 empty] | Bhiwandi Nizampur City Municipal Corporation
|  | Site Elevation (AMSL) = 9.84m Permissible Top Elevation (AMSL) = 176.12m | [5 empty] | 166.28
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 18262.18
Approved no of units |  |  | Flats - 211
Approved no of Floors |  |  | Building No.1 = B + Gr/Stilt + P1 to P7 + 8th Amenity Floor + 9th to 36th (pt) Floor
Proposed no of Floors |  |  | Building No.1 = B + Gr/Stilt + P1 to P7 + 8th Amenity Floor + 9th to 37th Floor
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Center, Yoga Area, Mini Theatre, Kids Play Area, Swimming Pool, Banquet Hall, Green Space, Meditation Area, CCTV etc. |  |  |  |  | https://www.99acres.com/sumit-kmr-param-borivali-west-mumbai-andheri-dahisar-npxid-r430049?nn_source=Performance&nn_account=Google_99acres-NPGoogle-Account&nn_campaign=22819151926_181475938943_766405001925&nn_medium=22819151926_181475938943_766405001925&nn_adtype=g_&nn_keyword=&nn_placement=&gad_source=1&gad_campaignid=22819151926&gbraid=0AAAAADLswZWg2VBWczw6FZ0lnTy9wvFtx&gclid=Cj0KCQjwovPGBhDxARIsAFhgkwT3cicQmSJ99DWwcfpoCBaXnP4TrP3k44F33qUV9PA4ZhqS3fnQ-LgaAsujEALw_wcB#showModal
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 = B + Gr/Stilt + P1 to P7 + 8th Amenity Floor + 9th to 37th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 9 Slab Completed | , RCC upto 9 Slab
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 37 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 9 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.25
Excavation |  | 37 | 100% | 19.47% |  | 52.11% |  | Excavation in process | 18.5
Plinth |  | 37 | 100% |  |  |  |  | Excavation Completed | 37
RCC (Including podiums) |  | 9 | 23.68% |  |  |  |  | Footing in Process | 9.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 18.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 27.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 37
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  |  | https://www.magicbricks.com/sumit-kmr-param-borivali-west-mumbai-pdpid-4d4235343234303535 | [5 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 20000 |  |  | On Carpet | 31550.8021 | 21033.8681 | [6 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [9 empty] | 0 | [6 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [9 empty] | 0 | [6 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from 10th Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [9 empty] | 0 | [6 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [9 empty] | 0 | [6 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [9 empty] | 0 | [6 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [9 empty] | 0 | [6 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [9 empty] | 0 | [6 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [9 empty] | 0 | [6 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 800000 |  |  |  | 31584.4701 | 21056.3134 | [6 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 16000 |  |  |  |  | https://dwello.in/view/sumit-param-by-sumit-group-at-borivali_b3568480-ca6a-4363-9448-904506262a66 | [7 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 211 |  | 179292.1698 |  | 268938.2548
Total |  | 211 |  | 179292.1698 |  | 268938.2548 | [5 empty] | On Carpet | 34805.8902 | 23203.9268
Grand Total |  | 211 |  | 179292.1698 |  | 268938.2548 | [6 empty] | 34750.843 | 23167.2287
Building Details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet Area | Balcony + Dry Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | 10.764
50%
Building No.1 | [7 empty] | 20666.6667
Basement Floor For Pump Room & Parking
Ground Floor For Entrance Lobby, Meter Room & Parking
1st Podium Floor For Parking | [7 empty] | 1
2nd to 7th Podium Floor For Parking | [7 empty] | 6
8th Podium Floor For Fitness Center & Swimming Pool | [7 empty] | 1
9th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | 2BHK | 727.5388 | 50.8707 | 778.4094 | 0 | 1167.6141 | 64.3275 | 4.726 | 69.0535
2 |  | Refuge Area
3 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602 | 62.3945 | 4.2525 | 66.647
4 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
5 |  | Refuge Area
6 |  | 2BHK | 707.1948 | 50.8707 | 758.0655 | 0 | 1137.0982 | 62.3945 | 4.2525 | 66.647
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
10th to 15th, 17th to 22nd, 24th to 29th & 31st to 33rd Floor | [7 empty] | 21 |  | 34th Double Floor Plan
1 |  | 2BHK | 727.5388 | 50.8707 | 778.4094 | 0 | 1167.6141
2 |  | 3BHK | 987.8123 | 73.1521 | 1060.9644 | 0 | 1591.4466
3 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
4 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
5 |  | 3BHK | 987.8123 | 73.1521 | 1060.9644 | 0 | 1591.4466
6 |  | 2BHK | 707.1948 | 50.8707 | 758.0655 | 0 | 1137.0982 |  |  |  | As per Visitor |  | 20666.6667
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644 | we have considered greater CA |  | 18807.9764 | As per site
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644 |  |  | 20323.311 | 21392.9589
16th & 23rd Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 3BHK | 940.1278 | 105.4011 | 1045.5288 | 0 | 1568.2933
2 |  | Refuge Area
3 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
4 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
5 |  | Refuge Area
6 |  | 3BHK | 919.7838 | 105.4011 | 1025.1849 | 0 | 1537.7773
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
30th Floor (Part Refuge Area) | [7 empty] | 1 |  | 20000
1 |  | 2BHK | 727.5388 | 50.8707 | 778.4094 | 0 | 1167.6141 |  |  | 23352282.72
2 |  | Refuge Area | [7 empty] | 0
3 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602 |  |  | 23799204
4 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602 |  |  | 23799204
5 |  | Refuge Area | [7 empty] | 0
6 |  | 2BHK | 707.1948 | 50.8707 | 758.0655 | 0 | 1137.0982 |  |  | 22741963.92
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644 |  |  | 22437288.9
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644 |  |  | 22437288.9
34th Floor | [7 empty] | 1
1 |  | 2BHK | 727.5388 | 50.8707 | 778.4094 | 0 | 1167.6141
2 |  | 3BHK | 987.8123 | 76.8119 | 1064.6242 | 0 | 1596.9363
3 |  | 4BHK Duplex With 35th Floor | 1493.0744 | 93.001 | 1586.0754 | 0 | 2379.1131
4 |  | 4BHK Duplex With 35th Floor | 1493.0744 | 93.001 | 1586.0754 | 0 | 2379.1131
5 |  | 3BHK | 987.8123 | 76.8119 | 1064.6242 | 0 | 1596.9363
6 |  | 2BHK | 707.1948 | 50.8707 | 758.0655 | 0 | 1137.0982
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
35th Floor | [7 empty] | 1
1 |  | 2BHK | 733.6742 | 105.1212 | 838.7955 | 0 | 1258.1932
2 |  | 3BHK | 995.9929 | 190.0815 | 1186.0744 | 0 | 1779.1116
3 |  | 4BHK Duplex With 34th Floor
4 |  | 4BHK Duplex With 34th Floor
5 |  | 3BHK | 995.9929 | 190.0815 | 1186.0744 | 0 | 1779.1116
6 |  | 2BHK | 713.3303 | 122.7096 | 836.0399 | 0 | 1254.0598
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
36th Floor (Part Terrace Area) | [7 empty] | 1
1 |  | 2BHK | 733.6742 | 105.1212 | 838.7955 | 0 | 1258.1932
2 |  | 3BHK | 995.9929 | 190.0815 | 1186.0744 | 0 | 1779.1116
3 |  | 2BHK | 746.8063 | 46.5005 | 793.3068 | 0 | 1189.9602
4 |  | Terrace Area
5
6
7 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
8 |  | 2BHK | 702.1357 | 45.7739 | 747.9096 | 0 | 1121.8644
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Dry Balcony Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have referred the latest Approved Plans, CC, Fire & Airport Noc from MCGM site.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate, Fire NOC, Airport NOC, CRZ NOC, Railway Noc.
* | We have given Valuation for Sale Flats and Shops only.
* | NO REMARK FOR CC
* | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Rahul Salve |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sumit KMR Param
Layout :
Google Map :
Formulas:
Borivali = [Borivali, row above]
Sumit KMR Param
Note on E13: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E14: Sachin: If exisiting Building is provided write it or else NA
Note on C57: SACHIN: Floor with height
Note on C59: SACHIN: Survey Nos.
Note on D65: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F94: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H123: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
36 | The project is not registered on RERA site, Beacause land area of project is less than 500 Sq.Mt
37 | Construction stage is reduced due to revision in proposed structure of project.
38 | Construction percentage has been reduced due to the construction work being processed in two parts.
39 | The project has received CC on 07/06/2019, But construction work is not yet Completed.
40 | Some flats are occupied by tenants but finishing work is in process at the time of visit.
41 | As per site visit dtd.23/01/2025 we have observed that the construction work is not done as per approved floor plan. (Extra Terrace Area are Constructed for flats) According to the approved 1st floor plan, terrace area is not attached to Flat No.3, 4 & 5, But on site terrace area is already constructed.
42 | As per approved plan & CC, project consists of Survey No.40, H.No.2A, Plot No.3 & 4. But as per RERA, project consists of Survey No.40/B, Plot No.3 & 4. | Vishw apartment
43 | Remark No. 42 is resolved by corrigendum (i.e. correction letter) provided by authority regarding survey nos. letter attached below.
44 | As per approved Floor plans does not consist of Unit Numbering, We have considered unit numbering from sale plan provided by site meet person during site visit.
45 | As per New version of RERA portal project consist of single building - Hasha Heights As per Old version of RERA portal project consist of Two buildings- Hasha Heights & Kunti Heights
46 | Remark No.11 is solved. we were asked to follow the old version of RERA by the bank official builder letter provided on the mail is attached below.
47 | The approved large land parcel layout plan does not consist of survey number, therefore we have referred Survey No. from Title Certificate.
48 | As per the discussion with the bank official, Builder provided approved EC on whatsapp for a large land parcel.
49 | As per the approved floor plan, out of 1199 flats, there are 132 flats that are "I to R" flats. Please check from your end. | Mahindra Vista Phase 1 & 2
50 | As per the approved plans & RERA in the project Shikara Heights Phase I consist of " Wing A, B, C " for Sale & " Wing D " for Rehab Therefore we have not considered Rehab Wing D in APF Report.
51 | As per Google Maps, we have observed that some plants or trees are surrounding of theproject (it plants might be mangroves also). | The Royal Bay
52 | As per the revised approved plan dated 08/09/2022, the approved structure of Wing A is reduced to Gr + 1st to 14th Floor (earlier it was Wing A = Gr + 1st to 15th Floor) | Balaji Govind
53 | As per the approved floor plan dtd.22/07/2024, the building height is 61.55 Mtrs (Upto OHT), which is reached up to his maximum height limit of 61.73 Mtrs with reference to the airport NOC. | The Domus Prive
54 | As per visit dtd 13/08/2025, we have observed that construction work of Shop no. 1, 2, 3, 6, 7, 8 from Building No. 1 and Shop no. 11, 12, 13, 16, 17 from Building No. 2 are Completed.Therefore it can be considered as Progress 100% and Disbursement 100%. | Remark if shops construction is asked
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## Construction Table
Jio Finance Table
Construction details: |  | Ground + 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 65% |  | 80% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20