## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [7 empty] | CC Renewal Letter Query
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-10-03
Branch Name/ID |  | Mahindra Rural Housing Finance - Panvel |  |  | Date & Time of Site Visit | 04/10/2025 at 11:27
Name of the person met at site & Contact No |  | Mr. Sambhaji 9822165022 |  |  | Date of Report Release | 04/10/2025
Project Details
Name of the project |  | Himalaya Gardens
Address |  | Himalaya Gardens, Survey No.8/1, 8/2A/1 & S No.9/1B, near Tulsi V City, Internal Road, Pashane, Vangani, Karjat, Raigad - 410101. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 8/1, 8/2A/1 & S No.9/1B | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Pashane | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Internal Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Vangani | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Karjat | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Raigad | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 410101 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P52000034333 | [11 empty] | Mahad | Daund
Landmark |  | Tulsi V City | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.107824,73.316795 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/mrBTG7jPaeXd5CiC6 | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Himalaya Builders And Developers LLP | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Unit No. 215, Commodity Exchange Building, Sector - 19, Vashi, Thane - 400705 | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | Not Provided | [5 empty] | Not Found on RERA site also
Contact No. |  | Mr. Mahesh Pawar 9588129999 / 8451948604
Location of the project Municipal Limit : |  | Collector Of Raigad
Project Type (Apartments/Plot/ Combined) |  | Apartments + Shops
No of Wings / Buildings |  | 3 |  | Other HFC's Approval / Funding |  | None
No. of Tenements / Units in Project |  | Flats - 74 |  | Exposure Limit (Proposed) |  | 11.1
Approved No. of Floor |  | Building No.10, 11, 12 = G + 1st to 4th Floor
Proposed No. of Floor |  | Building No.10, 11, 12 = G + 1st to 4th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | 4.75M Wide Internal Road | Other Plot | Other Plot | 9.00M Wide Existing Road
|  | Physical on site |  | Internal Road | Open Plot | Open Plot | Internal Road
Verification of survey No. (Title document) |  | Survey No. 8/1, 8/2A/1 & 9/1B
Plot area mentioned in the sale deed (As per 7/12) |  | 11990 Sq.mt |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 10619.1 Sq.mt
Approach road |  | Yes, Approx 18ft
Connectivity |  | 1) 1.6KM from R.Z.P Upper Primary English School 2) 2.7KM from Caliber Convent School 3) 2.4KM from Primary Health Care Vangani 4) 14.6KM from Gurudev Multi Speciality Hospital 5) 0.85KM from Shree Raigad Kirana and Vegetables 6) 3.2KM from Maharashtra Kirana Stores 7) 3.4KM from Green Market 8) 1.4KM from Shiv Mandir 9) 0.80KM from Karav - Vangani Auto Stand 10) 3.2KM from Vangani Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 10619.1 |  | 1.0888
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | -0.011212
|  | Total FSI availaible for the project |  |  |  | 1.0888
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 11681.01
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 11561.95
Building plan approvals - Approval No : |  | MS/LNA-1/S.R/93/2016 Date - 28/02/2017
Building height / No. of Floors |  | Building No.10, 11, 12 = G + 1st to 4th Floor (Height = 14.70m)
Construction/Building Permission |  | MSH/L.N.A.1(B)/S.R.93/2016 Date - 28/02/2017 Valid Upto - Building No. 10, 11, 12 = G + 1st to 4th Floor (B.U.A = 11561.95 Sq.mt) | [5 empty] | NA cum CC
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA
|  | Validity & area : mentioned |  | Date - Area -
Other statutory permissions (Fire NOC/ Environmental Clearance/ Airport NOC) |  | NA
CONSTRUCTION PROGRESS
Baseline start date |  | 2022-04-04 |  | Baseline finish date | 2025-09-30
Construction details:
Building No. 10, 11 & 12 = Gr + 1st + 4th Floor |  |  |  | Basement | Ground | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
|  |  |  | 0 | 1 | 0 | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1
Excavation |  | 0% |  | 4 | 100% | 91.25% |  | Excavation in process | 2
Plinth |  | 10% |  | 4 | 100% |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 40% |  | 5 | 100% |  |  | Footing in Process | 1
Brickwork |  | 15% |  | 4 | 100% |  |  | Footing Completed | 2
Internal Plaster |  | 5% |  | 4 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 4 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 4 | 100% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 3 | 75% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 2 | 50% |  |  | Plinth in process | 3
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 4
Building No. 11 = Gr + 1st + 4th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 3 Floor Completed
|  |  |  | 0 | 1 | 0 | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1
Excavation |  | 0% |  | 4 | 100% | 88.75% |  | Excavation in process | 2
Plinth |  | 10% |  | 4 | 100% |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 40% |  | 5 | 100% |  |  | Footing in Process | 1
Brickwork |  | 15% |  | 4 | 100% |  |  | Footing Completed | 2
Internal Plaster |  | 5% |  | 4 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 4 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 4 | 100% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 3 | 75% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 3
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 4
Building No. 12 = Gr + 1st + 4th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 3 Floor Completed
|  |  |  | 0 | 1 | 0 | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1
Excavation |  | 0% |  | 4 | 100% | 88.75% |  | Excavation in process | 2
Plinth |  | 10% |  | 4 | 100% |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 40% |  | 5 | 100% |  |  | Footing in Process | 1
Brickwork |  | 15% |  | 4 | 100% |  |  | Footing Completed | 2
Internal Plaster |  | 5% |  | 4 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 4 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 4 | 100% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 3 | 75% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 3
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 4
General comment on progress |  | Speed of Construction is Slow.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building no. 13 Shops |  | 15 |  | 2254.5198 |  | 3269.0537
Total |  | 15 |  | 2254.5198 |  | 3269.0537
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.10 Flats |  | 18 |  | 6938.0438 |  | 10060.1636
Building No.11 Flats |  | 38 |  | 12414.9823 |  | 18001.7244
Building No.12 Flats |  | 18 |  | 6938.0438 |  | 10060.1636
Building No.13 Flats |  | 46 |  | 17802.5258 |  | 25813.6624
Total |  | 74 |  | 26291.07 |  | 38122.0515
Grand Total |  | 89 |  | 28545.5898 |  | 41391.1052
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.13
Ground Floor For Commercial, Residential & Parking
1 |  | Shop | 122.4943 | 0 | 122.4943 | 0 | 177.6168
2 |  | Shop | 147.2515 | 0 | 147.2515 | 0 | 213.5147 | 12.7958
3 |  | Shop | 137.4563 | 0 | 137.4563 | 0 | 199.3116
4 |  | Shop | 174.915 | 0 | 174.915 | 0 | 253.6267 | 16.008
5 |  | Shop | 164.6892 | 0 | 164.6892 | 0 | 238.7993
6 |  | Shop | 124.97 | 0 | 124.97 | 0 | 181.2066
7 |  | Shop | 124.97 | 0 | 124.97 | 0 | 181.2066
8 |  | Shop | 164.6892 | 0 | 164.6892 | 0 | 238.7993
9 |  | Shop | 135.6264 | 0 | 135.6264 | 0 | 196.6583
10 |  | Shop | 111.7303 | 0 | 111.7303 | 0 | 162.009
11 |  | Shop | 164.6892 | 0 | 164.6892 | 0 | 238.7993
12 |  | Shop | 164.6892 | 0 | 164.6892 | 0 | 238.7993 | 14.964
13 |  | Shop | 110.2234 | 0 | 110.2234 | 0 | 159.8239
14 |  | Shop | 109.9004 | 0 | 109.9004 | 0 | 159.3556
15 |  | Shop | 296.2253 | 0 | 296.2253 | 0 | 429.5267
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | WS area + Encl Balcony + CB Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: |  |  | 10.764
45%
Building No.10
Ground Floor For Residential & Parking
1 |  | 1BHK | 296.2253 | 0 | 296.2253 | 0 | 429.5267 | 26.023
2 |  | 1BHK | 296.2253 | 0 | 296.2253 | 0 | 429.5267
1st, 2nd, 3rd & 4th Floor
1 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694 | 30.6085
2 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
3 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
4 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
Building No.11
Ground Floor For Residential & Parking
1 |  | 1BHK | 290.628 | 0 | 290.628 | 0 | 421.4106 | 26.2655
2 |  | 1RK | 188.37 | 0 | 188.37 | 0 | 273.1365
3 |  | 1RK | 213.4501 | 0 | 213.4501 | 0 | 309.5027
4 |  | 1RK | 213.4501 | 0 | 213.4501 | 0 | 309.5027
5 |  | 1RK | 188.37 | 0 | 188.37 | 0 | 273.1365 | 17.1711
6 |  | 1BHK | 290.628 | 0 | 290.628 | 0 | 421.4106
1st, 2nd, 3rd & 4th Floor
1 |  | 1BHK | 373.3762 | 32.6956 | 406.0719 | 0 | 588.8043
2 |  | 1BHK | 391.5405 | 50.8599 | 442.4004 | 0 | 641.4806
3 |  | 1RK | 210.4093 | 22.0393 | 232.4486 | 0 | 337.0504
4 |  | 1RK | 231.2107 | 17.7606 | 248.9713 | 0 | 361.0084
5 |  | 1RK | 231.2107 | 17.7606 | 248.9713 | 0 | 361.0084
6 |  | 1RK | 290.628 | 0 | 290.628 | 0 | 421.4106
7 |  | 1BHK | 392.3478 | 51.6672 | 444.015 | 0 | 643.8217 |  | 2640.4824
8 |  | 1BHK | 392.3478 | 51.6672 | 444.015 | 0 | 643.8217
Building No.12
Ground Floor For Residential & Parking
1 |  | 1BHK | 296.2253 | 0 | 296.2253 | 0 | 429.5267
2 |  | 1BHK | 296.2253 | 0 | 296.2253 | 0 | 429.5267
1st, 2nd, 3rd & 4th Floor
1 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
2 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
3 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
4 |  | 1BHK | 340.573 | 56.0266 | 396.5996 | 0 | 575.0694
Building No.13
Ground Floor For Commercial, Residential & Parking
1 |  | 1BHK | 290.3051 | 0 | 290.3051 | 0 | 420.9424
2 |  | 1RK | 230.3496 | 0 | 230.3496 | 0 | 334.0069
1st Floor
1 |  | 1BHK | 396.9225 | 56.3495 | 453.272 | 0 | 657.2445
2 |  | 1BHK | 340.573 | 56.3495 | 396.9225 | 0 | 575.5376
3 |  | 1BHK | 336.5903 | 63.0501 | 399.6404 | 0 | 579.4786
4 |  | 1BHK | 337.882 | 63.6152 | 401.4972 | 0 | 582.1709
5 |  | 1RK | 270.1764 | 56.3495 | 326.5259 | 0 | 473.4626
6 |  | 1BHK | 414.7369 | 56.3495 | 471.0865 | 0 | 683.0754
7 |  | 1BHK | 339.6042 | 38.266 | 377.8702 | 0 | 547.9118
8 |  | 1BHK | 388.9033 | 38.1046 | 427.0079 | 0 | 619.1614
9 |  | 1BHK | 373.5108 | 62.0814 | 435.5922 | 0 | 631.6086
10 |  | 1RK | 254.3533 | 42.3832 | 296.7366 | 0 | 430.268
11 |  | 1RK | 231.7489 | 38.266 | 270.0149 | 0 | 391.5217
2nd, 3rd & 4th Floor
1 |  | 1BHK | 340.573 | 55.2193 | 395.7923 | 0 | 573.8988
2 |  | 1BHK | 340.573 | 55.2193 | 395.7923 | 0 | 573.8988
3 |  | 1BHK | 336.5903 | 63.0501 | 399.6404 | 0 | 579.4786
4 |  | 1BHK | 344.448 | 62.9694 | 407.4174 | 0 | 590.7552
5 |  | 1BHK | 364.3614 | 61.6777 | 426.0391 | 0 | 617.7567
6 |  | 1RK | 244.3428 | 40.8494 | 285.1922 | 0 | 413.5287
7 |  | 1BHK | 339.6042 | 80.2456 | 419.8498 | 0 | 608.7822
8 |  | 2BHK | 519.0401 | 88.803 | 607.8431 | 0 | 881.3725
9 |  | 1RK | 244.3428 | 44.4015 | 288.7443 | 0 | 418.6792
10 |  | 1RK | 244.3428 | 44.4015 | 288.7443 | 0 | 418.6792
11 |  | 1BHK | 364.3614 | 62.485 | 426.8464 | 0 | 618.9273
Ground Floor For Residential & Parking
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
1st Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3200
Recommended of Parking ( If Available) |  |  |  |  | 1,00,000/-
REMARKS ON RECOMMENDATION
1 | Some flats are occupied by tenants but Construction work same as last visit dtd 12/12/2024 but work is in process. (Lift & Finishing work is Pending).
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Very Few Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + WS Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 45%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Dashrath vele 9403337330.
11 | The project has received first CC dated 28/02/2017 but still buildings are under construction. Please provide a CC renewal letter.
12 | As per RERA, the project consists of 10 to 13 buildings; as per bank officers requests, we have done APF for 10 to 12 buildings only.
13 | As per RERA, completion period of project Himalaya Gardens is expired on 30/09/2025 but still project is under construction.
Photographs Of Property : |  | Himalaya Gardens
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Naynesh Sunil Lovanshi |  | Authorized Signatory Name & Seal of the agency
Bldg
No.10
Bldg
No.11
Bldg No.12
Bldg No.13
1
2
3
4
5
Himalaya Gardens Phase 3
6
7
8
9
Phase 1
Phase 2
10
11
12
13
1
2
3
4
9
8
5
6
7
N
10
12
11
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C54: RERA Start date
Note on F54: RERA completion date
Note on H100: if multiple buildings are in project and are connected internally
Note on C102: AAC Block or Brick
Note on H104: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3