## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 04/10/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-10-03
Name of the builder group |  |  |  | M/s.Swaminarayan Life Space LLP
Name of the builder company |  |  |  | M/s.Swaminarayan Life Space LLP
Name of the Project |  |  |  | Swaminarayan City Phase 1, 1A, 1B & 1C
Contact Details ( Name & Contact No.) |  |  |  | Mr.Mahajan 9372246443
Name / No of the Building |  |  |  | Phase 1 Phase 1A Phase 1B Phase 1C | Tower A Athena Tower B Almada Tower C Aveiro Tower D Estonia Tower H Amadora Tower G Georgia Tower E Adonia Tower F Fiona |  |  | Please check the nomenclature.
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Phase 1 = P51700018305 Phase 1A = P51700019326 Phase 1B = P51700031749 Phase 1C = P51700049570
Project location details |  | Swaminarayan City Phase 1, 1A, 1B & 1C, CTS No.60/7, 60/8, 61/21, 61/51, 61/58, 61/80, 61/95, 61/75C, 61/81, 61/17, 61/18, 61/20, 61/52, 61/53, 61/54, 61/55, 61/56, 61/57, near Swastik Heights, Reti Bunder Road, Thakurli, Thakurli, Kalyan, Thane.
CTS No |  | 60/7, 60/8, 61/21, 61/51, 61/58, 61/80, 61/95, 61/75C, 61/81, 61/17, 61/18, 61/20, 61/52, 61/53, 61/54, 61/55, 61/56, 61/57
Road |  | Reti Bunder Road |  | Village |  | Thakurli
City |  | Thakurli |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421202
Nearby Landmark |  | Swastik Heights |  | Distance from city centre: |  | 3.3 Km from Thakurli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Building
North | NA | NA |  |  | Building
South | NA | NA |  |  | Reti Bunder Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.2278343,73.0711571
Location Link |  | https://goo.gl/maps/SSxf3PAAuBuFXSMn9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 23396.95
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.050467
Total FSI availaible for the project |  |  |  | 1.1505
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 26917.42
Total number of Buildings |  |  |  | 08 Buildings
Approval Detail : Plan approval
Phase 1 (Tower A, B & C)
Layout Approval No |  | KDMC/TPD/BP/DOM/2018-19/0026/156 |  |  | Dated | 18/03/2021.
Approved Floor plan No. |  | KDMC/TPD/BP/DOM/2018-19/0026/156 |  |  | Dated | 18/03/2021.
Commencement Certificate No. |  | KDMC/TPD/BP/DOM/2018-19/0026/156 |  |  | Dated | 18/03/2021.
Valid Up to: Phase 1(Tower A, B & C) = St/Gr + P + 24th Floor
Phase 1A (Tower D & H) Phase 1B(Tower G) Phase 1C(Tower E & F)
Layout Approval No |  | KDMC/TPD/BP/DOM/2018-19/0026/294 |  |  | Dated | 2022-10-19
Approved Floor plan No. |  | KDMC/TPD/BP/DOM/2018-19/0026/294 |  |  | Dated | 2022-10-19
Commencement Certificate No. Valid Up to: |  | KDMC/TPD/BP/DOM/2018-19/0026/294 |  |  | Dated | 2022-10-19
Phase 1A(Tower D) = St/Gr + 1st to 28th Floor Phase 1A(Tower H)= St/Gr + 1st to 24th Floor Phase 1C(Tower E & F) = St/Gr + 1st to 35th Floor Phase 1B(Tower G) = St/Gr + 1st to 33rd Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 26917.42
Approved no of units |  |  | Flats - 1625, Shops - 119, Office - 23
Approved no of Floors |  |  | Tower A, B & C = St/Gr + P + 2nd to 24th Floor Tower D = St/Gr + 1st to 28th Floor Tower E & F = St/Gr + 1st to 35th Floor Tower G = St/Gr + 1st to 33rd Floor Tower H = St/Gr + 1st to 24th Floor
Proposed no of Floors |  |  | Tower A & B = St/Gr + P + 2nd to 24th Floor
Tower C = St/Gr + P + 2nd to 24th Floor
Tower D = St/Gr + 1st to 28th Floor
Tower E = St/Gr + 1st to 35th Floor
Tower F = St/Gr + 1st to 35th Floor
Tower G = St/Gr + 1st to 33rd Floor
Tower H = St/Gr + 1st to 24th Floor
Expected Completion |  |  | As per RERA - 30/06/2027.
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Nothing
Construction details: |  | Tower A, B & C = St/Gr + P + 2nd to 24th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 100% |  | 100% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 24 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 24 | 100% |  |  |  |  | Plinth in process | 18
Possession |  | 24 | 100% |  |  |  |  | Plinth completed | 24
Progress % |  | 100% |  | Disbursement % |  | 100%
Construction details: |  | Tower C = St/Gr + P + 2nd to 24th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 100% |  | 100% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 24 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 24 | 100% |  |  |  |  | Plinth in process | 18
Possession |  | 24 | 100% |  |  |  |  | Plinth completed | 24
Construction details: |  | Tower D = St/Gr + 1st to 28th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 26 Floor, Internal Plaster upto 25 Floor, External Plaster upto 18 Floor, Flooring upto 8 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 26 Floor, Internal Plaster upto 25 Floor, External Plaster upto 18 Floor, Flooring upto 8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 72.95% |  | 88.75% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 29 | 100% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 26 | 92.86% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 25 | 89.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 64.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 28.57% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | Tower E = St/Gr + 1st to 35th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 35
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.75
Excavation |  | 35 | 100% | 37.86% |  | 64.65% |  | Excavation in process | 17.5
Plinth |  | 35 | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 17 | 47.22% |  |  |  |  | Footing in Process | 8.75
Brickwork | Brickwork & Internal Plaster | 16 | 45.71% |  |  |  |  | Footing Completed | 17.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 34.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10.4 | 29.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 26.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 35
Construction details: |  | Tower F = St/Gr + 1st to 35th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 11 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 35
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.75
Excavation |  | 35 | 100% | 25.69% |  | 56.57% |  | Excavation in process | 17.5
Plinth |  | 35 | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 12 | 33.33% |  |  |  |  | Footing in Process | 8.75
Brickwork | Brickwork & Internal Plaster | 11 | 31.43% |  |  |  |  | Footing Completed | 17.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 26.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 35
Construction details: |  | Tower G = St/Gr + 1st to 33rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 11.2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 33
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 11.2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.25
Excavation |  | 33 | 100% | 39.76% |  | 65.94% |  | Excavation in process | 16.5
Plinth |  | 33 | 100% |  |  |  |  | Excavation Completed | 33
RCC (Including podiums) |  | 17 | 50% |  |  |  |  | Footing in Process | 8.25
Brickwork | Brickwork & Internal Plaster | 16 | 48.48% |  |  |  |  | Footing Completed | 16.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 36.36% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11.2 | 33.94% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 33
Construction details: |  | Tower H = St/Gr + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 22 Floor, Painting upto 22 Floor, Finishing upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 22 Floor, Painting upto 22 Floor, Finishing upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 89.79% |  | 94.58% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 91.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 91.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 20.83% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Wheather the construction is as per approved Building plan : |  |  |  |  | Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8250
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 18000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 13000
Floor Rise Rate Per Sq.ft from 2nd Floor |  |  |  |  | 21
Development Charges |  |  |  |  | 350000
Club Charges |  |  |  |  | 250000
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 6600
Commercial Area Details :
Building & Tower |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 23 |  | 12698.3984 |  | 20317.4375
D Tower Shop |  | 66 |  | 40217.8981 |  | 64348.637
E & F Tower Shop |  | 30 |  | 35015.5955 |  | 56024.9529
Total |  | 119 |  | 87931.8921 |  | 140691.0273
Office |  | 23 |  | 9745.0798 |  | 15592.1276
Residential Area Details :
Building & Tower |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Tower |  | 179 |  | 98207.2861 |  | 147682.6756
B Tower |  | 179 |  | 98207.2861 |  | 147682.6756
C Tower |  | 179 |  | 98207.2861 |  | 147699.3733
D Tower |  | 126 |  | 132478.5113 |  | 199516.9939
E Tower |  | 313 |  | 147435.7459 |  | 222083.9782
F Tower |  | 249 |  | 142425.1846 |  | 214288.1512 |  |  | 24
G Tower |  | 224 |  | 83081.7187 |  | 125181.0951
H Tower |  | 176 |  | 96037.6351 |  | 144268.4526 |  |  | 24
Total |  | 1625 |  | 896080.6539 |  | 1348403.3956
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Phase 1
A, B & C Tower
Ground Floor For Commercial & Parking
1 |  | Shop | 461.9909 | 0 | 739.1854 | Ground Floor For Commercial & Parking
2 |  | Shop | 645.9476 | 0 | 1033.5162
3 |  | Shop | 608.0584 | 0 | 972.8934 |  |  | 39.6 | 7.92
4 |  | Shop | 325.0728 | 0 | 520.1165
5 |  | Shop | 325.0728 | 0 | 520.1165
6 |  | Shop | 608.0584 | 0 | 972.8934
7 |  | Shop | 671.9965 | 0 | 1075.1944
8 |  | Shop | 617.9612 | 0 | 988.738
9 |  | Shop | 666.9374 | 0 | 1067.0999
10 |  | Shop | 671.9965 | 0 | 1075.1944
11 |  | Shop | 608.0584 | 0 | 972.8934
12 |  | Shop | 325.0728 | 0 | 520.1165
13 |  | Shop | 608.0584 | 0 | 972.8934
14 |  | Shop | 671.9965 | 0 | 1075.1944
15 |  | Shop | 617.9612 | 0 | 988.738
16 |  | Shop | 617.9612 | 0 | 988.738
17 |  | Shop | 671.9965 | 0 | 1075.1944
18 |  | Shop | 608.0584 | 0 | 972.8934
19 |  | Shop | 325.0728 | 0 | 520.1165
20 |  | Shop | 325.0728 | 0 | 520.1165
21 |  | Shop | 608.0584 | 0 | 972.8934
22 |  | Shop | 645.9476 | 0 | 1033.5162
23 |  | Shop | 461.9909 | 0 | 739.1854
1st Floor For Commercial & Parking
101 |  | Office | 436.0496 | 0 | 697.6794 | 1st Floor For Commercial & Parking
102 |  | Office | 488.0398 | 0 | 780.8636
103 |  | Office | 479.9668 | 0 | 767.9468
104 |  | Office | 265.0097 | 0 | 424.0155
105 |  | Office | 265.0097 | 0 | 424.0155
106 |  | Office | 479.9668 | 0 | 767.9468
107 |  | Office | 485.9946 | 0 | 777.5914
108 |  | Office | 437.0184 | 0 | 699.2294
109 |  | Office | 437.0184 | 0 | 699.2294
110 |  | Office | 485.9946 | 0 | 777.5914
111 |  | Office | 479.9668 | 0 | 767.9468
112 |  | Office | 265.0097 | 0 | 424.0155
113 |  | Office | 479.9668 | 0 | 767.9468
114 |  | Office | 485.9946 | 0 | 777.5914
115 |  | Office | 437.0184 | 0 | 699.2294
116 |  | Office | 436.0496 | 0 | 697.6794
117 |  | Office | 488.0398 | 0 | 780.8636
118 |  | Office | 479.9668 | 0 | 767.9468
119 |  | Office | 265.0097 | 0 | 424.0155
120 |  | Office | 265.0097 | 0 | 424.0155
121 |  | Office | 479.9668 | 0 | 767.9468
122 |  | Office | 485.9946 | 0 | 777.5914
123 |  | Office | 437.0184 | 0 | 699.2294
Phase 1A
D Tower
Ground Floor For Commercial & Parking
13 |  | Shop | 303.8031 | 0 | 486.085 | Ground Floor For Commercial & Parking
14 |  | Shop | 207.5084 | 0 | 332.0134
15 |  | Shop | 2078.4746 | 0 | 3325.5593
16 |  | Shop | 184.7102 | 0 | 295.5364
17 |  | Shop | 154.8488 | 0 | 247.758 |  |  | 39.6 | 7.92
18 |  | Shop | 184.7102 | 0 | 295.5364
19 |  | Shop | 162.545 | 0 | 260.072
20 |  | Shop | 184.7102 | 0 | 295.5364
21 |  | Shop | 162.545 | 0 | 260.072
22 |  | Shop | 184.7102 | 0 | 295.5364
23 |  | Shop | 162.545 | 0 | 260.072
24 |  | Shop | 184.7102 | 0 | 295.5364
25 |  | Shop | 162.545 | 0 | 260.072
26 |  | Shop | 237.0233 | 0 | 379.2372
27 |  | Shop | 262.0754 | 0 | 419.3207
28 |  | Shop | 197.627 | 0 | 316.2033
29 |  | Shop | 405.5875 | 0 | 648.94
30 |  | Shop | 129.0604 | 0 | 206.4966
31 |  | Shop | 80.73 | 0 | 129.168
32 |  | Shop | 123.4545 | 0 | 197.5272
33 |  | Shop | 205.8615 | 0 | 329.3784
34 |  | Shop | 205.8615 | 0 | 329.3784
35 |  | Shop | 230.8878 | 0 | 369.4205
36 |  | Shop | 240.5754 | 0 | 384.9206
37 |  | Shop | 180.7663 | 0 | 289.2261
38 |  | Shop | 7163.2267 | 0 | 11461.1628
1st Floor For Commercial
39A |  | Shop | 15952.248 | 0 | 25523.5968 | 1st Floor For Commercial
2nd Floor For Commercial
201 |  | Shop | 385.4373 | 0 | 616.6997 | 2nd Floor For Commercial
202 |  | Shop | 385.954 | 0 | 617.5264
203 |  | Shop | 253.6214 | 0 | 405.7942
204 |  | Shop | 252.9432 | 0 | 404.7092
205 |  | Shop | 253.2823 | 0 | 405.2517 |  |  | 39.6 | 7.92
206 |  | Shop | 253.2823 | 0 | 405.2517
207 |  | Shop | 252.1402 | 0 | 403.4244
208 |  | Shop | 252.4782 | 0 | 403.9652
209 |  | Shop | 252.1402 | 0 | 403.4244
210 |  | Shop | 206.8496 | 0 | 330.9594
211 |  | Shop | 252.9432 | 0 | 404.7092
212 |  | Shop | 207.8475 | 0 | 332.5559
213 |  | Shop | 2333.7428 | 0 | 3733.9885
214 |  | Shop | 138.5327 | 0 | 221.6523
215 |  | Shop | 154.8488 | 0 | 247.758
216 |  | Shop | 138.5327 | 0 | 221.6523
217 |  | Shop | 154.8488 | 0 | 247.758
218 |  | Shop | 138.5327 | 0 | 221.6523
219 |  | Shop | 154.8488 | 0 | 247.758
220 |  | Shop | 138.5327 | 0 | 221.6523
221 |  | Shop | 154.8488 | 0 | 247.758
222 |  | Shop | 138.5327 | 0 | 221.6523
223 |  | Shop | 154.8488 | 0 | 247.758
224 |  | Shop | 138.5327 | 0 | 221.6523
225 |  | Shop | 162.545 | 0 | 260.072
226 |  | Shop | 109.1211 | 0 | 174.5938
227 |  | Shop | 180.7663 | 0 | 289.2261
228 |  | Shop | 179.5435 | 0 | 287.2696
229 |  | Shop | 80.73 | 0 | 129.168
230 |  | Shop | 123.4545 | 0 | 197.5272
231 |  | Shop | 205.8615 | 0 | 329.3784
232 |  | Shop | 205.8615 | 0 | 329.3784
233 |  | Shop | 230.8878 | 0 | 369.4205
234 |  | Shop | 240.5754 | 0 | 384.9206
235 |  | Shop | 315.2022 | 0 | 504.3235
236 |  | Shop | 446.6371 | 0 | 714.6194
237 |  | Shop | 184.5208 | 0 | 295.2333
238 |  | Shop | 235.3689 | 0 | 376.5902
239 |  | Shop | 235.3689 | 0 | 376.5902
Phase 1C
E & F Tower
Ground Floor For Commercial & Parking
1 |  | Shop | 385.405 | 0 | 616.648 | Ground Floor For Commercial & Parking
2 |  | Shop | 359.7329 | 0 | 575.5726
3 |  | Shop | 1062.1646 | 0 | 1699.4634
4 |  | Shop | 1062.1646 | 0 | 1699.4634
5 |  | Shop | 359.7329 | 0 | 575.5726 |  |  | 39.6 | 7.92
6 |  | Shop | 9627.214 | 0 | 15403.5423
1st Floor For Commercial
1 |  | Shop | 742.4717 | 0 | 1187.9547 | 1st Floor For Commercial
2 |  | Shop | 717.2355 | 0 | 1147.5767
3 |  | Shop | 318.6682 | 0 | 509.8692
4 |  | Shop | 296.2253 | 0 | 473.9604
5 |  | Shop | 948.0662 | 0 | 1516.9059 |  |  | 39.6 | 7.92
6 |  | Shop | 948.0662 | 0 | 1516.9059
7 |  | Shop | 296.2253 | 0 | 473.9604 |  |  | 39.6 | 7.92
8 |  | Shop | 9627.214 | 0 | 15403.5423
2nd Floor For Commercial
1 |  | Shop | 668.6306 | 0 | 1069.809 | 2nd Floor For Commercial
2 |  | Shop | 645.5472 | 0 | 1032.8756
3 |  | Shop | 252.2651 | 0 | 403.6242
4 |  | Shop | 233.0352 | 0 | 372.8563
5 |  | Shop | 636.26 | 0 | 1018.0161 |  |  | 39.6 | 7.92
6 |  | Shop | 636.26 | 0 | 1018.0161
7 |  | Shop | 233.0352 | 0 | 372.8563 |  |  | 39.6 | 7.92
8 |  | Shop | 389.899 | 0 | 623.8384
9 |  | Shop | 491.9428 | 0 | 787.1085
10 |  | Shop | 397.1916 | 0 | 635.5066
11 |  | Shop | 456.7703 | 0 | 730.8325
12 |  | Shop | 392.5093 | 0 | 628.0148
13 |  | Shop | 352.6556 | 0 | 564.2489 |  |  | 39.6 | 7.92
14 |  | Shop | 371.5464 | 0 | 594.4742
15 |  | Shop | 631.9587 | 0 | 1011.134 |  |  | 39.6 | 7.92
16 |  | Shop | 1475.5022 | 0 | 2360.8035
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Phase 1
Tower A
1st Podium Floor
2nd Floor for Residential
201 |  | 2BHK | 652.9765 | 356.692 | 1068.6378 | 2nd Floor for Residential
202 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
203 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
204 |  | 2BHK | 652.9765 | 356.692 | 1068.6378
205 |  | 2BHK | 652.9765 | 0 | 979.4648
206 |  | Recreational Area
207 |  | 1BHK | 438.3155 | 0 | 657.4732
208 |  | 2BHK | 652.9765 | 0 | 979.4648
3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor
301,..,2401 |  | 2BHK | 652.9765 | 0 | 979.4648 | 3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor |  |  |  |  | 301,..,2401 | 301 | 2401
302,..,2402 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 302,..,2402 | 302 | 2402
303,..,2403 |  | 1BHK | 438.3155 | 0 | 657.4732 |  |  | 8212.1219 | 253.7472 | 21.1456 | 303,..,2403 | 303 | 2403
304,..,2404 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 304,..,2404 | 304 | 2404
305,..,2405 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 305,..,2405 | 305 | 2405
306,..,2406 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 306,..,2406 | 306 | 2406
307,..,2407 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 307,..,2407 | 307 | 2407
308,..,2408 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 308,..,2408 | 308 | 2408
7th, 12th, 17th, 22nd Floor (Part Refuge Area)
701,..,2201 |  | 2BHK | 652.9765 | 0 | 979.4648 | 7th, 12th, 17th, 22nd Floor (Part Refuge Area) |  |  |  |  | 701,..,2201 | 701 | 2201
702,..,2202 |  | Refuge Area | [8 empty] | 702,..,2202 | 702 | 2202
703,..,2203 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 703,..,2203 | 703 | 2203
704,..,2204 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 704,..,2204 | 704 | 2204
705,..,2205 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 705,..,2205 | 705 | 2205
706,..,2206 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 706,..,2206 | 706 | 2206
707,..,2207 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 707,..,2207 | 707 | 2207
708,..,2208 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 708,..,2208 | 708 | 2208
Tower B
2nd Floor for Residential
201 |  | 2BHK | 652.9765 | 356.692 | 1068.6378 | 2nd Floor for Residential
202 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
203 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
204 |  | 2BHK | 652.9765 | 356.692 | 1068.6378
205 |  | 2BHK | 652.9765 | 0 | 979.4648
206 |  | Recreational Area
207 |  | 1BHK | 438.3155 | 0 | 657.4732
208 |  | 2BHK | 652.9765 | 0 | 979.4648
3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor
301,..,2401 |  | 2BHK | 652.9765 | 0 | 979.4648 | 3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor |  |  |  |  | 301,..,2401 | 301 | 2401
302,..,2402 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 302,..,2402 | 302 | 2402
303,..,2403 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 303,..,2403 | 303 | 2403
304,..,2404 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 304,..,2404 | 304 | 2404
305,..,2405 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 305,..,2405 | 305 | 2405
306,..,2406 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 306,..,2406 | 306 | 2406
307,..,2407 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 307,..,2407 | 307 | 2407
308,..,2408 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 308,..,2408 | 308 | 2408
7th, 12th, 17th, 22nd Floor (Part Refuge Area)
701,..,2201 |  | 2BHK | 652.9765 | 0 | 979.4648 | 7th, 12th, 17th, 22nd Floor (Part Refuge Area) |  |  |  |  | 701,..,2201 | 701 | 2201
702,..,2202 |  | Refuge Area | [8 empty] | 702,..,2202 | 702 | 2202
703,..,2203 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 703,..,2203 | 703 | 2203
704,..,2204 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 704,..,2204 | 704 | 2204
705,..,2205 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 705,..,2205 | 705 | 2205
706,..,2206 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 706,..,2206 | 706 | 2206
707,..,2207 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 707,..,2207 | 707 | 2207
708,..,2208 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 708,..,2208 | 708 | 2208
Tower C
2nd Floor for Residential
201 |  | 2BHK | 652.9765 | 423.4827 | 1085.3355 | 2nd Floor for Residential
202 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
203 |  | 1BHK | 438.3155 | 290.1006 | 754.1734
204 |  | 2BHK | 652.9765 | 356.692 | 1068.6378
205 |  | 2BHK | 652.9765 | 0 | 979.4648
206 |  | Recreational Area
207 |  | 1BHK | 438.3155 | 0 | 657.4732
208 |  | 2BHK | 652.9765 | 0 | 979.4648
3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor
301,..,2401 |  | 2BHK | 652.9765 | 0 | 979.4648 | 3rd, 4th, 5th, 6th, 8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th Floor |  |  |  |  | 301,..,2401 | 301 | 2401
302,..,2402 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 302,..,2402 | 302 | 2402
303,..,2403 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 303,..,2403 | 303 | 2403
304,..,2404 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 304,..,2404 | 304 | 2404
305,..,2405 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 305,..,2405 | 305 | 2405
306,..,2406 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 306,..,2406 | 306 | 2406
307,..,2407 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 307,..,2407 | 307 | 2407
308,..,2408 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 308,..,2408 | 308 | 2408
7th, 12th, 17th, 22nd Floor (Part Refuge Area)
701,..,2201 |  | 2BHK | 652.9765 | 0 | 979.4648 | 7th, 12th, 17th, 22nd Floor (Part Refuge Area) |  |  |  |  | 701,..,2201 | 701 | 2201
702,..,2202 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 702,..,2202 | 702 | 2202
703,..,2203 |  | Refuge Area | [8 empty] | 703,..,2203 | 703 | 2203
704,..,2204 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 704,..,2204 | 704 | 2204
705,..,2205 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 705,..,2205 | 705 | 2205
706,..,2206 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 706,..,2206 | 706 | 2206
707,..,2207 |  | 1BHK | 438.3155 | 0 | 657.4732 | [5 empty] | 707,..,2207 | 707 | 2207
708,..,2208 |  | 2BHK | 652.9765 | 0 | 979.4648 | [5 empty] | 708,..,2208 | 708 | 2208
Phase 1A (Tower D)
3rd Floor for Residential
1 |  | 3BHK | 1046.9228 | 613.548 | 1723.7712 | 3rd Floor for Residential
2 |  | 3BHK | 1046.9228 | 667.368 | 1737.2262
3 |  | 3BHK | 1060.0818 | 699.66 | 1765.0377
4 |  | 3BHK | 1049.9098 | 613.548 | 1728.2517
5 |  | 3BHK | 1049.9098 | 602.784 | 1725.5607
4th, 6th, 7th, 8th, 9th, 11th, 12th, 13th, 14th, 15th, 17th, 18th, 19th, 20th, 21st, 23rd, 24th,25th, 26th, 27th, 28th Floor
1 |  | 3BHK | 1048.5374 | 0 | 1572.8061 | 4th, 6th, 7th, 8th, 9th, 11th, 12th, 13th, 14th, 15th, 17th, 18th, 19th, 20th, 21st, 23rd, 24th,25th, 26th, 27th, 28th Floor |  |  |  |  | 301,..,2801 | 301 | 2801
2 |  | 3BHK | 1048.5374 | 0 | 1572.8061 | [5 empty] | 302,..,2802 | 302 | 2802
3 |  | 3BHK | 1060.0818 | 0 | 1590.1227 | [5 empty] | 303,..,2803 | 303 | 2803
4 |  | 3BHK | 1049.9098 | 0 | 1574.8647 | [5 empty] | 304,..,2804 | 304 | 2804
5 |  | 3BHK | 1049.9098 | 0 | 1574.8647 | [5 empty] | 305,..,2805 | 305 | 2805
5th, 10th, 16th, 22nd Floor (Part Refuge Area)
1 |  | 3BHK | 1048.5374 | 0 | 1572.8061 | 5th, 10th, 16th, 22nd Floor (Part Refuge Area) |  |  |  |  | 701,..,2201 | 701 | 2201
2 |  | 3BHK | 1048.5374 | 0 | 1572.8061 | [5 empty] | 702,..,2202 | 702 | 2202
3 |  | 3BHK | 1060.0818 | 0 | 1590.1227 | [5 empty] | 703,..,2203 | 703 | 2203
4 |  | Refuge Area | [8 empty] | 703,..,2203 | 703 | 2203
5 |  | 3BHK | 1049.9098 | 0 | 1574.8647 | [5 empty] | 704,..,2204 | 704 | 2204
Phase 1C (Tower E)
4th Floor for Residential
1 |  | 2BHK | 518.0175 | 519.0401 | 906.7863 | 4th Floor for Residential
2 |  | 1BHK | 391.9711 | 403.9729 | 688.9498
3 |  | 1BHK | 391.9711 | 403.9729 | 688.9498
4 |  | 1BHK | 391.9711 | 403.9729 | 688.9498
5 |  | 2BHK | 518.0175 | 519.0401 | 906.7863
6 |  | 2BHK | 518.0175 | 401.3896 | 877.3736
7 |  | Amenities Area
8 |  | 1BHK | 391.9711 | 333.2534 | 671.2699
9 |  | 1BHK | 391.9711 | 333.2534 | 671.2699
10 |  | 2BHK | 518.0175 | 403.5424 | 877.9118
5th, 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd, 34th & 35th Floor
1 |  | 2BHK | 549.5022 | 0 | 824.2533 | 5th, 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd, 34th & 35th Floor
2 |  | 1BHK | 422.3794 | 0 | 633.569
3 |  | 1BHK | 422.3794 | 0 | 633.569
4 |  | 1BHK | 422.3794 | 0 | 633.569
5 |  | 2BHK | 549.5022 | 0 | 824.2533
6 |  | 2BHK | 549.5022 | 0 | 824.2533
7 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 301,..,3501 | 301 | 3501
8 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 302,..,3502 | 302 | 3502
9 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 303,..,3503 | 303 | 3503
10 |  | 2BHK | 549.5022 | 0 | 824.2533 | [5 empty] | 304,..,3504 | 304 | 3504
7th, 12th, 17th, 22nd, 27th & 32nd Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th, 12th, 17th, 22nd, 27th & 32nd Floor (Part Refuge Area)
2 |  | 1BHK | 422.3794 | 0 | 633.569
3 |  | 1BHK | 422.3794 | 0 | 633.569
4 |  | 1BHK | 422.3794 | 0 | 633.569
5 |  | 2BHK | 549.5022 | 0 | 824.2533
6 |  | 2BHK | 549.5022 | 0 | 824.2533
7 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 301,..,3201 | 301 | 3201
8 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 302,..,3202 | 302 | 3202
9 |  | 1BHK | 422.3794 | 0 | 633.569 | [5 empty] | 303,..,3203 | 303 | 3203
10 |  | 2BHK | 549.5022 | 0 | 824.2533 | [5 empty] | 304,..,3204 | 304 | 3204
Phase 1C (Tower F)
4th Floor for Residential
1 |  | 2BHK | 593.9306 | 27.9864 | 918.8823 | 4th Floor for Residential
2 |  | 2BHK | 593.9306 | 27.9864 | 918.8823
3 |  | 2BHK | 497.2968 | 376.0942 | 839.9687
4 |  | Amenities Area
5 |  | 1BHK | 396.3036 | 333.2534 | 677.7687
6 |  | 2BHK | 497.2968 | 519.0401 | 875.7052
7 |  | 2BHK | 497.2968 | 519.0401 | 875.7052
8 |  | 3BHK | 864.5914 | 630.1784 | 1454.4317
5th, 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd, 34th & 35th Floor
1 |  | 2BHK | 625.1462 | 0 | 937.7193 | 5th, 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd, 34th & 35th Floor
2 |  | 2BHK | 625.1462 | 0 | 937.7193
3 |  | 2BHK | 525.2832 | 0 | 787.9248
4 |  | 1BHK | 424.29 | 0 | 636.435
5 |  | 1BHK | 424.29 | 0 | 636.435
6 |  | 2BHK | 525.2832 | 0 | 787.9248
7 |  | 2BHK | 525.2832 | 0 | 787.9248 | [5 empty] | 301,..,3501 | 301 | 3501
8 |  | 3BHK | 982.7263 | 0 | 1474.0894 | [5 empty] | 302,..,3502 | 302 | 3502
7th, 12th, 17th, 22nd, 27th & 32nd Floor (Part Refuge Area)
1 |  | 2BHK | 625.1462 | 0 | 937.7193 | 7th, 12th, 17th, 22nd, 27th & 32nd Floor (Part Refuge Area)
2 |  | 2BHK | 625.1462 | 0 | 937.7193
3 |  | 2BHK | 525.2832 | 0 | 787.9248
4 |  | 1BHK | 424.29 | 0 | 636.435
5 |  | 1BHK | 424.29 | 0 | 636.435
6 |  | 2BHK | 525.2832 | 0 | 787.9248
7 |  | 2BHK | 525.2832 | 0 | 787.9248 | [5 empty] | 301,..,3201 | 301 | 3201
8 |  | Refuge Area | [8 empty] | 302,..,3202 | 302 | 3202
Phase 1B (Tower G)
2nd Floor for Residential
1 |  | 1BHK | 370.9005 | 159.5763 | 636.1389 | 2nd Floor for Residential
2 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
3 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
4 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
5 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
6 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
7 |  | 1BHK | 370.9005 | 159.5763 | 636.1389
3rd to 33rd Floor
1 |  | 1BHK | 370.9005 | 0 | 556.3508 | 3rd to 33rd Floor
2 |  | 1BHK | 370.9005 | 0 | 556.3508
3 |  | 1BHK | 370.9005 | 0 | 556.3508
4 |  | 1BHK | 370.9005 | 0 | 556.3508
5 |  | 1BHK | 370.9005 | 0 | 556.3508
6 |  | 1BHK | 370.9005 | 0 | 556.3508
7 |  | 1BHK | 370.9005 | 0 | 556.3508
Phase 1A (Tower H)
2nd Floor for Residential & Parking
1 |  | Part Parking Area |  |  |  | 2nd Floor for Residential & Parking
2
3
4
5 |  | 2BHK | 658.1088 | 150 | 1062.1632
6 |  | 1BHK | 427.9982 | 31 | 672.9973
7 |  | 1BHK | 427.9982 | 31 | 672.9973
8 |  | 2BHK | 658.1088 | 150 | 1062.1632
3rd to 6th 8th to 11th 13th to 16th, 18th to 21st, 23rd & 24th Floor | [8 empty] | 176
1 |  | 2BHK | 658.1088 | 0 | 987.1632 | 3rd to 6th 8th to 11th 13th to 16th, 18th to 21st, 23rd & 24th Floor
2 |  | 1BHK | 427.9982 | 0 | 641.9973
3 |  | 1BHK | 427.9982 | 0 | 641.9973
4 |  | 2BHK | 658.1088 | 0 | 987.1632
5 |  | 2BHK | 658.1088 | 0 | 987.1632
6 |  | 1BHK | 427.9982 | 0 | 641.9973
7 |  | 1BHK | 427.9982 | 0 | 641.9973
8 |  | 2BHK | 658.1088 | 0 | 987.1632
7th, 12th, 17th & 22nd Floor (Part Refuge Area)
1 |  | 2BHK | 658.1088 | 0 | 987.1632 | 7th, 12th, 17th & 22nd Floor (Part Refuge Area)
2 |  | 1BHK | 427.9982 | 0 | 641.9973
3 |  | 1BHK | 427.9982 | 0 | 641.9973
4 |  | 2BHK | 658.1088 | 0 | 987.1632
5 |  | 2BHK | 658.1088 | 0 | 987.1632
6 |  | Refuge Area
7 |  | 1BHK | 427.9982 | 0 | 641.9973
8 |  | 2BHK | 658.1088 | 0 | 987.1632
Remarks:
1 | Tower A, B & C = All work completed. Please provide OC. Tower D, E, F, G & H = Construction Work is in process at the time of visit. Internal photo was not allowed.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + A.P Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Ms. Trupti : 7718831106.
7 | We have updated revised approved floor plan & C.C for D Tower, G Tower (3rd to33rd Floor) & H Tower (2nd to 24th Floor) (on 24/03/2023).
8 | Provide approved 3rd Floor plan for E & F Tower, Ground & 1st Floor plan for G Tower & Ground & 1st Floor plan for H Tower.
9 | We have updated revised approved floor plan & C.C for E, F Tower, G Tower (Gr + 1st to 2nd & 4th to 35th Floor) (on 29/03/2023).
10 | As checked on RERA portal on date 11/07/2025, we have observed that above project "Swaminarayan City Phase 1" is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram parshuram Lambore |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Swaminarayan City Phase 1, 1A, 1B & 1C
PHOTOGRAPHS OF PROPERTY : |  |  | Swaminarayan City Phase 1, 1A, 1B & 1C
Layout Plan:
Google Map :
Formulas:
Thakurli = [Thakurli, row above]
A, B & C Wing
G Wing
D Wing
H Wing
A , B & C
D
H
D Wing
A , B & C
D
H

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.9 | 4.94 | 14.326 | CB |  |  | 0 |  |  | 0
|  | 1.25 | 2.05 | 2.5625 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.13 | 2.9 | 6.177 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.76 | 3.2 | 8.832 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.05 | 3.2 | 9.76 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.35 | 1.82 | 2.457 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.23 | 2.15 | 2.6445 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.13 | 0.9 | 1.917 |  |  |  | 0 |  |  | 0
| passage2 | 1 | 0.9 | 0.9 |  |  |  | 0 |  |  | 0
| passage3 | 1.95 | 0.6 | 1.17 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  | 2.9 | 1.52 | 4.408 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 546.2299 | 50.746 |  |  | 47.4477 | 4.408 |  | 0 | 0
|  |  | 593.6777 | 55.154
21.75
3.48

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Swaminarayan City Phase I | 2BHK | 554.0231 | 886.4369 | 8460.8389 | 7500000
99 Acres | Swaminarayan City Phase I | 1BHK | 0 | 620 | 6290.3226 | 3900000
99 Acres | Swaminarayan City Phase I | 1BHK | 390 | 624 | 5368.5897 | 3350000
99 Acres | Swaminarayan City Phase I | 1BHK | 458 | 732.8 | 5867.9039 | 4300000
99 Acres | Swaminarayan City Phase I |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted