## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-10-03
Branch Name/ID |  | Mahindra Rural Housing Finance - Panvel |  |  | Date & Time of Site Visit | 04/10/2025 at 12:56
Name of the person met at site & Contact No |  | Mr. Arun Kumbar 8356853750 |  |  | Date of Report Release | 04/10/2025
Project Details
Name of the project |  | Omkara Pride Phase 1
Address |  | Omkara Pride Phase 1, Survey No.43/1/1 & 43/1/4, near Kamdhenu Lifespaces Gardenia, Ghot Road, Koynavele, Taloja Panchanand East, Panvel, Raigad - 410208. | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 43/1/1 & 43/1/4 | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Koynavele | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Ghot Road | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Taloja Panchanand East | [9 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Panvel | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Raigad | [9 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 410208 | [9 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P52000047562 | [12 empty] | Mahad | Daund
Landmark |  | Kamdhenu Lifespaces Gardenia | [12 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.082453,73.107606 | [9 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/KgMxwRQKBthrdKuW8 | [12 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Omkara Enterprises | [12 empty] | Mahasala | Bhor
Office address (agreement) |  | 909, 9th Floor, Mahavir Icon, Sector - 15, CBD Belapur 400614 | [12 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [12 empty] | Murud | Velhe
Builder Bank Details |  | Bank of Baroda IFSC Code - BARBOJUINAG
Contact No. |  | Mr. Arun 8356853750
Location of the project Municipal Limit : |  | Panvel Municipal Corporation
Project Type (Apartments/Plot/Combined) |  | Apartments
No of Wings / Buildings |  | Building No.1 (Wing A & B) |  |  | Other HFC's Approval / Funding | None |  | 33.75
No. of Tenements / Units in Project |  | Flats - 225 |  |  | Exposure Limit (Proposed) | 33.75 |  | Only Flats
Approved No. of Floor |  | Building No.1 (Wing A & B) = G + 1st to 14th Floor
Proposed No. of Floor |  | Building No.1 (Wing A & B) = G + 1st to 14th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | Koynavele Gaonthan | Gut No.43/1/1 | Gut No.43/1/3 | Gut No.43/1/5
|  | Approved Plan |  | S No. 41(Pt) / S No. 41 | 12.00 M Wide Approved Layout Road | S No. 43/1/2 & 3 S No.43/2 | S No. 43/1/5
|  | Physical on site |  | Open Plot | Ghot Road | Kamdhenu Lifespaces Gardenia | Riverside The Nest
Verification of survey No. (Title document) |  | Gut No.43 Hissa No.1/1 Gut No.43 Hissa No.1/4
Plot area mentioned in the sale deed (As per 7/12) |  | 11840 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 11840
Approach road |  | Yes, Approx 23ft
Connectivity |  | 1. Ajanta International School - 0.65Km 2. Radcliffe Group of Schools Ghotcamp - 1.2Km 3. Dmart Ready Taloja FC - 6.4Km 4. Town Bazaar - 2.8Km 5. Dr. Badade - Star Hospital - 3.3km 6. Apex Multi Speciality Hospital - 3.5Km 7. CIDCO Garden Phase 1 - 3.5Km 8. Owe Dam / Lake - 9.1Km 9. Pethali - Taloja Metro Station - 3.4Km 10.Taloja Panchanand Railway Station - 3.7Km
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 11840
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.5
|  | Total FSI availaible for the project |  |  |  | 3.6
|  | Total Proposed Builtup area of the project (Sq.Mt) |  |  |  | 34094.375
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 42624
|  | Total Approved Builtup area of the Building 1( Wing A & B) (Sq.Mt) |  |  |  | 15438.891
Building plan approvals - Approval No : |  | CARPC/RB/2024/APL/00095 |  |  |  | Date | 25/06/2024
Building height / No. of Floors |  | Building No.1 (Wing A & B) = Gr + 1st to 14th Floor (Height = 44.95 Mtrs)
Construction/Building Permission |  | PMC/TP/Koynavele/43/1/1 & 43/1/4/21-22/16374/1983/2022 Valid Upto - Building No.1 Wing A & B = G + 1st to 14th Floor (Total BUA = 15438.891 Sq. Mt) |  |  |  | Date | 2022-06-30
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA
|  | Validity & area : mentioned |  | NA
Fire NOC |  | PMC/Fire/2121/Ref No.1333/2024/1151 Building No.1 (Wing A & B) = Stilt + 1st to 14th Floor (Height = 44.95Mtrs) |  |  |  | Date | 2024-03-26
Airport NOC |  | NAVI/WEST/B/122218/356874 Site Elevation in mtrs AMSL = 9.97M Permissible Top Elevation in Mtr AMSL = 159.97M |  |  |  | Date Valid Upto Date | 17/01/2019 16/01/2027
Enviroment Clearcance Certificate No. |  | SIA/MH/INFRA2/413117/2023 Net Plot Area = 11840 Sq.mt Building 1 (Wing A to D) = S + 14 (Height = 44.95M) Building 2 (Wing E & F) = S + 14 (Height = 44.95M) |  |  |  | Date | 2024-02-08
CONSTRUCTION PROGRESS
Baseline start date |  | 2022-12-09 |  | Baseline finish date | 2027-10-31
Construction details:
Building No.1 (Wing A) = Gr + 1st + 14th Floor |  |  |  | Basement | Ground | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
|  |  |  | 0 | 1 | 0 | 14
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 3.5
Excavation |  | 0% |  | 14 | 100% | 90.36% |  | Excavation in process | 7
Plinth |  | 10% |  | 14 | 100% |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 40% |  | 15 | 100% |  |  | Footing in Process | 3.5
Brickwork |  | 15% |  | 14 | 100% |  |  | Footing Completed | 7
Internal Plaster |  | 5% |  | 14 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 14 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 13 | 92.86% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 12 | 85.71% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 5 | 35.71% |  |  | Plinth in process | 10.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 14
Building No.1 (Wing B) = Gr + 1st + 14th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 11 Floor, Painting upto 9 Floor Completed
|  |  |  | 0 | 1 | 0 | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 11 Floor, Painting upto 9 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 3.5
Excavation |  | 0% |  | 14 | 100% | 86.07% |  | Excavation in process | 7
Plinth |  | 10% |  | 14 | 100% |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 40% |  | 15 | 100% |  |  | Footing in Process | 3.5
Brickwork |  | 15% |  | 14 | 100% |  |  | Footing Completed | 7
Internal Plaster |  | 5% |  | 14 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 14 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 11 | 78.57% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 9 | 64.29% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 10.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 14
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Wing A) |  | 133 |  | 72346.7277 |  | 108520.0915
Building No.1 (Wing B) |  | 92 |  | 55489.604 |  | 83234.4061
Total |  | 225 |  | 127836.3317 |  | 191754.4976
Grand Total |  | 225 |  | 127836.3317 |  | 191754.4976
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Balcony Area + Chajja Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: | 10.764
50%
Phase 1
Building No.1 (Wing A) | [10 empty] | 6081.4959
Ground Floor For Entrance Lobby, Electric Room & Parking
1st Floor For Residential & Part Parking Area
1 |  | 2BHK | 580.9331 | 112.8605 | 693.7936 | 0 | 1040.6904 | 23.955 | 9.59
2 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762 | 40.545 | 10.2 | 6.225
3 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
4 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
5 |  | 2BHK | 564.0336 | 70.2351 | 634.2687 | 0 | 951.403
6 |  | Parking
7
8 | [8 empty] | 3.81
9 | [7 empty] | 25.465
10
2nd to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762 | 28.955 |  | 5176.688
2 |  | 2BHK | 564.0336 | 70.2351 | 634.2687 | 0 | 951.403 | 51.09
3 |  | 2BHK | 563.926 | 88.6415 | 652.5675 | 0 | 978.8512 | 48.825
4 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254 | 29.795
5 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
6 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254 |  |  | 5275.0046
7 |  | 2BHK | 580.9331 | 112.8605 | 693.7936 | 0 | 1040.6904 |  | 8.9
8 |  | 2BHK | 580.9331 | 112.8605 | 693.7936 | 0 | 1040.6904
9 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
10 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
8th & 13th Floor (Part Refuge Area)
1 |  | 1.5BHK | 588.8984 | 87.9957 | 676.8941 | 0 | 1015.3412 | 47.509
2 |  | Refuge Area | [7 empty] | 5219.9201
3 |  | 2BHK | 564.0336 | 88.6415 | 652.6751 | 0 | 979.0127 |  |  | 5311.4734
4 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
5 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
6 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
7 |  | 2BHK | 580.9331 | 112.8605 | 693.7936 | 0 | 1040.6904
8 |  | 2BHK | 580.9331 | 112.8605 | 693.7936 | 0 | 1040.6904
9 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
10 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
Building No.1 (Wing B)
Ground Floor For Entrance Lobby, Electric Room & Parking
1st Floor For Residential (Part Driver Room, Society Office & Parking)
1 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
2 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
3 |  | 2BHK | 564.0336 | 70.2351 | 634.2687 | 0 | 951.403
4 |  | Driver Room, Society Office & Parking
5 | [7 empty] | 27.745
6
7
2nd to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254 | 27.845
2 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
3 |  | 2BHK | 564.0336 | 88.6415 | 652.6751 | 0 | 979.0127 | 44.62
4 |  | 2BHK | 564.0336 | 70.2351 | 634.2687 | 0 | 951.403
5 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
6 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
7 |  | 3BHK | 930.8169 | 163.7204 | 1094.5373 | 0 | 1641.806 | 86.9529
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
2 |  | 1BHK | 388.688 | 77.6623 | 466.3503 | 0 | 699.5254
3 |  | 2BHK | 564.0336 | 88.6415 | 652.6751 | 0 | 979.0127
4 |  | Refuge Area
5 |  | 1.5BHK | 588.8984 | 87.9957 | 676.8941 | 0 | 1015.3412
6 |  | 1BHK | 385.6741 | 63.7767 | 449.4508 | 0 | 674.1762
7 |  | 3BHK | 930.8169 | 163.7204 | 1094.5373 | 0 | 1641.806 |  |  | 5542.6768
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5600 |  |  | 5400 to 5600 by rohan 21/04/2025
Recommended of Parking ( If Available) |  |  |  |  | 3,00,000/-
REMARKS ON RECOMMENDATION
1 | Wing A & B = Construction work is in process at the time of Visit. Internal visit was not allowed.
2 | AAC block, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose Balcony + Balcony Area + Chajja Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Kiran 8097366852
10 | We have updated EC & Airport Noc (On 25/02/2025).
Photographs Of Property : |  | Omkara Pride Phase 1
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Sunil Peravi |  | Authorized Signatory Name & Seal of the agency
Omkara Pride Phase 1
B
A
Bldg No.1
As per CC 30/06/2022 Builtup Area of building no.1 is same as per plan 25/06/2024 this date of plan newly amended beacuse new phase launched on plot as per mentiond layout plan
Wing A
Wing B
Phase 2
Phase 1
Wing C
N
N
Wing A
Wing B
Wing B
Wing A
Wing A
Wing A
Wing B
Wing A
Wing B
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C48: height should also be mentioned
Note on C57: RERA Start date
Note on F57: RERA completion date
Note on H89: if multiple buildings are in project and are connected internally
Note on C91: AAC Block or Brick
Note on H93: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3