## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-04-02
Branch Name/ID | Mahindra Rural Housing Finance - Panvel |  |  | Date & Time of Site Visit | 02/04/2025 at 01:41PM
Name of the person met at site & Contact No | Ms. Simran 9324984421 |  |  | Date of Report Release | 02/04/2025
Project Details
Name of the project | Mangalam
Address | Mangalam, Old Gut No.149/1, New Gut No. 19/1, near Super Ispat, Internal Road, Dharna Camp, Taloja Panchnand East, Panvel, Raigad - 410208. | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Old Gut No | 149/1, New Gut No. 19/1 | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village | Dharna Camp | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road | Internal Road | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City | Taloja Panchnand East | [7 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka | Panvel | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District | Raigad | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode | 410208 | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- | P52000032461 | [10 empty] | Mahad | Daund
Landmark | Super Ispat | [10 empty] | Roha | Mawal
Geo Coordinates | Latitude, Longitude |  | 19.098340,73.079046 | [8 empty] | Mangaon | Ambegaon
Geo Link | https://maps.app.goo.gl/WVbWz88bGejvbyRw7 | [10 empty] | Poladpur | Purandhar
Name of the builder / developer | Today Prachar Developers LLP | [10 empty] | Mahasala | Bhor
Office address (agreement) | Kesar Solitaire, Office No.-1601 & 1602, 16th Floor, Plot No.-05, Sector No.-19, Palm Beach Road, Sanpada, Navi Mumbai, Tal & Dist. Thane 400705 | [10 empty] | Shriwardhan | Mulshi
Builder Office Verified | No | [10 empty] | Murud | Velhe
Builder Bank Details | Bank Name - ICICI Bank Limited IFSC Code - ICIC0006990
Contact No. | Mr. Nikhil Daur 8779525273
Location of the project Municipal Limit : | Panvel Municipal Corporation
Project Type (Apartments/Plot/ Combined) | Apartments + Shops
No of Wings / Buildings | Building No. 1 (Wing A & B) Building No. 2 (Wing C ) |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project | Shop = 8 Flat = 327 |  | Exposure Limit (Proposed) | 49.05
Verification of the schedule of the property | Description | North | South | East | West
| Sale deed | NA | NA | NA | NA
| Approved Plan | Other Plot | Old S. No.149/2, New S.No.19/2 12.00 M Wide Row | Other Plot | Other Plot
| Physical on site | Open Plot | Internal Road | Open Plot | Open Plot
Verification of survey No. (Title document) | Survey No. 19/1
Plot area mentioned in the sale deed (As per 7/12) | 9975.508 Sq.M | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 8183.057 Sq.M |  | 8183.0573
Approach road | Yes, Approx 9ft
Connectivity | SCHOOL : Shree Chhatrapati Shivaji High School Rohinjan - 1.1Km Raja Prasenjeet Public School & Junior College, Rohinjan - 1.3Km SHOPPING : Vighnahar Complex - 9.0Km Prime Mall - 9.2Km HOSPITALS : Ayesha Hospital - 4.0Km Tata Memorial Hospital - 6.4Km PETROL PUMP : Bharat Petroleum - 800M Jio-Petrol Pump - 2.3Km
Approval Detail : Plan approval
Layout approval if applicable | Total land area of the project in Sq. Mt. |  |  | 8183.057
| Permissible FSI |  |  | 1.1
| Permissible TDR/Paid FSI |  |  | 1.2181
| Total FSI availaible for the project |  |  | 2.3181
| Total Permissible Builtup area of the project (Sq.Mt) |  |  | 18978.18 |  |  | 18969.046
| Total Approved Builtup area of the project (Sq.Mt) |  |  | 18969.046
Building plan approvals - Approval No : | PMP/NRV/16184/JK-2441/2021 Date - 30/11/2021
Building height / No. of Floors | Building No.1 (Wing A & B) = 40.40 M Building No.2 ( Wing C) = 40.50 M
Construction/Building Permission | PMC/TP/Dharna Camp/19/1/21-21/16184/2441/2021 Date - 30/11/2021 Valid Upto - Building No. 1 (A & B Wing) = Gr + 1st to 11th Floor. Building No. 2 (C Wing) = Gr + 1st to 11th Floor
NA / Land conversion | Name of the authority : | NA
| Reference No : | NA
| Validity & area : mentioned | Date - - Valid For one Year. Area - Sq.Mt.
Other statutory permissions
Mahatransco NOC Valid upto | CE/EHV/PC O&M/Zone/VSH/EE/Tech/No.02425 Date:29/10/2021 Survey No.19/1, At. Dansar, Tal - Panvel, Dist. Raigad Right of Way of 35 Meter (i.e 17.5 Mt on either side from the center line of Tower) for 220 KV line) | [6 empty] | Other statutory permissions (Fire NOC/ Environmental Clearance/ Airport NOC)
Airport NOC Valid upto | NAVI/WEST/B/100819/432115 Date -: 09/10/2019 Site Elevation = 18.85 Mtrs (AMSL ) Permissible Top Elevation = 68.85 Mtrs (AMSL)
CONSTRUCTION PROGRESS
Baseline start date | 2021-11-30 | Baseline finish date | 2025-12-31
Construction details: | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Building No. 1 (Wing A) = G/St + 1st to 11th Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 11 | All work Completed. OC Received.
Stage of construction: | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | Piling Work in process | 2.75
Type of Work | Project Progress % | Slab/Floor | Complition % | Progress % |  | Excavation in process | 5.5
Excavation | 0% | 11 | 100% | 91.36% |  | Excavation Completed | 11
Plinth | 10% | 11 | 100% |  |  | Footing in Process | 2.75
RCC (Including podiums) | 40% | 12 | 100% |  |  | Footing Completed | 5.5
Brickwork | 15% | 11 | 100% |  |  | Basement 1 | 0
Internal Plaster | 5% | 11 | 100% |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | 5% | 11 | 100% |  |  | Basement 3 | 0
Flooring & Fitting | 10% | 11 | 100% |  |  | Basement 4 | 0
Painting & Wooden | 5% | 10 | 90.91% |  |  | Plinth in process | 8.25
Building Common Amenities | 5% | 4 | 36.36% |  |  | Plinth completed | 11
Possession | 5% | 0 | 0% |  |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Building No. 1 (Wing B) = G/St + 1st to 11th Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 11 | All work Completed. OC Received.
Stage of construction: | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | Piling Work in process | 2.75
Type of Work | Project Progress % | Slab/Floor | Complition % | Progress % |  | Excavation in process | 5.5
Excavation | 0% | 11 | 100% | 91.82% |  | Excavation Completed | 11
Plinth | 10% | 11 | 100% |  |  | Footing in Process | 2.75
RCC (Including podiums) | 40% | 12 | 100% |  |  | Footing Completed | 5.5
Brickwork | 15% | 11 | 100% |  |  | Basement 1 | 0
Internal Plaster | 5% | 11 | 100% |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | 5% | 11 | 100% |  |  | Basement 3 | 0
Flooring & Fitting | 10% | 11 | 100% |  |  | Basement 4 | 0
Painting & Wooden | 5% | 10 | 90.91% |  |  | Plinth in process | 8.25
Building Common Amenities | 5% | 5 | 45.45% |  |  | Plinth completed | 11
Possession | 5% | 0 | 0% |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 9 Floor Completed
Building No. 2 (Wing C) = Gr + 1st to 11th Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 11 | All work Completed. OC Received.
Stage of construction: | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 9 Floor Completed |  |  |  |  | Piling Work in process | 2.75
Type of Work | Project Progress % | Slab/Floor | Complition % | Progress % |  | Excavation in process | 5.5
Excavation | 0% | 11 | 100% | 74.09% |  | Excavation Completed | 11
Plinth | 10% | 11 | 100% |  |  | Footing in Process | 2.75
RCC (Including podiums) | 40% | 12 | 100% |  |  | Footing Completed | 5.5
Brickwork | 15% | 11 | 100% |  |  | Basement 1 | 0
Internal Plaster | 5% | 11 | 100% |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | 5% | 9 | 81.82% |  |  | Basement 3 | 0
Flooring & Fitting | 10% | 0 | 0% |  |  | Basement 4 | 0
Painting & Wooden | 5% | 0 | 0% |  |  | Plinth in process | 8.25
Building Common Amenities | 5% | 0 | 0% |  |  | Plinth completed | 11
Possession | 5% | 0 | 0%
General comment on progress | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure | RCC | Expansion Joint Available |  | Yes/No | Yes
Mortar Type | Cement & Sand | Flood Prone Area |  | Yes/No | No
Masonry Type | AAC Block | Projected Parts Available |  | Yes/No | Yes
Footing Type | Isolated Footing | Fire Exit Available |  | Yes/No | Yes
Soil Type | Alluvial Soil | Ground Slope >20% |  | Yes/No | No
Concrete Grade | M20 | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade | FE415 | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) | 44 meter per sec | Coastal regulatory Zone |  | No
Seismic Zone | III | Environment exposure condition |  | Moderate
Commercial Area Details : Shops
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No.2 (Wing C) | 8 | 982.1074 |  | 1473.161
Total | 8 | 982.1074 |  | 1473.161
Residential Area Details : Flats | [5 empty] | 10.26
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No.1 (Wing A) | 87 | 39762.4205 |  | 57655.5097
Building No.1 (Wing B) | 120 | 49762.9408 |  | 72156.2641
Building No.2 (Wing C) | 120 | 51781.729 |  | 75200.9691
Total | 327 | 141307.0902 |  | 205012.743
Grand Total | 335 | 142289.1976 |  | 206485.904
BUILDING / BLOCK - Configuration Details
Floors | Flat / Unit No | Flat / Unit Area (Carpet Area) Sq. Ft. | Attached Terrace Area Sq. Ft. | Saleable Area Sq.Ft. Loading: | Remark (Commercial Configuration )
50%
Building No. 2
Wing C
Ground Floor For Commercial, Society Office, Driver's Room, Meter Room & Parking
Ground Floor For Commercial, Society Office, Driver's Room, Meter Room & Parking | 1 | 110.4386 | 0 | 165.658 | Shop
| 2 | 112.3762 | 0 | 168.5642 | Shop | 11.76 | 2.25
| 3 | 126.5846 | 0 | 189.877 | Shop | 13.16
| 4 | 141.6542 | 0 | 212.4814 | Shop | 13.44
| 5 | 144.6682 | 0 | 217.0022 | Shop | 11.48
| 6 | 123.5707 | 0 | 185.3561 | Shop
| 7 | 112.3762 | 0 | 168.5642 | Shop | 10.26
| 8 | 110.4386 | 0 | 165.658 | Shop
Floors | Flat / Unit No | Flat / Unit Area (Carpet Area) Sq. Ft. | Attached Terrace Area Sq. Ft. | Saleable Area Sq.Ft. Loading: | Remark (Flat configuration /Bungalows, etc.)
45%
Building No.1
Wing A
Ground Floor For Society Office, Driver's Room, Meter Room, Waiting Area & Parking
1st to 7th & 9th to 11th Floor for Residential | [5 empty] | 46.38
1st to 7th & 9th to 11th Floor for Residential | 1 | 547.7477 | 0 | 794.2341 | 2BHK
| 2 | 547.7477 | 0 | 794.2341 | 2BHK | 30.006
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 547.7477 | 0 | 794.2341 | 2BHK
| 6 | 547.7477 | 0 | 794.2341 | 2BHK
| 7 | 364.2215 | 0 | 528.1211 | 1BHK
| 8 | 364.2215 | 0 | 528.1211 | 1BHK
8th Floor (Part Refuge Area)
8th Floor (Part Refuge Area) | 1 | 547.7477 | 0 | 794.2341 | 2BHK
| 2 | 547.7477 | 0 | 794.2341 | 2BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 547.7477 | 0 | 794.2341 | 2BHK
| 6 | 547.7477 | 0 | 794.2341 | 2BHK
| 7 | 364.2215 | 0 | 528.1211 | 1BHK
| 8 | Refuge Area
Wing B
Ground Floor For Meter Room, Waiting Area & Parking
1st to 7th & 9th to 11th Floor For Residential
1st to 7th & 9th to 11th Floor For Residential | 1 | 547.7477 | 0 | 794.2341 | 2BHK
| 2 | 364.2215 | 0 | 528.1211 | 1BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 364.2215 | 0 | 528.1211 | 1BHK
| 6 | 547.7477 | 0 | 794.2341 | 2BHK
| 7 | 547.7477 | 0 | 794.2341 | 2BHK
| 8 | 364.2215 | 0 | 528.1211 | 1BHK
| 9 | 364.2215 | 0 | 528.1211 | 1BHK
| 10 | 364.2215 | 0 | 528.1211 | 1BHK
| 11 | 364.2215 | 0 | 528.1211 | 1BHK
8th Floor (Part Refuge Area)
8th Floor (Part Refuge Area) | 1 | 547.7477 | 0 | 794.2341 | 2BHK | 29.905
| 2 | 364.2215 | 0 | 528.1211 | 1BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 364.2215 | 0 | 528.1211 | 1BHK
| 6 | 547.7477 | 0 | 794.2341 | 2BHK
| 7 | 547.7477 | 0 | 794.2341 | 2BHK | 6.1837
| 8 | 364.2215 | 0 | 528.1211 | 1BHK
| 9 | Refuge Area
| 10 | 364.2215 | 0 | 528.1211 | 1BHK
| 11 | 364.2215 | 0 | 528.1211 | 1BHK
Building No. 2
Wing C
1st Floor For Residential
1st Floor For Residential | 1 | 364.2215 | 0 | 528.1211 | 1BHK
| 2 | 364.2215 | 0 | 528.1211 | 1BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 364.2215 | 0 | 528.1211 | 1BHK
| 6 | 364.2215 | 0 | 528.1211 | 1BHK
| 7 | 547.7477 | 58.7311 | 852.9652 | 2BHK
| 8 | 547.7477 | 58.7311 | 852.9652 | 2BHK
| 9 | 364.2215 | 0 | 528.1211 | 1BHK
| 10 | 547.7477 | 0 | 794.2341 | 2BHK
| 11 | 547.7477 | 0 | 794.2341 | 2BHK
2nd to 7th & 9th to 11th Floor
2nd to 7th & 9th to 11th Floor | 1 | 364.2215 | 0 | 528.1211 | 1BHK
| 2 | 364.2215 | 0 | 528.1211 | 1BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | 364.2215 | 0 | 528.1211 | 1BHK
| 6 | 364.2215 | 0 | 528.1211 | 1BHK
| 7 | 547.7477 | 0 | 794.2341 | 2BHK
| 8 | 547.7477 | 0 | 794.2341 | 2BHK
| 9 | 364.2215 | 0 | 528.1211 | 1BHK
| 10 | 547.7477 | 0 | 794.2341 | 2BHK
| 11 | 547.7477 | 0 | 794.2341 | 2BHK
8th Floor (Part Refuge Area)
8th Floor (Part Refuge Area) | 1 | 364.2215 | 0 | 528.1211 | 1BHK
| 2 | 364.2215 | 0 | 528.1211 | 1BHK
| 3 | 364.2215 | 0 | 528.1211 | 1BHK
| 4 | 364.2215 | 0 | 528.1211 | 1BHK
| 5 | Refuge Area
| 6 | 364.2215 | 0 | 528.1211 | 1BHK
| 7 | 547.7477 | 0 | 794.2341 | 2BHK
| 8 | 547.7477 | 0 | 794.2341 | 2BHK
| 9 | 364.2215 | 0 | 528.1211 | 1BHK
| 10 | 547.7477 | 0 | 794.2341 | 2BHK
| 11 | 547.7477 | 0 | 794.2341 | 2BHK
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  | 7400
Recommended of Parking ( If Available) |  |  | 3,00,000/-
REMARKS ON RECOMMENDATION
1. Building No. 1 Finishing Work is in process and Building No. 2 construction work is in process at the time of visit. 2. AAC block, Cement bags, aggregate, Sand, etc found on site in average quantity. 3. 4 to 5 labours found on site at the time of visit. 4. We considered Carpet area as per Approved Plan. 5. We considered Saleable area as per our calculation. (i.e 50% Loading) 6. We considered Gross carpet area = Net carpet + Balcony Area 7. We have considered rate by verifying it from market inquire. 8. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 9. Car parking is subjected to authentic documentation. 10. On Site, we meet Ms. Simran 9324984421.
Photographs Of Property : | Mangalam
Layout Of Property :
Google Map :
Name of Engineer Visited the property | Mr. Sunil Peravi | Authorized Signatory Name & Seal of the agency
N
N
Building No.1 Wing B
Building No.1 Wing A
Building No.2 Wing C
High Tension Lines
High Tension Lines
Wing A
Wing B
Wing C
C Wing
C Wing
Wing C
Wing B
Wing A
Wing C
Wing C
Wing C
Note on A9: SACHIN: As per CC
Note on B9: Take address from CC
Note on B21: Builder's office address from RERA
Note on B24: Provided during initiation
Note on B25: Authority
Note on B26: Apartments or Apartments + Shops
Note on E28: 15% of Total No of Flats
Note on C30: If Sale deed is provided
Note on D30: If Sale deed is provided
Note on E30: If Sale deed is provided
Note on F30: If Sale deed is provided
Note on B45: height should also be mentioned
Note on B54: RERA Start date
Note on D54: RERA completion date
Note on F100: if multiple buildings are in project and are connected internally
Note on B102: AAC Block or Brick
Note on F104: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3
110.4386
112.3762
121.2026
120.1262
144.6682
144.6466
112.3762
110.331