## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-10-04
Branch Name/ID |  | Mahindra Rural Housing Finance - Virar |  |  | Date & Time of Site Visit | 04/10/2025 at 12:43
Name of the person met at site & Contact No |  | Mr. Prem Singh 7977712298 |  |  | Date of Report Release | 06/10/2025
Project Details
Name of the project |  | Jade Gardens
Address |  | Jade Gardens, Survey No.828/3/B, near Magnus Nirman Complex, Internal Road, Mahim, Palghar West, Palghar, Palghar - 401404. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 828/3/B | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Mahim | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Internal Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Palghar West | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Palghar | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Palghar | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 401404 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P99000048402 | [11 empty] | Mahad | Daund
Landmark |  | Magnus Nirman Complex | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.680134,72.745534 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/smGjq9W5xUxekKcbA | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s. Niwas Lifespaces LLP | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Office No. 405, K.P. Aurum Building, Marol Maroshi Road, Opposite Uttam Dhaba, Andheri East, Andheri 400059. | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | Bank Name - ICICI Bank A/c Name - 104405005111 IFSC Code - ICIC0001044
Contact No. |  | Ms. Priti Powar 8169460126
Location of the project Municipal Limit : |  | Collector Of Palghar
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | Building No.1 (Wing A & B) Building No.2 (Wing C & D) |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flat = 213 |  |  | Exposure Limit (Proposed) | 31 |  | 31.95
Approved No. of Floor |  | Building No.1 (A & B Wing) = Gr/St + 1st to 7th Floor Building No.2 (C & D Wing) = Gr/St + 1st to 7th Floor
Proposed No. of Floor |  | Building No.1 (A & B Wing) = Gr/St + 1st to 7th Floor Building No.2 (C & D Wing) = Gr/St + 1st to 7th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | 9.00 M Wide Road | Other Plot | Other Plot | Other Plot
|  | Physical on site |  | Internal Road | Open Plot | Building | Open Plot
Verification of survey No. (Title document) |  | Survey No.828, Hissa No.3/B
Plot area mentioned in the sale deed (As per 7/12) |  | 4000 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 3902.67
Approach road |  | Yes, Approx 15ft
Connectivity |  | 1. 0.85km from Sir J. P. International School 2. 1.2km from JDS Pal English High School 3. 3.0km from Sharda Hospital 4. 3.5km from Rural Hospital 5. 2.6km from B Mart 6. 3.9km from Vijay Super Market 7. 0.24km from Vagulsar Vighnaharta Ganesh 8. 0.55km from Mahakali Mata Mandir 9. 0.29km from Vagulsar Bus Stop 10.3.5km from Palghar Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 3902.67
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.1918
|  | Total FSI availaible for the project |  |  |  | 2.2918
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 8944.43
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8944.21
Building plan approvals - Approval No : |  | Mahasul/K-1/Mej1/B.S.P/S.R/C.R/339/2021 |  |  |  | Date | 2022-10-18
Building height / No. of Floors |  | Building No.1 (A & B Wing) = Gr/St + 1st to 7th Floor (Height = 23.25 Mtrs) Building No.2 (C & D Wing) = Gr/St + 1st to 7th Floor (Height = 23.25 Mtrs)
Construction/Building Permission Valid Upto |  | Mahasul/KS-1/T-1/NAP/SR-339/2021 Building No.1 (A & B Wing) = Gr/St + 1st to 7th Floor Building No.2 (C & D Wing) = Gr/St + 1st to 7th Floor |  |  |  | Date | 2022-10-18
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: | [5 empty] | Date
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2023-01-03 |  | Baseline finish date |  | 01/10/2029
Construction details:
Building No.1 (Wing A & B) = Gr/St + 1st to 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 80.71% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 7 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 4 | 57.14% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
Building No.2 (C Wing) = Gr/St + 1st to 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor, Painting upto 3 Floor Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 82.86% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 7 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 4 | 57.14% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 3 | 42.86% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
Building No.2 (D Wing) = Gr/St + 1st to 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 3 Floor Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 84.29% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 7 | 100% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 5 | 71.43% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 3 | 42.86% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 | Wing A | 55 |  | 21159.2254 |  | 30680.8768 |  | OK
| Wing B | 55 |  | 18552.1846 |  | 26900.6676 |  | OK
Building No.2 | Wing C | 55 |  | 18552.1846 |  | 26900.6676 |  | OK
| Wing D | 48 |  | 16018.9848 |  | 23227.528 |  | OK
Total |  | 213 |  | 74282.5793 |  | 107709.74
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No. 1
Wing A
Ground Floor For Entrance Lobby & Parking | [7 empty] | 1977080
1st to 6th Floor For Residential | [7 empty] | Housing |  | 4500
1 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886 | 4531.1548 | 4479.2278 | 1986248.628
2 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886 | 4757.7125 |  | 1986248.628
3 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886 |  |  | 1986248.628
4 |  | 2BHK | 482.5501 | 32.8302 | 515.3803 | 0 | 747.3015 | 4683.5182 |  | 3362856.588
5 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042 | 4866.6518 |  | 2126718.828
6 |  | 2BHK | 479.6438 | 32.8302 | 512.474 | 0 | 743.0874 |  |  | 3343893.111
7 |  | 2BHK | 473.2931 | 0 | 473.2931 | 0 | 686.275 |  |  | 3088237.347
8 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042 |  |  | 2126718.828
7th Floor For Residential & Part Society Office | [7 empty] | vxcv
1 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
2 |  | Society Office
3 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
4 |  | 2BHK | 482.5501 | 32.8302 | 515.3803 | 0 | 747.3015
5 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042 | 4866.6518
6 |  | 2BHK | 479.6438 | 32.8302 | 512.474 | 0 | 743.0874
7 |  | 2BHK | 473.2931 | 0 | 473.2931 | 0 | 686.275
8 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
Wing B
Ground Floor For Entrance Lobby & Parking
1st to 6th Floor For Residential
1 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
2 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
3 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
4 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
5 |  | 2BHK | 478.1369 | 0 | 478.1369 | 0 | 693.2985
6 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
7 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
8 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
7th Floor For Residential & Part Driver Room
1 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
2 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
3 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
4 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
5 |  | 2BHK | 478.1369 | 0 | 478.1369 | 0 | 693.2985
6 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
7 |  | Driver Room
8 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
Building No. 2
Wing C
Ground Floor For Entrance Lobby & Parking
1st to 6th Floor For Residential
1 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
2 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
3 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
4 |  | 2BHK | 478.1369 | 0 | 478.1369 | 0 | 693.2985
5 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
6 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
7 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
8 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
7th Floor For Residential & Part Society Office
1 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
2 |  | Society Office
3 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
4 |  | 2BHK | 478.1369 | 0 | 478.1369 | 0 | 693.2985
5 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
6 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
7 |  | 1BHK | 325.2881 | 0 | 325.2881 | 0 | 471.6677
8 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
Wing D
Ground Floor For Entrance Lobby & Parking
1st to 6th Floor For Residential
1 |  | 1BHK | 326.5798 | 0 | 326.5798 | 0 | 473.5407
2 |  | 2BHK | 450.0428 | 0 | 450.0428 | 0 | 652.5621
3 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
4 |  | 1BHK | 316.1387 | 0 | 316.1387 | 0 | 458.4011
5 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
6 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
7 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
7th Floor For Residential & Part Driver Room
1 |  | 1BHK | 326.5798 | 0 | 326.5798 | 0 | 473.5407
2 |  | 2BHK | 450.0428 | 0 | 450.0428 | 0 | 652.5621
3 |  | 1BHK | 325.9339 | 0 | 325.9339 | 0 | 472.6042
4 |  | 1BHK | 316.1387 | 0 | 316.1387 | 0 | 458.4011
5 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
6 |  | Driver Room
7 |  | 1BHK | 304.4059 | 0 | 304.4059 | 0 | 441.3886
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 4700
Development Charges |  |  |  |  | 100000
Recommended of Parking (If Available) |  |  |  |  | 1,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 45%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Prem Singh 7977712298
Photographs Of Property : |  | Jade Gardens
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Yadnesh Patil |  | Authorized Signatory Name & Seal of the agency
Wing A
Wing B
Wing C
Wing D
Building No.1
Building No.2
B
D
C
A
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C60: RERA Start date
Note on H106: if multiple buildings are in project and are connected internally
Note on C108: AAC Block or Brick
Note on H110: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3