## Report
1302-ELLORA FIESTA, PLOT NO. 8, SECTOR 11, OPP. JUINAGAR RAILWAY STATION, SANPADA, NAVI MUMBAI 400 706. TEL: 022-27758396/95. FAX :022-27758394. E mail : axisbank@vsjadon.com. vsjcvaluer@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 03/09/2021.
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  | 05/11/2020. |  | 10/08/2021.
Name of the builder group |  | M/s.Abhishek Mahesh Chowdhary |  | M/s.Abhishek Mahesh Chowdhary
Name of the builder company |  | M/s.Abhishek Mahesh Chowdhary |  | M/s.Abhishek Mahesh Chowdhary
Name of the Project |  | Devashree Apartment |  | Devashree Apartment
Contect Details ( Name & Contect No.) |  | 9819543514 |  | 9819543514
Name / No of the Building |  | Building No.1 - Wing A |  | Building No.1 - Wing A (Type A1)
Docouments Provided |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  | P99000022579 |  | P99000022579
Project location details | Devashree Apartment, Survey No.380 & H No.13 , Mahim - Palghar Road, Mahim, Palghar, Palghar, Palghar.
Survey No | 380 & H No.13
Road | Mahim - Palghar Road |  |  | Village |  | Mahim
City | Palghar | District |  | District |  | Palghar
Taluka | Palghar | Pin Code |  | Pin Code |  | 401402
Near by Landmark | J P International School | Distance from city centre: |  | Distance from city centre: |  | 3.9Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage |  | Yes |  | Yes | Yes | Yes | Yes
Class of locality |  | Middle Class |  | Middle Class | Middle Class | Middle Class | Middle Class
Nature of land with topographical condtion |  | Plane |  | Plane | Plane | Plane | Plane
Nature of the locality |  | Developing |  | Developing | Developing | Developing | Developing
Quality of infrastructure in vicinity |  | Good |  | Good | Good | Good | Good
Type of Structure |  | RCC Frame Structure |  | RCC Frame Structure | RCC Frame Structure | RCC Frame Structure | RCC Frame Structure
Approved usage of the Property: |  | Residential + Commercial |  | Residential + Commercial | Residential + Commercial | Residential + Commercial | Residential + Commercial
Restrictive Covenants in regard to Land Use |  | No |  | No | No | No | No
Boundries |  | As per deed |  |  | At site
East |  | NA |  |  | Open Plot | Open Plot | Open Plot
West | NA | NA | NA | NA | Road | Road | Road
North | NA | NA | NA | NA | Open Plot | Open Plot | Open Plot
South | NA | NA | NA | NA | Open Plot | Open Plot | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.675 |  | Longitude | 72.7446
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 510
Permissible FSI |  | 1 |  | 1 | 1 | 1 | 1
Permissible TDR/Paid FSI |  | 0 |  | 0.2 | 0 | 0 | 0
Total FSI availaible for the project |  |  |  | 1.2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 612
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | MHASUL/KS.1/MJ.1/ANAP/SR/192/16 |  |  | Dated | 19/08/2017.
Approved Floor plan No. |  | MHASUL/KS.1/MJ.1/ANAP/SR/192/16 |  |  | Dated | 19/08/2017.
Commencement Certificate No. |  | MHASUL/KS.1/T.1/ANAP/SR/192/16 |  |  | Dated | 19/08/2017.
Valid Up to: Building No.1- A Wing(Type A1) = Gr. + 1st to 3rd Floor
O. Certificate No.: |  | NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 510
Approved no of units |  |  | Flats-13 & Shop- 05
Approved no of Floors |  |  | Building No.1- A Wing(Type A1) = Gr. + 1st to 3rd Floor
Proposed no of Floors |  |  | Building No.1- A Wing(Type A1) = Gr. + 1st to 3rd Floor
Expected Completion |  |  | As per RERA - 30/06/2022.
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.1(A Wing) = Gr. + 1st to 3rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 2.5 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 2.5 Floor, Painting upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 85% |  | 94.17% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% |  |  |  |  | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2.5 | 83.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 33.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 2.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5500
Recommended rate of Parking |  |  |  |  | 100000/-
Distressed valuation of the Property |  |  |  |  | 2720
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 5 |  | 516.3491 |  | 774.5236
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 13 |  | 5015.2682 |  | 7272.1389
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1 - A Wing (Type A1)
Ground Floor for Commercial, Residential & Parking
1 |  | Shop | 98.2753 | 0 | 147.413 | Ground Floor for Commercial, Residential & Parking
2 |  | Shop | 106.5636 | 0 | 159.8454 | Ground Floor for Commercial, Residential & Parking
3 |  | Shop | 106.133 | 0 | 159.1996 | Ground Floor for Commercial, Residential & Parking
4 |  | Shop | 98.8135 | 0 | 148.2203 | Ground Floor for Commercial, Residential & Parking
5 |  | Shop | 106.5636 | 0 | 159.8454 | Ground Floor for Commercial, Residential & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Building No.1 - A Wing (Type A1)
Ground Floor for Commercial, Residential & Parking
1 |  | 1BHK | 404.834 | 0 | 587.0094 | Ground Floor for Commercial, Residential & Parking
1st to 3rd Floor
101 to 301 |  | 1BHK | 398.628 | 0 | 578.0105 | 1st to 3rd Floor |  | 2023036.8463 | 1965235.7935 | 1734031.5825
102 to 302 |  | 1BHK | 379.5739 | 0 | 550.3822 | 1st to 3rd Floor |  | 1926337.5425 | 1871299.327 | 1651146.465
103 to 303 |  | 1BHK | 370.639 | 0 | 537.4265 | 1st to 3rd Floor |  | 1880992.6713 | 1827250.0235 | 1612279.4325
104 to 304 |  | 1BHK | 387.9706 | 0 | 562.5574 | 1st to 3rd Floor |  | 1968950.795 | 1912695.058 | 1687672.11
Remarks:
1. Construction work has increased as compare to last visit (05/11/2020) but at the time of visit no active work found on site. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4.We have updated Approved Floor plan (on 03/09/2021). 4. On Site, we meet Mr.Love (Sales) - 9226733391.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Bhavesh |  | Report By : |  | Dhanashree
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY :
Google Map :

## C% for old Flormat
Add 14 Black Row in OLD APF format
1 | Construction details: |  | Building No. = G + 20th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
2 | Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 20
3 | Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [6 empty] | All work Completed. OC Received.
4 | Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 5
5 | Excavation |  | 20 | 100% |  | 50% |  | 75% |  | Excavation in process | 10
6 | Plinth |  | 20 | 100% | [5 empty] | Excavation Completed | 20
7 | RCC (Including podiums) |  | 21 | 100% | [5 empty] | Footing in Process | 5
8 | Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 10
9 | Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
10 | Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
11 | Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
12 | Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
13 | Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 15
14 | Possession |  | 0 | 0% | [5 empty] | Plinth completed | 20
[6 empty] | 50% |  | 75%

## C% for new format
Construction details: |  | Building No. = G + 20th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
|  |  |  | 50% |  | 75%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted